The Secretary

Department of Treasury and Finance

1 Treasury Place

Melbourne Victoria 3002

Australia

Telephone: +61 3 9651 5111

Facsimile: +61 3 9651 5298

www.dtf.vic.gov.au

Authorised by the Victorian Government

1 Treasury Place, Melbourne, 3002

© Copyright State of Victoria 2010

This book is copyright. No part may be reproduced by any process except in accordance with the provisions of the Copyright Act 1968.

ISBN 978-1-922045-83-6

Published July 2012.

If you would like to receive this publication in an accessible format please telephone 9651 0909 or email mailto:information@dtf.vic.gov.au

This document is also available in PDF format at www.dtf.vic.gov.au

Acknowledgments

The information in this workbook is based on material published in the Victorian Department of Treasury and Finance's investment lifecycle and high value/ high risk guidelines, and by the UK Office of Government Commerce (OGC). OGC Gateway™ is a trademark of the UK Cabinet Office and is owned and published by that Office. OGC Gateway™ is subject to Crown Copyright protection and reproduced under licence with kind permission of Controller of Her Majesty’s Stationery Office (HMSO) and the Cabinet Office.

Contents

1.	The Gateway review process	5

1.1	About the Gateway review process	5

1.2	About this booklet	5

2.	Stage 1: Conceptualise	7

2.1	Gate 1: Concept and feasibility	7

2.2	Aim of Gate 1	7

2.3	When Gate 1 should take place	7

2.4	Applying the review to different sized proposals	8

3.	Conducting Gate 1: Concept and feasibility	9

3.1	Summary	9

3.2	Sources of information to inform your review	9

4.	Detailed guide to Gateway review 1	11

4.1	Documentation	11

4.2	Organisation	16

Appendix 1: Strategic assessment and preliminary business case – information requirements	19

Appendix 2 Best practice sources	24

# The Gateway review process

## About the Gateway review process

Gateway review is a process the Victorian Government applies to its most significant projects and policy initiatives to help ensure they are well managed and delivered to plan. It provides an independent assessment of a project's health at a point in time and improves the capability of project management via lessons learned.

The Gateway review process examines funding proposals, funded programs and projects. It aims to provide timely advice to the senior responsible owner (SRO) as the person responsible for a program or project.

A review provides the SRO with an independent view on the current progress of the proposal, project or program and an understanding of whether it is properly prepared to successfully proceed to the next stage or decision point.

Given the aim is to help the SRO at key decision points, each review is short and focused on the work that is complete, or should be, at the time. For the best result, a review is carried out shortly before a key decision point to allow sufficient time for any recommendations to be incorporated.

The Gateway review process is mandatory for all High Value/High Risk (HVHR) projects.

## About this booklet

This booklet supports Gate 1: Concept and feasibility.

Gate 1 investigates the strategic direction and concept development of the proposed investment against the wider agency, portfolio or whole-of-government (see Figure 1) goals or needs. Gate 1 usually applies to investments nominated under the HVHR framework; however, it can be applied to any type of proposed investment to help confirm that:

- the policy merit is sound and evidence based;

- strategic options in response to the problem have been sufficiently explored; and

- the way forward is achievable.

This booklet describes the appraisal questions and sources of further information, including information about better practice. It provides review teams with questions to explore and suggested evidence to support those questions. Because the nature of each problem is unique and circumstances change, the booklet should be used as a guide to the range of appropriate questions and evidence, not as a complete checklist of mandatory items.

The guide provides you with a table that demonstrates the difference in information requirements between HVHR submissions (preliminary business cases) and non-HVHR submissions (strategic assessments).

Figure 1 shows the point at which Gateway reviews take place throughout the investment lifecycle.

Figure 1: Overview of the Gateway review process

# Stage 1: Conceptualise

## Gate 1: Concept and feasibility

Every investment develops in response to an identified problem. Problems may relate to meeting a policy target, adapting to a changing environment, meeting user demand for a particular service, or avoiding a lost opportunity. Before developing and implementing a project solution it is critical to develop an agreed understanding and properly characterise the problem your proposal seeks to address, in terms of its cause and effect. Only once this is done can an agency decide what benefits, or objectives, it is trying to achieve in addressing the problem.

Understanding the problem enables an agency to identify, dimension and prioritise the investments they believe are most deserving of attention from government. The Victorian Investment Lifecycle Guidelines requires agencies to conduct this process internally. The Department of Treasury and Finance recommends doing this using the tools provided in the Investment Lifecycle Guidelines and using an accredited Investment Management Standard (IMS) facilitator to guide the organisation through the process.

Once the problem and benefits have been identified, scoped and understood, a natural decision point arises for the agency. The decision is whether the benefits are of critical importance and whether the department should proceed to identifying, documenting, and justifying the best strategic way forward. It is not until this policy analysis and strategic assessment is complete that agencies should think about the correct project options to explore.

Where agencies have decided there is a problem worthy of government attention, agencies are required to prepare a strategic assessment (non-HVHR) or a preliminary business case (HVHR projects) for submission to government. Gate 1 confirms to the Senior Responsible Owner of a project whether the agency is in a position to present a compelling case in this submission with:

strong policy merit (has a well-defined problem and clear, important and desirable benefits);

adequate exploration of strategic options that could address the problem and realise the benefits;

an identified way forward (the proposed solution is only required to be ‘indicative’ at this stage, it is not confirmed until full business case stage).

## Aim of Gate 1

Gate 1 is aimed at assisting the SRO by advising them:

whether the project team has done sufficient work on the preliminary business case/strategic assessment submissions to allow government to make a well-informed judgement as to whether the project should proceed with the preparation of a full business case; and

whether the agency has the capacity and capability to deliver a robust submission in the transition to the full business case stage.

## When Gate 1 should take place

The timing of Gate 1 should be once the strategic assessment or preliminary business case has been substantially completed but prior to formal submission to DTF or the government for final consideration.

## Applying the review to different sized proposals

Most of the time, Gate 1 will be conducted in relation to HVHR investments. An investment is HVHR if any of the following criteria are met:

total estimated investment (TEI) is more than $100 million, regardless of funding source

the Gateway project profile model identifies the asset as ‘high risk’; or

the government identifies the asset as warranting extra rigour – e.g. ICT projects or multi-sector funding sources.

A Gateway review may also be applied to non-HVHR investments. The information in this booklet is equally applicable to strategic assessments (which are the indicative business cases required for non-HVHR proposals). Where you are conducting a Gateway review on a strategic assessment, the breadth of information that is required is the same as for a preliminary business case; however, the depth of expected information is less.

# Conducting Gate 1: Concept and feasibility

## Summary

Conducting a Gate 1 review ensures the strategic assessment or preliminary business case is sufficiently robust. To do this, agencies need to demonstrate that they have:

identified and properly defined the problem;

defined the benefits that would result from fixing the problem, in a way that is SMART (specific, measurable, achievable, relevant and time-bound);

explored the appropriate strategic response; and

outlined an indicative solution.

In addition, Gate 1 conducts a ‘health check’ of the organisation and project team developing the proposal, to identify any risks to either the development of the preliminary business case or strategic assessment, or any risks to the investment in transitioning to the next stage (full business case). The outcome of the health check may also inform and identify any gaps in the robustness of the preliminary business case or strategic assessment (step 1). See Figure 2: Gate 1 process

Figure 2: Gate 1 process

## Sources of information to inform your review

Documentation and evidence providing information on the areas of investigation should be available before the Gateway review starts.

By this stage of an investment’s lifecycle, it is usual that documents would have been prepared, and  discussions and workshops would have taken place to various levels of detail and completion depending on the proposal. Such documents, workshops and discussions often serve to inform the strategic assessment and the preliminary business case, and therefore should be captured accurately in them.

### Key sources of information

Both the strategic assessment and the preliminary business case are tools used to provide key information to enable government to decide whether or not to continue developing the investment proposal (ie. whether to progress to full business case preparation).

The depth and breadth of information required in the strategic assessment differs from that of the preliminary business case, and should be scaled according to the risk profile and value of the proposal. Once the decision is made by government to support the continued development of a proposal to full business case stage, the required depth and breadth of information required is extended further as the investment moves into full business case development stage (see Appendix 1: Scope, depth and breadth of information required in strategic assessment vs preliminary business case).

### Other sources

The strategic assessment and preliminary business case documents are important tools in assisting in the government’s investment decision-making process. However, they are considered to be only one of a suite of important documents, pieces of work and consultations that may have occurred by this stage of a project’s lifecycle.

The Gateway review team should also consider the following documents (if not already contained within the strategic assessment or preliminary business case) in their assessment of the project’s readiness for the next phase:

the business strategy or business plan that sets out the organisation’s strategy and policy objectives in relation to a set of public services or explains the objectives of the organisation’s change agenda;

any long-term planning document;

any relevant service-level agreements and associated targets and delivery plans;

the main assumptions and constraints on which the project will be founded and dependencies with other projects, programs or policy;

a list of the projects in the program’s portfolio and interdependencies that have to be delivered successfully if the project is to achieve its objectives, and their current status;

the financial provision made for the proposal and its components; and

a plan covering the work to be done over the short to medium term

identifying the streams of work and the main deliverables and milestones for each and the contribution each is making to project outcomes

resource estimates, e.g. funding for delivery bodies, people and systems.

# Detailed guide to Gateway review 1

## Documentation

One of the roles of Gate 1 is to confirm that the strategic assessment or preliminary business case presents a compelling case with:

strong policy merit (has a well-defined problem and clear benefits);

adequate exploration of strategic options that could address the problem and realise the benefits;

an identified way forward (preferred solution should be indicative only at this stage).

The areas Gateway review 1 should consider are outlined below.

### Problem

| Areas to probe | Evidence expected |
| --- | --- |
| Is it clear what the problem is that needs to be addressed, both the cause and effect? Is there sufficient evidence to confirm the cause and effect of the problem? Does the problem need to be addressed now and by this government? Does the defined problem capture its full extent/scope? | Review the problem or issue being addressed to confirm it clearly outlines the problem that needs to be addressed, both the cause and effect. Confirm there is sufficient and balanced evidence to verify the cause and effect of the problem. Confirm the problem is specific to this investment and that it has been defined in such a way that properly captures the full extent/scope of the problem. The organisation should be able to demonstrate that the issue is not more widespread or, if it is a systematic problem, that is not being addressed in its entirety. The organisation should justify why it is only addressing the problem to the extent that it is proposing to. An investment concept brief, Investment Logic Map and benefits management plan are well formulated and complete. It should be evident that sufficient research has been conducted to support the information that justifies the problem. |

### Benefits

| Areas to probe | Evidence expected |
| --- | --- |
| Have the benefits that will result from fixing the problem been adequately defined? Are the benefits of high value to government or this organisation? Does the proposal’s sponsoring group, e.g. ministers or the organisation’s management board, agree with the business strategy and is it robust? | The benefits that will result from fixing the problem (or addressing the issue) should be adequately defined. The benefits that would result from fixing the problem should be of high value to the government. The benefits should make the necessary contribution to the overall strategy of the organisation and its senior management and interfaces effectively with broader high level government policy objectives and initiatives: a description of the link to government performance, wider government objectives and delivery targets and/or commitments of senior management; and details of any overlap or link with existing internal or external programs or policies. You should confirm the project’s potential to succeed has been considered in the wider context of the organisation’s delivery plans and change programs and any interdependencies with other programs or projects in the organisation’s portfolio and those of other organisations. |
| Does the proposal reflect the current policy and organisational environment and does the scope of the project fit with the strategy or program? How well does this investment support the identified policies and service needs of the organisation over the next 10–15 years? | Documented evidence that the sponsoring group, e.g. minister or the board, have agreed the scope of the problem/procurement activity as defined and the alignment of benefits sought with policy or program objectives, organisational strategy and/or change priorities. Where there are significant changes in policy priorities (in stakeholders views or in the key benefits), evidence there has been a reappraisal of the policy or program. An analysis to show the project’s relationship to relevant cross-cutting government policies. Alignment of the proposal to the organisation’s service logic and investment prioritisation in consideration of the identified policies and service needs of the organisation over the next 10–15 years. |
| Are the KPIs SMART (specific, measurable, achievable, relevant, time-bound) and will they provide strong evidence that the benefits have been delivered? Have key dependencies critical to benefit delivery been considered? | A description of the policy drivers behind the benefits and how they contribute to the overall objectives of senior management for a particular public service or the organisation’s change agenda. A definition of key critical success factors and how the required quality of performance will be measured. The KPIs to measure the benefits that will flow from addressing the problem should be pitched at a level so they are SMART. This will mean the impact of the investment can be tracked and its success can be attributed. A description of the main outcomes and an analysis of the leading and lagging indicators. An appropriate forum for reporting benefits should be outlined. There should be evidence that the investment can be evaluated in a practical and affordable way. |

### Strategic response

| Areas to probe | Evidence expected |
| --- | --- |
| Has a reasonable spread of strategic interventions been identified and packaged into sensible strategic options? Strategic assessment demonstrates procurement solution will improve service delivery and/or achieve organisational efficiencies? Is there evidence to demonstrate that the strategic options are feasible? Were the strategic options evaluated fairly to reflect their ability to respond to the problem and deliver the benefits? Is the preferred strategic option the most effective way to address the problem and deliver the benefits? | Demonstrated exploration of strategic responses to the problem, including measures to: change demand; change supply; and change productivity. Strategic interventions should be packaged up cleverly into groups of feasible strategic options that jointly address the benefits sought. Where it is unclear at this stage what the best strategic response is, agencies should consider taking more than one possible response forward for further examination. |

### Indicative solution

| Areas to probe | Evidence expected |
| --- | --- |
| Project options |  |
| Consistent with the preferred strategic option, have a reasonable spread of project options been analysed? Is the recommended project solution the best value-for-money way to respond to the problem and deliver the expected benefits? | A high-level comparative analysis of short-listed project options should have taken place. The options analysis should be focused on ascertaining the best value-for-money way to respond to the problem and deliver the expected benefits. The project options analysis is likely to be high level at this stage; however, based on the size and cost of the proposal, it may include social, environmental, economic and financial analysis. High-level rationale justifying that the recommended solution is the best way forward. |
| Scope Is the solution specified clearly and fully? (all business changes and assets) Is there an understanding of the scope of the recommended solution? | The organisation should have an indication of its likely preferred project or program solution. This solution should be specified clearly and fully – outlining all business changes and assets that would be required to implement it. A description of the proposal scope as far as it is known. Details of any overlap or link with existing internal or external or policies or programs. A description of program strands and/or sub-programs and main projects with an explanation of how each will contribute to the required outcomes. Key deliverables and an identification of key interdependencies should be outlined. |
| Deliverability | At this stage, there should be high-level evidence that the solution can really be delivered. As the focus at Gateway 1 is mostly on evidence to prove the policy and strategic merit for the proposal, evidence of the deliverability is not required to be detailed or finalised at this stage; however, the deliverability should be mapped out in a high-level form. |
| Cost Are the cost assumptions realistic and can the solution be delivered for the estimated cost? | The cost estimates should be sufficiently reliable to provide an ‘order of magnitude’ of the final cost. The cost estimate will be used as a component of the analysis to determine which project investment options should be considered further in the full business case. Estimated capital costs should be provided with a brief description including: the estimated range of TEI; the basis for this estimate; outline of cost inclusions/exclusions consistent with scope; and cost assumptions that were used. Where the project will also have an operating impact, you should also provide estimates of the changes to ongoing operating costs. |
| Procurement Has a procurement strategy been nominated? For alliancing projects, where procurement is necessary to move the proposal forward to the full business case stage, how is capability and capacity for acquisition to be managed? | There may be an anticipated procurement method nominated at this point; however, analysis or details of the procurement strategy is not required at this time. A market management plan is in place and evidence of a good understanding of supplier capability and capacity exists. |
| Stakeholders Who are the stakeholders and are they supportive? Are key stakeholders confident outcomes will be achieved when expected? | A list of key stakeholders and statements of their needs and support for the project. For cross-cutting projects, clear lines of accountability for resolving any conflicting stakeholder requirements. Where appropriate, there should be recognition of the need to involve external delivery partners, industry and the supplier. Confirmation of time-critical stakeholder issues and a realistic schedule to achieve them. The project board is confident that planned milestones will result in good-quality deliverables that will deliver the necessary outcomes. A commitment from key stakeholders that project deliverables will achieve the desired outcomes. |
| Risk Have key risks to implementing the indicative solution been identified together with strategies for managing them? Does this proposal have impacts that need to be considered? What else could affect success? | A current list of the major strategic, political and/or reputation, environmental and legislative risks to the overall project, analysed by likelihood and impact. Risk register identifies key risks both to the procurement process and to the business should an appropriate solution not be sourced. Risk owners nominated. Early warning indicators identified. The risks of success have been considered, e.g. take-up or usage greater than expected and contingencies identified. Depending on the nature of the project, the project team may have considered reviews of major risks, mitigation options and contingency plans. Where there are significant environmental impacts, that any relevant regulatory requirements are being considered. If a cost-benefit analysis has taken place (not mandatory at this stage), there should be an explicit inclusion in it of significant environmental impacts where they are priced, i.e. waste, land and contamination. If a legal framework for the project exists, it should be comprehensive and sound. |
| Governance Does the proposal require new governance arrangements e.g. across portfolios? Have project controls been determined, especially where constituent projects will be joined with other organisations? | A governance framework should have been identified if relevant at this stage of the proposal. Project governance framework is commensurate with the complexity of the procurement activity with clearly defined roles and responsibilities. The agency may have also considered the following but is not required to at this stage: details of the escalation procedures; for cross-portfolio projects, programs or policy, evidence all parties involved know how they are engaged in the project and are committed to its delivery; clear governance arrangements to ensure sustainable alignment with the business objectives of all organisations involved; and processes identified to manage and record key project information and decision making. |
| Time management Have the major deliverables for the investment been outlined? Are there delivery timelines for the investment? Does the recommended solution need to comply with broader government or departmental timing requirements? | The proposal report and plan should be up to date. Milestones for implementation phase should be set. |

## Organisation

In the second step, you will assess and review issues of governance, timing, risks, cost, etc.; however, this time you are not focused on the deliverability of the preferred project solution as identified in the strategic assessment or preliminary business case, but rather, you are looking at the capacity and capability of the organisation to deliver a robust preliminary business case, or strategic assessment, and move successfully to the next stage (full business case development). Specifically:

Does the organisation have the capacity and capability to deliver a robust preliminary business case or strategic assessment? Are the arrangements at the strategic concept and feasibility stage sound enough to ensure the organisation has the ability and processes to deliver a high-quality preliminary business case or strategic assessment (e.g. proper governance arrangements, financing, feasibility studies, issues management, quality assurance of feasibility studies at this stage)?

Does the organisation have the capacity and capability to move to full business case stage? Are the organisation’s arrangements to move the project to the next stage adequate to ensure the project’s health may be maintained through to full business case?

| Areas to probe | Evidence expected |
| --- | --- |
| Lessons learned |  |
| Is the organisation able to learn from experience with this proposal and other projects or programs? | The organisation has processes in place to incorporate lessons from this proposal and its components into wider best practice. The organisation learns from the experiences of others. |
| Have lessons from similar projects been considered? | Details of issues identified from previous or similar projects and their application to the current project. |
| Quality assurance |  |
| Have assurance measures for the project been put in place? | Key project stakeholders, e.g. internal audit, procurement specialists and/or peer reviewers, are appointed, with evidence they challenge assumptions, decisions and risks. Gateway reviews, health checks and/or policy reviews are incorporated into plans. Advice from key stakeholders is acted upon. Audit arranging for complementary assurance from audit functions through the delivery chain. The proposal is subject to the organisation’s assurance framework for its portfolio of programs and projects. Market/supply considerations are understood and acted upon. Quality assurance measures have been put in place to measure feasibility studies and the quality of information inputted into the strategic assessment or preliminary business case. |

| Timing on track |  |
| --- | --- |
| Are the proposed timelines for delivering the preliminary business case on track? | Plans showing key deliverables, approvals and timelines for developing the preliminary business case. Key aspects identified e.g. costs, reports and assessments. Any issues affecting delivery timelines are being resolved. Confidence from delivery partners that upcoming timeframes are realistic. Interdependencies with other projects are understood and managed. Timelines for processes identified and lead times factored into the preliminary business case development process. |
| Governance |  |
| What governance is currently in place for developing the preliminary business case or strategic assessment? | At this stage, the organisation has sound governance arrangements in place to ensure the concept and feasibility stage of the investment is delivered successfully. The governance framework to drive the proposal forward should also be developed. |
| Is the governance framework fit for purpose and is there commitment to key roles and responsibilities for this project within current corporate priorities? What governance framework is proposed for the future? How will governance risks be managed? | A commitment from sponsors, e.g. senior management, key partners and ministers, a willingness to take ownership and a clear understanding of their roles in achieving successful outcomes. Key roles in the development of the preliminary business case should be identified and assigned, e.g. responsible minister, SRO, project director, project manager, business change manager or equivalent role and sub-program managers with named individuals given responsibility for the transition to new ways of working. |
| Risk |  |
| Is there a contingency plan and business continuity plans to transition the proposal from concept and feasibility through to full business case development? | Decisions about contingency and necessary business continuity arrangements made with appropriate plans. The project’s potential effects on public services are analysed and decisions made about those for which contingency arrangements will be needed. Milestones relating to contingency measures in plans and the milestones being achieved as expected. |
| Is there a framework for managing issues and risk? | Defined roles, responsibilities and processes for managing issues and risk across the proposal, with clearly defined routes for bringing current issues and risks to the attention of senior management. |

| Capability and capacity |  |
| --- | --- |
| Does the team/organisation have the necessary capacity and capability to transition to full business case stage? Are appropriate management controls in place to deliver a robust preliminary business case or strategic assessment? Are appropriate management controls in place to move forward? | Review the arrangements for leading and managing the concept and feasibility stage. Review the arrangements for identifying and managing the main risks to the proposal at this stage including external risks such as changing business priorities. Appropriate resourcing and capability of the department has been identified to manage the procurement activity. Accountabilities allocated to SROs. Plans for ongoing management of the delivery chain are in place. |
| Are the required internal/external individuals and organisations suitably skilled, available and committed to carrying out the work? | Key roles in place, with skills matched to the nature of the work. Information showing who needs to be involved, and when and what they must deliver in relation to the preliminary business case or strategic assessment. |
| Are the required skills and capabilities available to move this proposal forward, taking account of the organisation’s current commitments and capacity to deliver? | The specialist and management skills required to move the proposal forward to the next phase of the project are identified. The organisation has brought together or has credible plans to bring together the skills and capabilities it needs to plan and achieve the desired outcomes and has access to external sources of expertise. The resources will be available when needed throughout the next phase. The organisation is realistic about the complexity of any changes and how they can be managed and demonstrates learning from previous and/or other projects. Key roles within the project are identified with named individuals. Key individuals have an appropriate track record of successful delivery. The project has access to expertise that can benefit those fulfilling the requisite roles. An allocation of key project or program roles between internal staff and consultants or contractors. |
| Affordability |  |
| Are the funds to reach the next phase available? | Budget provision for the project business case development. Adequate approaches for estimating, monitoring and controlling expenditure on the project. Financial and other resources have been considered for the project, and plans through to the next stage are realistic. |
| Probity | Is probity being appropriately dealt with? |

Appendix 1: Strategic assessment and preliminary business case – information requirements

The below table outlines the scope, depth and breadth of information required for a strategic assessment or preliminary business case. While it is not expected that the strategic assessment or preliminary business case is complete at the time a Gate 1 review is conducted, it is expected that the project team has intentions to incorporate the information listed below where possible.

| Heading | Strategic assessment (appx 5 pages plus attachments) | Preliminary business case |
| --- | --- | --- |
| Executive summary | Explain the proposal in narrative terms, generally following the main points of the body of the strategic assessment. For efficiency minimise duplicating the body of the report. | One-page summary of the proposed investment. Explain the proposal in narrative terms, generally following main points of the body of the preliminary business case. For efficiency minimise duplicating the body of the report. |
| Part 1 Problem |  | This section should be as long as is needed to provide the required information, which may be up to five pages. |
| 1.1 Definition of problem | Explain in plain English in less than one page the problems that the investment is intended to solve. Present the cause of each problem, who is affected, and how they are affected. | As per the strategic assessment. |
| 1.2 Evidence of the problem | Provide the evidence of both the cause and effect of the problem. Detailed quantitative evidence is not sought, but other facts or examples of the problem can be helpful. | Provide the evidence of both the cause and effect of the problem. Evidence might include, for example: demand forecasts with assumptions; KPIs on current performance levels; and facts/examples of the problem. |
| 1.3 Timing considerations | Briefly explain why the problem should be solved by government now rather than later. | Describe why the problem needs to be solved at this time. Explain the implications of delaying a response to the defined problem. |
| 1.4 Problem statement scope | Explain whether similar needs exist either inside or outside your organisation that might be addressed together with this proposal. | As per the strategic assessment. |
| Part 2 Benefits |  | This section should be as long as is needed to provide the required information, which may be around two pages. |
| 2.1 Benefits to be delivered | Explain the key benefits (drawn from the Investment Logic Map and Benefit Map) that flow if the problem is solved. Also note any dis-benefits. | As per the strategic assessment. |
| 2.2 Importance of the benefits to Government | Outline how or why the benefits reflect government and/or organisational policies, objectives or priorities. | Show how this investment will help to advance the organisation to meet its objectives. Describe how this initiative connects to government and/or organisational priorities and the department’s strategic plan and multi-year strategy. List the key high-level economic, social and environmental benefits this initiative will deliver. Describe also any detriments that will arise from this proposal. |
| 2.3 Evidence of benefit delivery | Define the measures to be used to show whether the benefits have been delivered. | Define the measures to be used to show whether the benefits have been delivered, including: KPIs that will be used to measure the delivery of the benefits; baseline, interim and target measures and dates for the KPIs; and person/position responsible for delivering the benefits, and the forum in which they will be reported. Some of this information can be presented in an appended benefit management plan. |
| 2.4 Interdependencies | Outline any key interdependencies critical to benefit delivery. | As per the strategic assessment. |

| Part 3 Strategic response |  | This section should be as long as is needed to provide the required information, which may be around four to eight pages. |
| --- | --- | --- |
| 3.1 Method and criteria | Specify the method and criteria used to select assess and rank strategic options, including assumptions . | As per the strategic assessment. |
| 3.2 Strategic options analysis | Explain the strategic options analysis process undertaken. Specifically, explain potential strategic interventions, packaged them into sensible groupings and analysed them to arrive at the recommended strategic response. | Strategic interventions: Explain potential strategic interventions Strategic options: Explain how the potential strategic interventions can be packaged into strategic options. List (by way of appendix of appropriate) any strategic options that were considered but then removed from consideration prior to the strategic options analysis. Provide a justification if appropriate. Ranking of strategic options: Evaluate the strategic options to determine the recommended strategic response. Strategic response: Present the recommended strategic response. |
| Part 4 Solution |  | This section should be as long as is needed to provide the required information, which may be around five pages. |
| 4.1 Project options considered | Describe the potential project options embraced by the strategic response. Shortlist the preferred project options (including a base case). Nominate the recommended project option. | Describe the potential project options embraced by the strategic response. Shortlist the preferred project options (including a base case). Provide evidence supporting the selection of the recommended project option. |
| 4.2 Details of the solution | Describe the recommended solution. | Describe the recommended solution. Describe each of the changes and assets that will be required (as depicted in the Investment Logic Map). |
| 4.3 Cost estimates | Provide high-level cost for the recommended solution expressed as a cost range ($x million -$y million). An indicative estimate of the full cost of the investment should be included with a brief description outlining the basis for this estimate and ay key cost assumptions. Where the investment will result in substantial changes to output costs this should be noted. Indicative estimate: Note that costs are not fully analysed and should be exposed in terms of an indicative cost rage (eg $10-20m; $80-100m Provide an explanation of a basis of the cost estimate (eg benchmarked on similar projects recently delivered) Where the project will also have an operating impact, you should also provide estimates of ongoing operating costs. | [The cost estimates should be sufficiently reliable to provide an ‘order of magnitude’ of the final cost. The expected accuracy at this stage is -30/+50 per cent for preliminary business cases. The cost estimate will be used as a component of the analysis to determine which project investment options should be considered further in the full business case. At a minimum, capital costs of the investment should be included with a brief description including: the estimated range of TEI; the basis for this estimate; outline of cost inclusions and exclusions consistent with scope; and cost assumptions that were used. Where the project will also have an operating impact, you should also provide estimates of ongoing operating costs.] |
| 4.4 Procurement strategy | If known, nominate the anticipated procurement method. Evidence for its selection is not required. | Nominate the anticipated procurement method. Evidence for its selection is not required. |
| 4.5 Stakeholders | List of the key stakeholders, their particular interests in relation to the recommended solution. | List of the key stakeholders, their particular interests and their likely position in relation to the recommended solution. Present a preliminary stakeholder communications plan. |
| 4.6 Risk management | List the key risks to the success of this investment (refer to the investment concept brief). | List the key risks to the success of this investment (refer to the investment concept brief). Explain how these risks are to be managed. |
| 4.7 Governance arrangements | Outline governance arrangements in place to progress this proposal next stage. | Outline governance arrangements in place to progress this proposal next stage. Outline any existing governance frameworks that the recommended solution could align with. |
| 4.8 Timelines | Identify any key timelines. | List the major deliverables and their delivery timelines (refer to the investment concept brief). |
| 4.9 Next steps | Explain the main areas of uncertainty to be resolved in Stage 2: Prove. | As per the strategic assessment. |
| Appendices |  |  |
| Appendix A | Investment concept brief (including Investment Logic Map). | As per the strategic assessment. |
| Appendix B | Benefit Map. | Benefit Map. Benefit management plan. |

Appendix 2 Best practice sources

| Source | Information |
| --- | --- |
| High Value/High Risk project assurance process Available: http://www.dtf.vic.gov.au/CA25713E0002EF43/pages/high-value-high-risk-and-investment-guidance-material | Process requirements Eligibility of projects Approvals requirements |
| Investment Lifecycle Guidance Available: http://www.dtf.vic.gov.au/CA25713E0002EF43/pages/high-value-high-risk-and-investment-guidance-material-investment-lifecycle-guidelines | Business case development guidelines, including strategic assessment guidance Procurement strategy guidelines Project tendering guidelines Risk management guidelines |
| Investment management Available: www.dtf.vic.gov.au/investmentmanagement | Investment Management Standards Investment Logic Maps Investment concept briefs Benefit management plans Lessons learnt |
| Gateway review process Available: www.gatewayreview.dtf.vic.gov.au | Gateway guidance materials Becoming a Gateway reviewer |
| National Public Private Partnerships policy and guideline Available: www.infrastructureaustralia.gov.au Partnerships Victoria requirements Available: www.partnerships.vic.gov.au | Contract management policy and guidance material |
| Project alliancing Available: http://www.dtf.vic.gov.au/CA25713E0002EF43/pages/alliance-contracting | Project Alliancing Practitioners Guide National Alliance Contracting Policy Principles |
| Victorian Government Purchasing Board Available: www.vgpb.vic.gov.au | Purchasing advice, policy and guidelines Longer term contract management Contract variations |

# Text boxes

2012