The Gateway Review Process

The Gateway Review Process examines programs and projects at key decision points. It aims to provide timely advice to the Senior Responsible Owner (SRO) as the person responsible for a program or project. A review provides the SRO with an independent view on the current progress of the program or project and assurance that it can proceed successfully to the next stage.

Given the aim is to help the SRO at key decision points, each review is short and focused on the work that is complete at the time. For the best result, a review is carried out shortly before a decision is made to allow sufficient time for any recommendations to be implemented.

About this workbook

This workbook supports Gateway Review 4: Tender Decision. This review investigates the business case and the governance arrangements for the tender decision to confirm the project is still required, affordable and achievable. The review also checks implementation plans are robust.

This workbook describes the main products and provides appraisal questions and sources of further information, including best practices for review teams. It offers key questions to explore and evidence to look for. Because each policy, program or project is unique and circumstances change, the workbook should be used as a guide to the range of appropriate questions and evidence, and not a full checklist of mandatory items.

Tender decision

Gateway Review 3 reviewed the project’s market readiness, in particular the procurement strategy for achieving the project’s objectives, prior to proposals or tenders. For organisations with existing commercial arrangements, it reviewed similar information and decisions. During this project phase, potential suppliers, partners and/or other delivery organisations - such as internal units of the client organisation - submitted proposals or tenders. An evaluation panel analysed them on a ‘like-for-like’ basis and recommended the  proposal  which met all client and end-user needs and which offered the best value-for-money. This Gateway Review 4 should happen before a work order is placed with a supplier or other delivery partner, or at preferred bidder stage, and before the award of a contract.

Gateway Review 4 confirms the recommended tender decision is appropriate before the contract is awarded to a supplier or partner, or a work order is placed with an existing supplier or other delivery partner. It assures the project board the  processes used to select a supplier are sound.  It also assesses whether the process has been well managed; whether the business needs are being met; whether client and supplier can implement and manage the proposed solution; and whether a successful outcome can be achieved.  The project team and review team must be satisfied due consideration has been given to all the factors, including choices about proposed commercial arrangements with any existing supplier that offer value-for-money.

A project will normally go through one Gateway Review 4. However, it may be necessary for a project to repeat Gateway Review 4 including:

- for construction projects, if there is a second tender decision such as for two-stage design and construct or there may be a need for an initial review for the contract award and a subsequent review to confirm the tender decision based on the construction price;

- for IT-enabled and service enhancement projects which may need an initial review before a pilot implementation or initial design contract is undertaken, and a subsequent review to confirm the tender decision before full implementation; and

- for alliance projects once the commercial parameters and framework are agreed with the preferred proponent and again once the out-turn costs and performance targets have been developed at the project development phase.

It should be noted Partnership Victoria projects are exempt from performing Gateway 4 Reviews.

NB: The term ‘supplier’, ‘bid’, ‘tender’, ‘contract’ etc., in the following sections should be interpreted in the context of the nature of the delivery solution and the proposed commercial relationship between the client organisation and the recommended delivery partner organisation.

Figure 1:	Overview of the Gateway Review Process

Figure 2:	Applying the Gateway Review Process to different project

delivery methods

### Gateway Review 4: Tender decision

The purpose of the review is to:

confirm the business case including the benefits management plan, now the bid information is approved;

confirm the objectives and desired outputs of the project remain aligned with the wider organisation’s business strategy and/or the program to which it contributes;

check all the necessary statutory and procedural requirements were followed through the procurement and/or evaluation process;

confirm the recommended contract decision is properly executed within a standard lawful agreement and is likely to deliver the specified outputs and/or outcomes on time, within budget and provide value-for-money;

ensure management controls are in place to manage the project through to completion, including contract management aspects;

ensure there is continuing support for the project;

confirm the approved procurement strategy has been followed;

confirm the development and implementation plans of both the client and the supplier and/or partner are sound and achievable;

check the business has prepared for developing new processes, for implementing and operating new services or facilities and  the transition process;

confirm  there are plans for risk management, issue management and change management both technical and business, and these plans are shared with suppliers and/or delivery partners;

confirm the technical implications, such as ‘buildability’ for construction projects, information assurance and security for IT-enabled projects, and the impacts of e-government frameworks have been addressed; and

- confirm the proposed procurement meets financial approvals and has an adequate budget.

Project documents

The investigation areas and examples of evidence should be available before the review starts. The required information is likely to be found in the documents suggested below, but may be located in other program or project documents, or elsewhere in the organisation’s documentation system:

project management documents, including:

strategies for managing risks and issues, plus plans and a risk register showing identified and managed risks;

plans for implementing business change and handling future change;

service management documents defining how services will be managed, how performance will be measured, and outlining responsibilities for client and supplier;

the benefit management strategy, benefit management plans and responsibilities for delivery;

the delivery strategy, including a procurement strategy, if appropriate; and

the operational requirement and draft contract.

business case and benefits plans for each of the acceptable bids:

to confirm the delivery strategy;

to confirm negotiated and agreed solutions remain within the original criteria;

realistic supplier plans for development and implementation;

an evaluation report recommending the selected supplier or partner; justification of the selected supplier; details of close contenders; and plans for the debriefing of unsuccessful suppliers;

an outline of tender decision plans and plans for the next phase;

an updated time plan developed with the selected suppliers;

an updated communications plan; and

confirmation of funds and authority to proceed.

### 1.	Assessment of proposed solution

| Areas to probe | Evidence expected |
| --- | --- |
| 1.1 Does the proposed solution still meet business needs and government and departmental objectives? | the proposed solution complies with all requirements; and consultation with stakeholders and their acceptance of the proposed solution. |
| 1.2 Have the suppliers proposed any alternatives or innovative options beyond a fully compliant bid? If so, how was this assessed? | an assessment showing whether options benefit the project and remain within the scope of the tender documents. |
| 1.3 Will the proposed bid deliver the business need described in the business case? | analysis showing: the proposal is defined in business outcome terms; proposed solution is fit for purpose, meeting business objectives and anticipated benefits and delivers value for money; the business can achieve the necessary process changes; and the proposed services and service levels, as defined in the contract or agreement, meet agreed business requirements. |
| 1.4 Has the proposed solution affected the strategy for business change and expectations of business benefits? | an updated plan for managing change on the basis of the proposed solution, which is agreed by the project board, users and stakeholders; an analysis of changes to the original plan; an updated plan for realising benefits and descriptions of benefits and their owners; and changes documented and agreed with users and stakeholders. |
| 1.5 Is the client and supplier prepared for the development including new systems and processes, implementation, transition and operation of new services? | the proposed supplier’s development and implementation plans are included in the delivery solution and recommended to the project board; and the client’s implementation plan is agreed with users, or their representatives if the end-user is the citizen, and stakeholders. |
| 1.6 Are there plans and processes to address future business and technical issues? | all parties agree with the strategy for managing change. |
| 1.7 Is there clear demarcation and understanding of responsibilities between all parties, beyond any contractual liabilities? | defined client and supplier organisation, personnel and responsibilities; the client has identified internal relationships and interfaces describing ‘who does what’ with the supplier; |
|  | the supplier has reciprocal arrangements, including senior management roles; partnering arrangements are defined; details of how a single supplier will manage their supply chain; details of how the client will manage the interface with multiple suppliers; the client and supplier will work together in an integrated project team; and if the project crosses organisational boundaries on the client side, governance arrangements will align the business objectives of all organisations. |
| 1.8 Are there resources available for the business to fulfil its obligations within the contract and/or agreement? | there is a plan for implementing the new contract which identifies the quantity, type and quality of resources required; formal management acceptance of agreed resource requirements, with key roles and personnel identified and in place; and adequate plans and procedures for contract management, including availability of requisite skills and experience. |
| 1.9 Have the technical implications been assessed including ‘build ability’, health and safety and sustainability issues for construction projects and information assurance and security, the impact of e-business and legacy systems for IT-enabled projects? | the delivery solution is technically acceptable; for construction projects, design quality indicators are used; there are project-specific plans for health and safety; and sustainable construction practices; and for IT-enabled projects, information assurance and the impact of e-business etc. has been considered. |
| 1.10 Does the project have resources with the appropriate skills and experience to achieve the intended outcomes of the investment? | plans for providing the required ‘intelligent customer’ capability, with names allocated to the major roles; an internal and external commitment to provide the resources required; job descriptions for key project staff; a skills appraisal has been undertaken and any shortfall addressed; and external sources of expertise can be accessed. |
| 1.11 Does the proposed procurement meet financial approvals and is there an adequate budget for it? | confirm financial approvals have been obtained and budgeted costs are adequate. |
| 1.12 Do the transaction documents accurately reflect the business requirements and the risk allocation approved for the project? | confirm the business requirements and risk allocation have been approved and details are contained in the transaction documents. |

2.	Business case and stakeholders

| Areas to probe | Evidence expected |
| --- | --- |
| 2.1 Is the project still required? | confirmation the project still fits with strategic objectives, including government and/or organisational objectives; and confirmation external factors have not affected priorities. |
| 2.2 Are the requirements of the business case complete or does the tender decision require the business case to be amended and/or re-assessed? | a reassessment of the updated business case, including strategic, economic, financial, commercial and project management factors. |
| 2.3 Does the recommended way forward meet the business need? | the main objectives are reviewed against the final bid and proposed solution. |
| 2.4 Has the most appropriate option been selected? | a cost/benefit/risk analysis against the final bid information is complete and results of the evaluation, including sensitivity analysis, are available; and for construction project, whole-life design quality, cost and time are maximised. |
| 2.5 Does the commercial arrangement represent value-for-money, with an appropriate level of quality over the project’s life? | market conditions, other organisational benchmarks and previous experience assessed; evaluation results; and assessment of a supplier’s funding arrangements. |
| 2.6 Is the client realistic about their ability to manage the change? | documented understanding of cultural implications and account taken of the current organisational culture; and comparison with others. |
| 2.7 Is the business case still viable when incorporating the bid proposal? | the business case incorporates bid information including: changes in budgeted figures; returns and value recalculated with new benefits plan; and costs compared with budget and pretender estimates. |
| 2.8 Is there an agreed benefits-realisation plan? | benefits management strategy and plans, including: critical success factors; those responsible for achieving benefits are identified; an agreed process for measuring and assessing benefits; measurement baselines data is available for assessment; and the post implementation review plan identifies review points and benefits to be assessed and payment mechanisms are linked to benefits realisation. |
| 2.9 Have suitable stakeholders, business and user representatives been involved and have they approved the tender recommendation and draft contract? | involvement of stakeholders and business or user representatives in reviews; stakeholder views have been considered; representation on the evaluation team; and project board or steering group approval. |

### 3.	Risk management

| Areas to probe | Evidence expected |
| --- | --- |
| 3.1 Are risk and issue management plans up-to-date? Are they being monitored? | the risk register and issue log is regularly reviewed, updated and acted upon. |
| 3.2 Have all major risks that arose during this stage been resolved? | risk and issue management plans and the risk register have been updated to include risks associated with project resourcing and funding; team competencies; legislation; technical dependencies; users and stakeholders. Owners of risks and/or issues have been assigned under clients risk transfer plans. |
| 3.3 Are arrangements in place to minimise risks to the business in the event of major problems during implementation and roll-out? | a business continuity and contingency approach has been agreed with stakeholders and suppliers; business or client continuity and contingency plans are under development; an assessment of supplier continuity and contingency plans; and for IT-enabled projects, information assurance including risk assessment and management is in place. |
| 3.4 Does the contract reflect the standard terms and conditions and the required level of risk transfer? | contracts comply with standard terms and conditions; any changes to standard terms and conditions are assessed; and an analysis of the risk allocation proposed by supplier or partner versus expectations of the client. |
| 3.5 For longer term partnering contracts, have the retendering issues been considered? | plans for an exit strategy at the end of the contract, with appropriate review points built in over the contract’s life to update these arrangements. |

### 4.	Review of current phase

| Areas to probe | Evidence expected |
| --- | --- |
| 4.1 Is the project under control? | project is running to schedule and costs are within budget; and recommendations from the last Gateway review have been acted upon. |
| 4.2 What caused any deviation such as over and under-runs? | reconciliations set against budget and time plan. |
| 4.3 What actions are necessary to prevent deviations recurring in other phases? | analyses and plans are included in project documentation which is continually updated and reviewed. |
| 4.4 Have all the assumptions from Gateway Reviews 1, 2 and 3 been validated? | validation of all assumptions. Any that cannot be validated are examined, appear in the risk register and/or issue management log, and are assessed and discussed with potential suppliers and partners; and documentation of any new assumptions. |
| 4.5 Have all the required organisational procurement and technical checks been undertaken? | review of bid management and approval processes; compliance with relevant procurement policies and guidelines; the evaluation strategy, underpinning models and criteria have been followed; and compliance with statutory requirements such as planning and building regulations. |
| 4.6 Did the project team follow the steps in the delivery strategy? | documented information confirms activities and processes in the delivery strategy and plan were followed. |
| 4.7 Has the procurement process adequately managed probity? | probity advisor or equivalent sign off. |

### 5.	Readiness for next phase:  Readiness for service

| Areas to probe | Evidence expected |
| --- | --- |
| 5.1 Is the working relationship likely to succeed? | realistic assessment of management style and/or behaviours on both sides; appropriate level reporting arrangements are identified on both sides; suitable procedures and responsibilities for contract management are defined and agreed; plans for partnering workshops are in place; continuity of personnel from the contract award phase into the implementation phase; and for construction projects, there are plans for integrating the project team. |
| 5.2 Are all resources and internal funds in place? | budget provision; agreed human resource; subsequent years’ expenditure included in program or project budgets; an authorisation and/or approval process for payments to suppliers; a process for expenditure reporting and reconciliation; and insurances established by supplier. |
| 5.3 Are the supplier’s project, risk and management plans adequate and realistic? | confirmation the project plan meets timescale; and realistic implementation and risk management plans. |
| 5.4 Do the client’s plan reflect the supplier’s plan, and vice-versa? | updated project management plan reflects tender proposals; defined client organisation, personnel and responsibilities; supplier personnel cleared to meet project requirements; process for resolving issues agreed with supplier and/or partner; and all plans have been reviewed, agreed and included in the contract. |
| 5.5 Are the long-term contract administration plan and benefit measurement process complete? | long-term plan includes contract management strategy and a detailed service delivery plan; identified sources of resources; benefit measures agreed with supplier and/or partner; project plan shows resource requirements have been identified, planned, budgeted for and are available; and defined roles and responsibilities. |
| 5.6 Are all the mechanisms and processes in place for the next phase? | project plan confirms arrangements for management, monitoring, transition and implementation; and external consultants are accountable and committed. |
| 5.7 Are the service management plan, administration and service level arrangements complete? | documented service management strategy and plan; defined and agreed service level management, service levels, quality and measurement; defined responsibilities for each party; defined and agreed standards for services; and defined and agreed monitoring, reporting and review mechanisms. |
| 5.8 Is the management process for service change complete? | technical and business change control procedures are defined, agreed and included in the contract; and defined and agreed management process and responsibilities. |
| 5.9 Is there an acceptance strategy or commissioning strategy? | an acceptance and/or commissioning strategy and plan, with fully documented and timetabled decision paths; decision makers clearly identified and informed about their role and the information they will be given; agreed acceptance criteria; and a validated acceptance testing plan, including technical and business components. |
| 5.10 Is there an implementation strategy? | implementation strategy and plan; users, stakeholders and client business management are involved in developing strategy; organisational transition plans; clearly defined roles for client and supplier to monitor and control handover; and clearly defined training roles for client and supplier. |

### Best practice sources

| Source | Information |
| --- | --- |
| Investment management guidelines See Investment management www.dtf.vic.gov.au/investmentmanagement | investment management standards investment logic maps investment concept briefs benefit management plans |
| Investment lifecycle guidance See lifecycle guidance www.lifecycleguidance.dtf.vic.gov.au | business case development guidelines, including strategic assessment guidance procurement strategy guidelines project tendering guidelines risk management guidelines |
| Procurement advice, policy and guidelines Victorian Government Purchasing Board www.vgpb.vic.gov.au | longer term contract management contract variations |
| PPP projects for the National PPP policy and guidelines, see www.infrastructureaustralia.gov.au specific Partnerships Victoria requirements apply, see www.partnerships.vic.gov.au. | contract management policy and guidance material |
| Project alliancing See Project alliancing www.dtf.vic.gov.au | Project Alliancing Practitioners Guide |
| Capital development guidelines Department of Human Services www.dhs.vic.gov.au/capdev . | contract administration commissioning of facilities managing contract occupational health and safety |
| Asset lifecycle Department of Education and Early Childhood Development www.education.vic.gov.au | operations and maintenance |
| Information and Communications Technology (ICT) projects www.mmv.vic.gov.au | standard contracts whole of Victorian Government ICT contracts Government IT&T Policies 1–46 |
| Victorian Government asset management series Department of Treasury and Finance http://home.vicnet.net.au/~assetman | further information about commissioning assets other general information |
| Gateway Review Process See www.gatewayreview.dtf.vic.gov.au | Gateway Guidance material Becoming a Gateway reviewer |