The Gateway Review Process

The Gateway Review Process examines programs and projects at key decision points.  It aims to provide timely advice to the Senior Responsible Owner (SRO) as the person responsible for a program and project.  A review provides the SRO with an independent view on the current progress of the program and project and assurance that it can proceed successfully to the next stage.

Given the aim is to help the SRO at key decision points, each review is short and focused on the work that is complete at the time.  For the best result, a review is carried out shortly before a decision is made to allow sufficient time for any recommendations to be implemented.

#### About this workbook

This workbook supports Gateway Review 6: Benefits evaluation. This review confirms benefits set out in the business case are being achieved and the operational service or facility is running smoothly. The review may be repeated throughout the life of the service with the first review typically 6-12 months after handover to the new owner and a final review shortly before a service contract ends. The review can also be used on a one-off basis, to check a project has delivered its intended outputs and benefits.

This workbook describes the main products and provides appraisal questions and sources of further information, including best practices for review teams.  It offers key questions to explore and evidence to look for.  Because each policy, program or project is unique and circumstances change, the workbook should be used as a guide to the range of appropriate questions and evidence, and not as a full checklist of mandatory items.

### Benefits evaluation

Gateway Review 6 is for the operational phase of a project, after the agreed outputs have been delivered. This might be a new facility, IT asset or a soft output such as training. Unlike earlier phases, the operational phase is likely to be long term and consume a significant proportion of investment costs outlined in the business case.

Gateway Review 6 will typically occur several times over the life of the operational service. The first review concentrates on the business case and how well arrangements have been set up for service delivery and associated contract management. Depending on its lifespan, there may be a number of mid-term reviews to check operational management. For a long term service contract such as a hospital Partnership Victoria (PV project), there may be four reviews over a period of 20 years. For IT enabled projects, the period may be much shorter; there may be only two reviews over a five year period. The mid term review examines aspects such as contract management arrangements, improvements in value-for-money and performance incentives against a baseline. The final review looks at activities relating to closure of the current service contract and ensuring suitable arrangements are in place for the future.

There may be projects where only one Gateway Review 6 is needed, such as the provision of works or a new module of an existing IT system. In this instance, the review should be held 6-12 months after rollout of the new service and/or delivery of the new assets, when evidence of the delivered benefits is available.

Benefits may not all be delivered at the same time. For example, new work practices need to be established in a new school environment before improvements in educational results are seen.

Handover from the project’s SRO to the operational business owner typically occurs within a year of the operational service commencing. It will be the business owner’s responsibility to ensure expected benefits are delivered and the operational service runs smoothly. It will also be their responsibility to close the current arrangements and report back to senior and/or corporate management.

At Gateway Review 5, the project’s SRO decides on the timing of the initial Gateway Review 6 to coincide with key decision points following the post-implementation review. The new owner of the operational service will decide when subsequent reviews are held.

The post implementation review is an internal project assurance for the SRO.  It confirms investment in the business case was justified and lessons learnt have been captured.  Gateway Review 6 is an external peer review that considers the post implementation review as a major part of the initial review process.

Figure 1:	Overview of the Gateway Review Process

Figure 2:	Applying the Gateway Review Process to different project

delivery methods

### Gateway Review 6: Benefits evaluation

Purpose of Gateway Review 6 is to:

assess whether the business case for the project was realistic at Gateway Review 4; Tender Decision;

confirm there is still a business need for the investment;

assess whether the benefits anticipated at this stage are being delivered;

assess the effectiveness of the ongoing contract and/or facility and service delivery management processes;

confirm the client continues to have the necessary resources to manage the facility and any contract successfully;

confirm continuity of key personnel in facility and/or contract management roles;

assess the ongoing requirements to meet the business need and if circumstances have changed, ensure the service delivery and any contracts are adapting to the new situation. Changing circumstances could affect: partner management; relationship management; service management; change management; contract management; benefits management; and performance management;

check any changes do not compromise the original delivery strategy;

check there are ongoing continuous improvement mechanisms to maximise value-for-money;

confirm there are plans to manage the facility and any operational contracts to their conclusion and the validity of exit strategy and arrangements for decomposition; and

assess ‘lessons learnt’ and the methodology for sharing information within government.

Project documents

Investigation areas examples of evidence should be available before the review starts. The required information is likely to be found in the documents suggested below, but may be located in other program or project documents or elsewhere in the organisation’s documentation system:

an updated business case that reflects actual operating conditions and is against the business case in Gateway Review 5;

report on the findings from post implementation review or equivalent major post project review;

an assessment of the benefits delivered to date and expectations for the future (refer to Benefits Management Plan);

a summary of contract changes since Gateway Review 5;

plans for contract improvement and service improvement;

performance reports;

customer surveys;

performance measurement systems;

resources, skills appraisals and personnel plans for future contract management;

reports on stakeholder issues;

plans for disposal of any assets at the end of the contract e.g. resources, buildings, staff, intellectual property rights;

information showing how clients and/or providers manage the relationship and engage with each other;

investment management standard benefit management plan and benefits reporting spreadsheet;

for construction projects, updated health and safety file and plans for future use of the integrated project team; and

for IT enabled projects, security documents.

# 1.	Review of operating phase

| How to use this section for: |  |
| --- | --- |
| An initial Gateway Review 6 | All investigation areas and evidence expected in this section may not be available at this review. |
| A Gateway Review 6 at the start of a medium to long term contract for operational service: | This Review will occur 6-12 months after the asset/system/service commences; or Partnership Victoria (PV) projects and other service contracts, this review should look at current processes and behaviours as well as future difficulties that could hinder the success of the operating period e.g. client, provider and user relations; and The review should look at how transition to the operational state is progressing. |
| A mid stage Gateway Review 6 | This section together with section 3: Plans for ongoing improvements in value-for-money and section 4: Plans for ongoing improvements in performance and innovation, form the core of the repeating reviews for operational service contracts, including PV. There are a number of specific issues pertinent to PV projects. |
| A final Gateway Review 6 | The main focus of this section at the final stage is to assess the operation of the contract over the period since the last review in the same way as a mid stage Gateway Review 6. It would also look ahead to see how the operating phase is being brought to a close. |

| Areas to probe | Evidence expected |
| --- | --- |
| 1.1 Is the service and/or facility operating to defined parameters? | operating parameters are updated as needs change and are documented in change control and updated service level agreements (SLAs); service delivery measured against those parameters; measures to address poor and/or non performance are proving effective; facility safe to operate and maintain; information on how the assets are being satisfactorily maintained, including mechanical and electrical systems; maintenance plans over the asset’s lifecycle; sustainability targets met or exceeded; and customer and/or stakeholder satisfaction assessed. |
| 1.2 Is the benchmarking and/or market testing appropriate? | details of the benchmarking and/or market testing conducted by the parties as agreed; and regular value-for-money reviews are conducted in the absence of contractual benchmarking or market testing. |
| 1.3 Has the project documentation including training material and program been delivered and kept current? | new staff trained and existing staff updated at appropriate intervals; no backlog of material to be updated; defined responsibilities for updating training material and documentation; and health and safety file updated. |
| 1.4 Are the governance and contractual relationships satisfactory? | regular reviews between supplier and client; improvements are documented and changes to the contract are justified; documentation showing how agreed actions are dealt with operationally; action plan kept up to date as a live plan; measurement of service or contract improvements; reports on completed work plans for expected work; and representation of client and supplier at an appropriate senior level. |
| 1.5 Are there plans for continued contract management? | future resource plans; succession planning for key roles; continuity of knowledge when contract team staff change; handover and process information recorded clearly; facility management and/or contract guide available and in use; informal contract agreements documented on a regular basis; record of customer input; and skills appraisal and plans for addressing shortfalls. |
| 1.6 Are plans for ongoing risk management current? | updated risk register, risk reporting and management according to best practice; updated business continuity and/or contingency plans; and consideration of operational health and safety aspects. |
| 1.7 Is change management effective? | process for evaluating and agreeing proposals for major change; documented process for minor changes; approval process; and reviews identifying possible change. |
| 1.8 Is relationship management effective? | meetings held between various parties with forward outline timetable; communication and meeting structure, both formal and informal, between all parties including stakeholders; a structure for running a long term contract; robust contract management processes and good records; client views of on site presence of supplier staff; and user groups or equivalent. |
| 1.9 Is training and support adequate? | the key post holders have appropriate skills and experience; and access to expertise or specialist training. |

2.	Business case and benefits management

| How to use this section for: |  |
| --- | --- |
| An initial Gateway Review 6 | This is for projects delivering an asset as a stand alone project or as an input to a program. Alternatively, the project may be delivering an asset as part of the maintenance regime of an existing operational service. The main focus of this section will be delivery of the business case and the benefits that will be subsequently managed within a larger operational program or service. |
| A Gateway Review 6 at the start of a medium to long term contract for operational service | This review will occur 6 -12 months after the asset/system/service becomes operational. All areas in this section will need to be investigated to confirm there is a business need and supportive stakeholders. The governance arrangements of the operational contract are fundamental to the success of all contracts. For PV projects, this section will measure the delivery of the asset and benefits against the original business case and will set a benchmark at the time of the review for any changes to the business case. |
| A mid stage Gateway Review 6 | This section will focus on what has changed in terms of assumptions or circumstances e.g. change of policy direction, technology change, people skills or resources, the governance arrangements and user satisfaction. For PV and partnering projects, reviews are held every three to five years depending on key decision points and the extent of policy change within that sector. |
| A final Gateway Review 6 | This review is held one to two years before the end of the contract period. The key aspects to probe in this section include whether the asset will fit in with a new program and whether the business case meets the requirements of stakeholders. The new business case is examined as a Gateway Review 2 on a new program or project. A strong governance structure should be in place to oversee the end of one contract, and if applicable, the start of another. |

| Areas to probe | Evidence expected |
| --- | --- |
| 2.1 Is the business case still valid? | confirmation the business case still fits with the organisation’s strategic objectives and priorities, is achievable and affordable; confirmation of ongoing stakeholder commitment; the investment logic remains sound; and confirmation the business owner is committed to the business case. |
| 2.2 Have the business benefits been realised as set out in the business case and benefits management plan? Did the organisation achieve more or less than expected? | findings from post implementation review and/or post project review or equivalent major review show: success criteria met; project performance criteria and key performance indicators including design quality indicators met or exceeded; and whole of life value targets achieved. contribution to program or project benefits and strategic outcomes tracked. Does the benefits report show the achievement of the benefits as detailed in the benefits management plan? updated benefits capture plans compared with Gateway Reviews 4 and 5; assessment of benefits in current operating regime using the benefits measurement basis confirmed in Gateway Review 5; and anticipated future benefits. |
| 2.3 Have the needs of the business, end users or stakeholders changed? | comparison of current business and end user needs with those identified in Gateway Reviews 4 and 5; and periodic reviews of business and end user needs and a projection of future changes. |
| 2.4 Have all the governance and stakeholder issues been addressed? These include: the statutory process; communications; external relations; environmental issues, personnel. | operational communications strategy, updated communications plan and issues log; governance structure reciprocated in both client and provider organisation; issues addressed at the appropriate level in client and provider organisations; staff empowerment to make decisions; and stakeholder involvement. |
| 2.5 Are the users satisfied with the operational service? | details of user groups, outputs and the feedback process; Indication of advance preparation for changes in way services are delivered; and user-friendly guide to the services provided. |

# 3.	Plans for ongoing improvements in 
value-for-money

| How to use this section for: |  |
| --- | --- |
| An initial Gateway Review 6 | All investigation areas and evidence expected in this section may not be available at this review. |
| A Gateway Review 6 at the start of a medium to long term contract for operational service Gateway Review 6 | After 6-12 months the client and provider of the service will be implementing the operational contract management. This section’s aim is to ensure future value-for-money improvements are being considered and are reflected in the next review. |
| A mid stage Gateway Review 6 | This section together with section 1: Review of operating phase and section 4: Plans for ongoing improvements in performance and innovation form the core of the repeating reviews for operational service contracts, including PV. There are a number of issues pertinent to PV projects. |
| A final Gateway Review 6 | All investigation areas and evidence expected in this section may not be available at this review. |

| Areas to probe | Evidence expected |
| --- | --- |
| 3.1 What is the scope for improved value-for-money: Can more be done for less? Could the provider deliver better service quality at the same price? Can maintenance costs be driven down? | analysis of value-for-money to date against future service use scenarios; commercial intelligence about the provider’s track record and/or comparison with other providers offering similar services; and details of expected and achieved efficiency gains. |
| 3.2 Has the organisation benchmarked its processes by comparing them with other equivalent organisations involved in similar relationships? | benchmarking of: demand management; service planning and development; service quality; investment decisions and/or project justification; and benefits management. |
| 3.3 Are commercial mechanisms providing appropriate incentives? | examples could include: payments to the provider dependent on the benefits derived from implementing a particular program of change; provider has incentives to deliver and also for ensuring individual investments are well planned, achievable and will deliver value; clear business justification with identified benefits; target incentive mechanisms where work is task based; and provider is given incentives to submit estimates for a task, with risks and benefits shared in pre defined ratios of the provider exceeding or undercutting those original estimates. |
| 3.4 Are inter related projects integrating appropriately? | governance arrangements operating effectively; and related service enhancing or limiting service delivery. |

# 4.	Plans for ongoing improvements in performance and innovation

| How to use this section for: |  |
| --- | --- |
| An initial Gateway Review 6 | All investigation areas and evidence expected in this section may not be available at this review. This is an important section to ensure the teams are positioning themselves to innovate and deliver improvements in performance between now and the next Gateway Review 6. |
| The start of a medium to long term contract for operational service Gateway Review 6 | After 6-12 months the client and provider of the service will be implementing operational contract management. This section’s aim is to ensure future value-for-money improvements are being considered and are reflected in the next review. |
| A mid stage Gateway Review 6 | This section together with section 2: Review of operating phase and section 3: Plans for ongoing improvements in value-for-money, form the core of the repeating reviews for operational service contracts, including PV. There are a number of issues are pertinent to PV projects. |
| A final Gateway Review 6 | All investigation areas and evidence expected in this section may not be available at this review. |

| Areas to probe | Evidence expected |
| --- | --- |
| 4.1 Is the organisation setting realistic targets for continuous improvement each year from this service? Are the targets specific, measurable, agreed, realistic and timely? | an understanding of and use of techniques such as balanced scorecard, ongoing stakeholder analysis, benchmarking and goal/question/metric approach. |
| 4.2 Are the client and partners working together to actively identify opportunities for improvement through innovation? | details of innovation achieved using industry surveys, benchmarking, reviews by external consultants and reports from the service provider; and whether people at all levels are able to contribute and is this encouraged by using feedback and staff suggestion schemes. |
| 4.3 Is the organisation tracking its progression to improved performance and the flow of results through key milestones and the business planning cycle? | performance information clearly linked to planned outcomes which enables ready assessment of performance in terms of effectiveness, efficiency and service quality; performance information that meets multiple purposes, is consistent and complementary; ongoing assessment of appropriateness of performance information; responsibilities for performance management are defined and understood by the organisation and supplier; direct links between planning and results; ongoing monitoring of performance and periodic evaluation; and integration with corporate and business planning. |
| 4.4 Does the organisation have performance measures to cover all aspects of the contract? | performance measures relating to: cost and value obtained; performance and customer satisfaction surveys; delivery improvement and added value; delivery capability; realised benefits; and relationship strength and responsiveness. defined roles for measurement responsibilities; details on how the information is used and followed up; and effect of any contract change or rebalancing of the performance measurement system. |
| 4.5 Do the performance measures offer clear and demonstrable evidence of the success or otherwise of the contract? | performance measures are meaningful and visible to an organisation’s management group, properly reflect user and stakeholder perceptions and identify the need for supporting or remedial action. |
| 4.6 Are performance measures related to delivery or capability improvement tracked against an existing baseline? | baseline is established in the business case; and performance measures tracked against that baseline. |
| 4.7 Are there performance assessment measures for: ongoing service delivery?; the desired results of individual programs of change or improvement?; the overall results or impact of the project?; and benefit tracking and realisation? | formal SLA approaches and related measures; investment appraisal and benefits management techniques are constructed on a case by case basis; objectives identified during project scoping and in the preliminary business analysis activity; review of the benefits management plan and benefits reporting spreadsheet; and for construction projects, user satisfaction is monitored. |

# 5.	Review of organisational learning and maturity targets

| How to use this section for: |  |
| --- | --- |
| An initial Gateway Review 6 | All investigation areas and evidence expected in this section may not be available at this review. |
| A Gateway Review 6 at the start of a medium to long term contract for operational service | To look at the arrangements organisations have to collect and evaluate lessons learnt from the contract and how it will operate. This is important for contracts let on a similar contract basis e.g. PV, term contract, to confirm the relevant organisations collect learning. |
| A mid-stage Gateway Review 6 | The topics in this section assess whether organisations are collecting learning on an ongoing basis. |
| A final Gateway Review 6 | To look at a review of documented learning during the project’s close down. |

| Areas to probe | Evidence expected |
| --- | --- |
| 5.1 Does the organisation have an effective process for taking improvements out of the lessons learnt from the project and sharing them across government? | a mechanism for capturing and recording the initial data; internal evaluation of lessons learnt; mechanisms and policy for providing information internally and externally; a feedback process for organisational project teams; participation in knowledge sharing forums; help and expertise provided by the corporate centre; and details of the provider’s systems and how learning is applied. |
| 5.2 Has there been a review of project management? | a formal review at project closure; and for construction projects, a post project review using key performance indicators. |
| 5.3 Are suppliers encouraged to learn from experience? | incentives for suppliers to improve project delivery; and a commitment to long-term relationships with integrated project teams. |

# 6.	Readiness for the future:  Plans for future service provision

| How to use this section for: |  |
| --- | --- |
| An initial Gateway Review 6 | All investigation areas and evidence expected in this section may not be available at this review. |
| A Gateway Review 6 at the start of a medium to long term contract for operational service | All investigation areas and evidence expected in this section may not be available at this review. |
| A mid stage Gateway Review 6 | All investigation areas and evidence expected in this section may not be available at this review. |
| A final Gateway Review 6 | This is the key section in relation to future service provision. Are there clear plans for the future use of the asset post contract? What preparatory work has been done regarding the condition of the asset post contract? In a PV for a facility such as a school or hospital the life of the facility is generally longer than the contract and clear plans for future use of the asset as part of an overall service are needed. The closing down of the contract and all the preparatory work relating to asset condition is very important. |

| Areas to probe | Evidence expected |
| --- | --- |
| 6.1 Is there an ongoing need for the service? | Department has planned sufficiently for the contract’s expiry i.e. sufficient time to undertake forward planning, current contract performance assessment, business needs, market analysis and market engagement preparation. updated business case, linked to current business strategy. |
| 6.2 What is the likely scope of the service in the future? | options appraisal to include some or all of the following: do nothing; to retain the scope of the existing contract; to split the scope of the existing contract; to broaden the scope of the existing contract; to completely rethink the requirement for the contract; single and/or multiple sources of supply; and combining new services with other similar and/or complementary service providers. |
| 6.3 Are there any major issues with the current contract that could affect the approach to re-tendering the service? Factors to consider include: range of services – could the provider cope with the range of services offered or were there significant weaknesses? flexibility of contract – how adaptable was the relationship to both foreseen and unexpected changes in the nature and level of demand? customer’s reaction and adjustment to outsourcing – how well did users adapt to services provided by a third party? Was management confident the provider could be trusted to provide the service? Is the organisation now ready for a greater dependence upon outsourcing? exit strategy – will the re-competition be straightforward or is there a danger the customer is now locked in? Have agreements been made to ensure the handover is as smooth as possible? | updated risk register and issue log; reporting of exceptions at regular client and/or provider progress meetings; reports from contract and service management functions; and exit strategy and details of handover arrangements. |
| 6.4 What is the predicted condition of the asset at the end of the contract period? | contract information relating to condition of asset at the end of the contract; and supplier maintenance plans and clients understanding of these e.g. responsibility for software updates. |

Best practice sources

| Source | Information |
| --- | --- |
| Investment management guidelines See Investment management www.dtf.vic.gov.au/investmentmanagement | investment management standards investment logic maps investment concept briefs benefit management plans |
| Investment lifecycle guidance See lifecycle guidance www.lifecycleguidance.dtf.vic.gov.au | business case development guidelines, including strategic assessment guidance procurement strategy guidelines project tendering guidelines risk management guidelines |
| Procurement advice, policy and guidelines Victorian Government Purchasing Board www.vgpb.vic.gov.au | longer term contract management contract variations |
| PPP projects for the National PPP policy and guidelines, see www.infrastructureaustralia.gov.au specific Partnerships Victoria requirements apply, see www.partnerships.vic.gov.au. | contract management policy and guidance material |
| Project alliancing See Project alliancing www.dtf.vic.gov.au | Project Alliancing Practitioners Guide |
| Capital development guidelines Department of Human Services www.dhs.vic.gov.au/capdev . | contract administration commissioning of facilities managing contract occupational health and safety |
| Asset lifecycle Department of Education and Early Childhood Development www.education.vic.gov.au | operations and maintenance |
| Information and Communications Technology (ICT) projects www.mmv.vic.gov.au | standard contracts whole of Victorian Government ICT contracts Government IT&T Policies 1–46 |
| Victorian Government asset management series Department of Treasury and Finance http://home.vicnet.net.au/~assetman | further information about commissioning assets other general information |
| Gateway Review Process See www.gatewayreview.dtf.vic.gov.au | Gateway Guidance material Becoming a Gateway reviewer |