Supplementary Guidance

Project Risk Management

Version 1.1 November 2013

The Secretary

Department of Treasury and Finance

1 Treasury Place

Melbourne Victoria 3002

Australia

Telephone: +61 3 9651 5111

Facsimile: +61 3 9651 5298

www.dtf.vic.gov.au

Authorised by the Victorian Government

1 Treasury Place, Melbourne, 3002

© Copyright State of Victoria 2012

This book is copyright. No part may be reproduced by any process except in accordance with the provisions of the Copyright Act 1968.

ISBN 978-1-922045-92-8

Published November 2013.

If you would like to receive this publication in an accessible format please telephone 9651 0909 or email mailto:information@dtf.vic.gov.au

This document is also available in PDF format at www.dtf.vic.gov.au

Contents

Abbreviations	2

Executive summary	3

1.	Context	4

2.	What is project risk management?	5

3.	Project risk management process	7

3.1	Risk management and the investment lifecycle	7

3.2	Establishing context	8

3.3	Risk identification /analysis	9

3.4	Risk evaluation	10

3.5	Risk treatment	11

3.6	Risk monitoring and review	12

3.7	Techniques to assist managers with risk management	13

4.	Further Resource	14

Appendix 1: Common sources of risk	15

Appendix 2: Common types of risk	1

Appendix 3: Risk management checklist	1

Appendix 4: Risk management case study	3

Appendix 5: Common elements of a project risk management plan	5

Abbreviations

BMP benefit management plan

CEO Chief Executive Officer

CFO Chief Finance Officer

DTF Department of Treasury and Finance

DPC Department of Premier and Cabinet

ERC Expenditure Review Committee (Cabinet Committee)

GRP Gateway Review Process

GSC Gateway Supervisory Committee

ICT information and communications technology

ICB investment concept brief

ILM investment logic map

IMS Investment Management Standard

IPA Information Privacy Act 2000

IPP information privacy principle

IT information technology

KPI key performance indicator

MAM meaningful; attributable; measurable

PPM project profile model

SRO Senior Responsible Owner

TEI total estimated investment VGRMF Victorian Government Risk Management Framework

Executive summary

Managing risk is an integral part of good management practice and an essential element of good corporate governance. It is something many managers do already in one form or another but when undertaken effectively across an organisation it enables continuous improvement in decision-making and facilitates continuous improvement in performance. The objective of risk management is to identify and analyse risks and manage their consequences. Organisations which manage risks effectively and efficiently are  more likely to achieve their objectives at a lower overall cost.

This project risk management guideline aims to provide those responsible for managing project risks with a common source of risk terminology and definitions. It aims to provide practical guidance on how to implement and apply risk management in a project management context.

The guideline also identifies issues and processes involved in managing project risks. It includes:

a general overview of project risk management

common sources of risk

the Victorian Government’s approach to risk management

examples of the project risk management process

a guide for risk management by phase of the investment lifecycle

an example checklist for risk management; and

a risk management case study

The guideline also provides references to material that will assist project teams and managers in identifying and managing project risks.

Box 1.0 – Tips for successful risk management

The Guideline, has been updated in March 2013 to reflect changes to Risk Standard

notably the replacement of the previous AS/NZS 4360 Risk Management Standard to the new AS/NZS ISO 31000:2009 Risk Management Standard The ISO 31000 standard represents international best practice.

# Context

This project risk management guideline is designed as supplementary guidance to Victoria’s investment lifecycle and High Value/High Risk (lifecycle guidelines)  guidelines. The lifecycle guidelines provide practical assistance to those proposing investment projects in Victoria. They help shape proposals, inform investment decisions, monitor project delivery and track the benefits projects achieve. Using the guidelines will help ensure government investments provide maximum benefit to Victoria.

The lifecycle guidelines apply to all government departments, corporations, authorities and other bodies falling under the Financial Management Act 1994. The lifecycle guidelines support the development of business cases which are mandatory for capital investments with a total estimated investment(TEI) of $10 million or more. But they can be used for investments of any type, complexity or cost.

For more information on the lifecycle guidelines go to http://www.lifecycleguidance.dtf.vic.gov.au.

The need for a project risk management guideline for all Victorian Government agencies and departments was identified in December 2006, when the former Gateway Supervisory Committee (GSC) identifies emerging issues in risk management and approved a proposal to address a Whole-of-Victorian Government (WoVG) approach to project risk management.

Box 1.1 –Common risk management issues

The intention of this guideline is to provide a broad guide reflecting good practice which can be adopted depending on size, scale, scope of the investment..   This guideline should be used as a tool. It is not a compliance process document. Rather, its  purpose is to provide agencies with guidance on useful processes that will help them frame their thinking and encourage a higher standard of risk management and capability across Government. The extent of detail should be scaled to the relative complexity of the proposal and some areas may not be relevant for all proposals.

# What is project risk management?

Risk management is the identification, assessment, and prioritization of risks(defined in ISO 31000 as the effect of uncertainty on objectives, whether positive or negative) followed by coordinated and economical application of resources to minimize, monitor, and control the probability and/or impact of unfortunate event or to maximize the realization of opportunities. Risks can come from uncertainty in financial markets, project failures (at any phase in design, development, production, or sustainment life-cycles), legal liabilities, credit risk, accidents, natural causes and disasters as well as deliberate attack from an adversary, or events of uncertain or unpredictable root-cause.

Project risk management is the culture, processes and structures, adopted by an organisation, directed towards the effective management of risk in projects. It is a pervasive management discipline that is integrated with all other project disciplines. The goal of risk management is to ensure informed decisions are made at the right time, and that there is visibility of sources of uncertainty that may impact on the success of a project.

From a project management perspective, risk management seeks to identify, prevent, contain and reduce negative impacts and maximise opportunities and positive outcomes in the interests of projects and stakeholders. It is a systematic approach that allows risks to be embraced, avoided, reduced or eliminated through a logical, comprehensive and documented strategy.

Risk management should be viewed as an ongoing process throughout a project that begins at the ‘Stage 1: Conceptualise ’the investment’s lifecycle, and continues throughout its entire lifecycle. (Detailed guidance on this phase is set out in the Stage 1: Conceptualise and is available at www.lifecycleguidance.dtf.vic.gov.au).

Projects endorsed as HVHR should ensure they have assessed the business case deliverability, costing’s, key risks, timeliness, procurement strategy and governance and seeked Treasurer’s approval before proceeding. More information on the HVHR process go to http://www.lifecycleguidance.dtf.vic.gov.au

Box 2.0 – Application of Risk Assessment

Understanding risk management entails comprehending the underlying factors that contribute to project risks. Fundamentally, this includes considering sources of risk – see Appendix 1 for ‘Common Sources of Risk’. The Victorian Government’s approach to risk management. In Victoria, risk management is mandatory under legislation including the ‘Victorian Managed Insurance Authority Act 1996’, the ‘Financial Management Act 1994’, (S. 44B).  In July 2007 the Victorian Government adopted a Victorian Government Risk Management Framework (VGRMF), which was endorsed by the Minister for Finance. This framework, which has been applied across the Whole of Victorian Government, includes an attestation by accountable officers, principally departmental Secretaries to ensure that risk management requirements are built into annual corporate planning and reporting processes. Project risk is a source that needs to be linked to this. The release of the VGRMF did not signal a change in policy but formalised and built upon existing risk processes; as part of the Government’s commitment to continuous improvement in public sector governance.

# Project risk management process

## Risk management and the investment lifecycle

The investment lifecycle is reflected in the DTF Gateway Review processes. Risk management in projects begins with concept development and continues throughout the lifecycle of the project.

While the concept of a investment lifecycle can be applied to all projects, it is acknowledged that different types of projects may have different project strategies. The project strategy defines how a project is partitioned into different stages, or phases. While an individual projects life-cycle or development and delivery strategy may be unique, they can most often be aligned to the generic Investment Lifecycle and associated Gateway review process as set out below in Figure 1.

Figure 1 Investment lifecycle and Gateway review

Project phase or stage boundaries usually represent key deliverable and decision points throughout the project. It is at these stage or phase boundaries that detailed risk assessments should occur. The risk assessment coincides with stage reviews and stage plans, and informs both the planning process and the governance board, facilitating prudent decision making. The main outputs from the risk management process throughout the investment lifecycle are as follows:

high level risk assessments coinciding with concept and options development.

risk management plan coinciding with options development.

detailed risk assessment for the life of the investment, coinciding with business case development.

detailed risk assessment reviews coinciding with project phase or stage boundaries.

treatment plans and other implementation outputs as required.

The process of risk management should commence at Stage 1: Conceptualise of a proposed project. The steps are represented in Figure 2.0 –Risk management process.

Figure 2.0 – Risk management process

## Establishing context

Risk management should align to the context of project management processes and the internal and external environment.

Ensure that the risk management strategy has been developed in accordance with best practice, including establishing criteria for risk evaluation (see risk management framework below)

Define proposal/investment scope and objectives including key performance indicators

Develop the risk management methodology to be used for assessing the proposal or project

Define the objectives and expected benefits of the risk management process

Consult with key stakeholders (internal and external) to agree appropriate levels of materiality. See Table 1

Seek government approval if required (eg. HVHR investments)

Table 1: Example risk management context and consequence table

| Consequence |
| --- |
| Rating |
| 5 | 4 | 3 | 2 | 1 |
| Description |
| Catastrophic | Major | Moderate | Minor | Insignificant |
| Objective |
| Project Objective as stated in the Project statement not achieved | Objective delayed by 50% or more | Objective delayed by less than 50% | Milestone not achieved | Negligible impact on milestones |
| Human |
| Multiple fatalities or significant irreversible effects to <50% persons | Single fatality and / or severe irreversible disability (>30%) to one or more persons | Moderate irreversible disability or impairment (<30%) | Significant but reversible disability requiring hospitalisation | No medical treatment required |
| Financial |
| 50% variance to budget | 30% variance to budget | 20% variance to budget | 10% variance to budget | 5% variance to budget |
| Environmental |
| Very serious long-term environmental impairment of ecosystem functions | Serious long-term Environmental impairment of ecosystem functions | Serious medium term environmental effects | Moderate short-term effects but not Affecting cosystem functions | Minor effect on biological or physical environment |
| Legal |
| Significant prosecution and fines | Major breach of regulation | Serious breach of regulation with investigation or report to authority with prosecution powers, moderate fine possible | Minor legal issues, non-compliances and breaches of regulation |  |
| Reputation |
| Serious public or media outcry (international coverage) | Serious public or media outcry (National coverage) | Significant adverse attention by media, public, or NGO (State based) | Media attention of local concern | Minor, adverse local public or media attention or complaints |

## Risk identification /analysis

This is the process of identifying risks relevant to the project and their causes, determining the likelihood of risks materialising, who is responsible for their management and how they might impact on the attainment of project objectives and outcomes.

identify all risks which could influence the achievement of the proposal or project’s objectives, using risk management workshops, or other appropriate research and consultation;

assess the potential likelihood and consequences of each risk using a risk scoring matrix (as set out in Table 2 below);

screen risks to filter the minor risks having low impacts and low likelihood of occurrence (be mindful that minor risks can aggregate to higher level risks, and may still need to be monitored); and

identify the ‘medium to high’ level risks that require management attention

Contingency shifting should be applied where risks change throughout the lifecycle of the project. Appendix 2 identifies a number of types of risks which might be encountered.

Table 2 Risk Scoring Matrix

| Consequence ► ▼ Likelihood | Overall Rating |
| --- | --- |
|  |  | Insignificant | Minor | Moderate | Major | Catastrophic |
|  |  | 1 | 2 | 3 | 4 | 5 |
| Almost Certain | 5 | Medium (5) | Medium (10) | Significant (15) | High (20) | High (25) |
| Likely | 4 | Low (4) | Medium (8) | Significant (12) | Significant (16) | High (20) |
| Neutral | 3 | Low (3) | Medium (6) | Medium (9) | Significant (12) | Significant (15) |
| Unlikely | 2 | Low (2) | Low (4) | Medium (6) | Medium (8) | Medium (10) |
| Rare | 1 | Low (1) | Low (2) | Low (3) | Low (4) | Medium (5) |

## Risk evaluation

Risk evaluation uses the understanding of risk obtained during risk analysis to make decisions about future actions. Ethical, legal, financial and other considerations including perceptions of risk are also inputs to the decision. Factors affecting decisions include:

whether a risk needs treatment;

priorities for treatment;

whether an activity should be undertaken; and

the number of paths should be followed

Risks are compared using criteria established to determine treatment options, costs, benefits and priorities. Treating a single risk can have implications elsewhere and can impact on other activities. Consequently, impacts and risk dependencies need to be understood to ensure that in managing one risk, an intolerable situation is not created elsewhere. Understanding the complexity of a single risk or of a portfolio of risks of an organisation is crucial for the selection of the appropriate risk responses.

To start, create a risk register (see table 3) to identify the feasible responses and treatment actions to amend and moderate major risks (see below). Risk responses may include:

risk prevention

impact mitigation

risk transfer

risk acceptance

select the best response

develop risk action schedules (treatment plans) for major risks; and

develop management measures for moderate risks

Table 3: Risk register content

| Risk |  | Part X: (Stage of the Project) | State of risk |
| --- | --- | --- | --- |
| Description |  |  | Provide description on the risk |
| Description of Consequence |  |  | Describe consequence resulting from the risk |
| Pre-Treatment Risk Assessment | Likelihood |  | What is the likelihood of the risk occurring pre-treatment? |
|  | Consequence |  | What is the consequence of the risk occurring pre-treatment? |
|  | Risk Rating |  | What is the Risk Rating pre-treatment (low, medium, significant or high) |
| Treatment Strategies |  |  | How will the risk be managed or deal with to reduce its impact? |
| Post-treatment Risk Assessment | Likelihood |  | What is the likelihood of the risk occurring post-treatment? |
|  | Consequence |  | What is the consequence of the risk post-treatment? |
|  | Risk Rating |  | What is the remaining Risk Rating post-treatment (low, medium, significant or high) |

## Risk treatment

Risk treatment involves developing strategies and action plans to maximise potential benefits and minimise the potential adverse impacts of risks.

For major undertakings, prepare a risk management plan and ensure that it aligns with the project scope

For other projects, compile and collate risk action schedules and measures

Figure 3 Alignment of roles and risk types

(Source: risk treatment diagram developed by Ian Hord)

In considering risk treatments it is sometimes helpful to categorise, or organise the risks into named categories or tiers aligned with the context of the project and aligning the function of the treatment to particular project outcomes. Figure 3 demonstrates this split of risk types and responsibilities. Table 4 - Risk treatment schedule provides an example template which can be used to capture the required information. The treatments can then be viewed clearly in terms of their desired effect on particular elements of the project, assisting in identifying the appropriate tools and workforce required to assess and treat each risk. For example:

Tier 1 (or Strategic) – Strategic level risks are generally those risks that will have an impact on the strategic (or high level) outcomes for the project. These risks generally give rise to ‘treatment strategies’ or deliberate treatment actions that may become part of the scope of work of the project, or be provided for in the form of pre-planned actions which may draw upon various contingent reserves of time, funding or scope negotiation.

They are generally monitored at the highest levels of direction or governance in the project. Tools such as the Investment Logic Map or Strategic Risk Workshops (SWOT or other methods) involving senior executives, strategic planners or key stakeholders would identify the key sources of uncertainty which may impact on the desired project outcomes - ‘what are the strategic objectives for this project and what might prevent us achieving them?’

Tier 2 (or Operational) – These risks pertain more to the delivery of the project and will be the focus of the Project Director (or Project Manager). ‘What do we need to deliver, when do we need to deliver it, to what quality should it be delivered and how much do we have to spend? What could prevent us delivering against these objectives?’

Tier 3 (or Compliance) – These risks relate more to administration and operational standards, for example with mandatory design standards or standard financial and operating procedures (compliance with the Financial Management Act for example). ‘What standard procedures and audit mechanisms do we need?’ ‘What skills and capabilities should the auditors have?’

Treatment options should be specific, accountable and clear enough for others to understand how the risk is to be treated. Risk treatments need to be assessed to ensure good cost benefit ratio. Where cost benefit ratio is poor, alternative treatment should be sought. Examples of treatments include:

establish contingency plans

change plans to reduce risk

initiate further investigations to reduce uncertainty through the gathering of more detailed information

purchase insurance

transfer risk via contracts

set contingencies in cost and schedule estimates

set tolerances in specifications

Table 4: Risk treatment schedule (template example):

|  | Identified Project Risks | Cause | Risk Ranking | Treatment Strategies | Responsible Person | Due Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |

## Risk monitoring and review

Monitor the current known risks to the project and the effectiveness of the respective treatments and controls. Review the identified risks and consider whether new risks may be evident and should be included on the risk register and treatments developed. This may include:

ensuring that the risk has an identified owner (the person/s with the authority and resources to decide on the appropriate response, and give effect to the selected treatment)

implementing the risk treatment plan in accordance within the intended schedule and other key parameters

ensuring that risk management activities continue to occur in accordance with the project risk management plan

periodically reviewing risks via the risk register/risk log/consultation and evaluate the need for additional risk management effort

monitoring the progress and effectiveness of implemented treatment strategies. Are existing contingencies still applicable and resourced to treat remaining risks?

The main output from the project risk management process is the definition of actions, associated schedules, management measures and assignment of responsibility for their implementation. For designated undertakings, the risk management plan summarises the risk analysis process and details the action strategies for managing individual risks.

Consistently applying all of the stages identified by the risk management process is vital to ensure project success. The implementation or ‘Treat Risks’ stage, is generally the most poorly executed of the process. Planning for implementation requires particular attention to resources required, defining responsibilities for all personnel and suitable timing of tasks.

It is important that each project team has sufficient resources to implement their risk management plan effectively. Further to this, each team member must have a clear understanding about their role in mitigating the projects risks.

## Techniques to assist managers with risk management

Many specialised tools have been developed to enhance the role of the manager in risk management. Such techniques provide assistance in analysis and evaluation of tasks – some of which are summarised in Table 5 ‘Specialist risk management techniques’. Departments and agencies should select  and apply the tools in a way which will best assist them in addressing the specific needs of their project. Table 5: Specialist risk assessment techniques

| Technique | Application |
| --- | --- |
| Decision Analysis (1) | Choice amongst uncertain alternatives |
| Event Tree Analysis (2) | Identifies the consequences of an initiating event |
| Failure Modes, Effects & Criticality Analysis (1) | Analysis of designs and operating plants; may be directed to safety, plant integrity or ensuring production is maintained |
| Fault Tree Analysis (2) | Identifies the causal factors that may lead to a risk arising |
| Hazard Analysis (1) | HAZOP Safety analysis for operating plant |
| Scenario Analysis (3) | Economic appraisals and feasibility studies |
| Sensitivity Analysis (3) | Very wide application, from economic appraisal and financial feasibility to operations and maintenance models |

(1) Ward, E 2007, Advances in Decision Analysis: From Foundations to Applications

(2) Zio, E 2007, Introduction to the Basics of Reliability and Risk Analysis

(3) Cox, D 2006, The Mathematics of Banking and Finance

A risk management checklist is another simple tool that managers can use to keep track of risks throughout the lifecycle of their project and seek approval that risk processes have been followed before moving onto the next phase. An example checklist for managing risks can be found in Appendix 3 ‘Checklist for risk management’ and is a useful starting point for projects to develop their own.

It is common for lessons learned exercises to reflect on negative examples of risk management to assist learning. Appendix 4 offers a different perspective by exploring the positive risk management process that was applied to a Barwon Water Project. One of the highlights of this particular project was the risk management mindset embedded across the Project Team along with the quality of the documentation created to support this. Examples of risk management documents such as a risk management plan (or framework), risk scoring matrix and risk register have been included for Project Managers who are documenting risk management for their own projects.

# Further Resource

Further information may be obtained from the following publications/websites. Please advise the Department of Treasury and Finance if your agency, or other agencies, have additional information that should be included in this listing.

Victorian Auditor General’s Office 2004, Managing Risk Across the Public Sector, viewed

1 April 2008,

<http://archive.audit.vic.gov.au/reports_better_practice/Risk_guide_final.pdf > pp 3.

Victorian Managed Insurance Authority (VMIA) 2007, Risk Attestation, viewed April 8 2008.

http://www.vmia.vic.gov.au/Risk-Management/Guides-and-publications/Risk-Management-Guidelines/VGRMF/Risk-attestation.aspx

Ward, E 2007, Advances in Decision Analysis: From Foundations to Applications, Cambridge University Press.

Zio, E 2007, Introduction To The Basics Of Reliability And Risk Analysis, World Scientific, Singapore.

Appendix 1: Common sources of risk

| Source of Risk | Example |
| --- | --- |
| Political | Parliamentary support, community support, government endorsement, policy change. |
| Economic | Economic growth, exchange rate variation, inflation. |
| Socio-Cultural | Community expectations, pressure groups. |
| Technological | Technological change, technology and obsolescence, communications or network failure. |
| Legal | Change in legislation. |
| Commercial & Strategic | Competition, market demand levels, stakeholder perceptions, market share private sector involvement. |
| Organisational | Industrial relations, resources shortage, management capabilities/structures, operational policies, work practices, personnel skills. |
| Environmental | Site availability/zoning, approval processes, endangered species, conservation/heritage, degradation/contamination, visual intrusion, force majeure events, natural events/disasters. |
| Procurement and Contractual | Contract selection, client commitment, consultant/contractor performance, negligence of parties, damages and claims, errors in documentation, insurance and indemnities. |
| Construction and Maintenance | Contractor capability, design viability, geotechnical conditions, quality controls, equipment availability and breakdowns, OH&S procedures. |

Risk management commonly required by project team members at each phase of the investment lifecycle

- A risk assessment by itself is of little value. Evidence that the risk information is being integrated into project strategies is shown through linkages between risk assessment and other key areas of project planning and management.

Projects deemed medium or high risk via the Project Profile Model (PPM) should undertake the Gateway Reviews at key decision points: Concept assessment, Business Case, Readiness for Market, Tender Decision, Readiness for Services and Benefits Evaluation.

Delegate approval represents the acknowledgement, understanding and acceptance of the risk management process (risk management plan, risk assessment) by the delegate. Delegate sign-off would normally be expected for the risk management plan as well as the initial, detailed risk assessment.

A statement of context describes the environment in which the project exists. A description may also include other projects/programs that the project interacts or shares dependencies. It should link the project’s existence to strategic outcomes, government policy and other relevant objectives.

A high level risk assessment makes allowance for the early stages of planning. Detailed information on risks is often not available however it is possible to identify the key categories and potential sources of risk.

A start stage risk assessment is undertaken to identify any risks to the successful development of the particular project stage. Risks to strategic fit may include lack of access to adequately skilled resources, poorly defined outcomes and lack of adequate data.

At options assessment detailed information on risks is not always available however the risk assessment is part of the ongoing development of the risk database. It is possible to gather information from like projects and begin to consider risks of a like nature

The project risk management plan describes the approach to risk management throughout the project.

A detailed risk assessment may be undertaken at business case phase that expands on the higher level risk assessments and focuses on one (but sometimes two) of the preferred options.

The risk assessment at Stage 3: Procure is a stage/start risk assessment that should consider all issues to do with procurement. The procurement risks are further developed in the detailed risk assessment and again at the project tendering stage.

A risk profile can be a narrative or graphical representation of key risk exposures for the project. Inherent project risks are linked to the environment and the desired outcomes that culminates with a statement of the overall risk level for the project. The risk level in many respects will relate to the ‘inherent’ risk of the project.

Capturing ‘lessons learned’ is an iterative process, commencing at the beginning of the investment lifecycle and recurring at every stage in the lifecycle. A lessons learned log can be kept in conjunction with a risk register.

The purpose of the contract risk allocation plan is to make explicit the thought process applied to the selection or construction of a particular contract for engagement with a service provider or supplier. The risk allocation must be realistic, taking account of which risks can be realistically borne by each party to the contract.

Appendix 2: Common types of risk

| Type of risk and definition |
| --- |
| Context | Examples |
| Site Risk: the risk that the project land will be unavailable or unable to be used at the required time, in the manner or at the cost anticipated, or that the site will generate unanticipated liabilities, with the result that the contracted service delivery and/or projected revenues are adversely affected. |
| Site risk is a significant issue at the inception of the project and during construction, and becomes less important in the operational phase. However, environmental risk may materialise during the operational phase if previously unidentified problems come to light or the project operation itself gives rise to pollution or to land or groundwater contamination | Unanticipated land acquisition costs and delays in acquisition; Planning permission being refused or granted on onerous terms; Delays and costs arising from environmental impact assessments, including the risk of route-diversion of linear infrastructure and the costs of special measures to protect environmental values; contamination risks and liability for clean-up; Liability for contamination of adjacent land; Costs and delays associated with archaeological and cultural heritage discoveries; Costs and delays arising from negotiating indigenous land use agreements (ILUAs) on land which may be subject to native title; The site subsequently proves to be an inefficient/unsuitable location for delivery of the services; and Existing infrastructure on the site proves to be unsuitable for the project proposed for the site, e.g. it may not complement the proposed infrastructure. |
| Design, construction and commissioning risk is the risk that the design, construction or commissioning of the facility or certain elements of each of these processes, are carried out or not carried out in a way which results in adverse cost and/or service delivery consequences. The consequences if the risk materialises may include delays and/or cost increases in the design, construction and commissioning phases, or design or construction flaws which may render the infrastructure inadequate for effective service delivery, either immediately or over time. |
| Design, construction and commissioning risks are the core risks of the development phase and are among the most likely risks to materialise. | The design of the facility is incapable of delivering the services at anticipated cost Events occur during construction which prevent the facility being delivered on time and on cost Either the physical or the operational commissioning tests which are required to be completed for the provision of services to commence, cannot be successfully completed |

| Sponsor risk is the risk that: where the SPV (Special Purpose Vehicle) and/or its sub-contractors are unable to fulfil their contractual obligations to government, government will be unable to enforce those obligations against the sponsors or recover some form of compensation or remedy from the sponsors for any loss sustained by it as a result of the SPV's breach; or that the sponsor(s) is, for security or other probity reasons, inappropriate or unsuitable to be involved in, or (through the private party) connected with, the delivery of a Partnerships Victoria project, and in so being may harm the project or bring it into disrepute. |
| --- |
| Sponsor and financial risks stem from the complex structure involved in these public private partnership arrangements. | The risk that the private party: Is unable to provide the required services or becomes insolvent Is later found to be an improper person for involvement in the provision of these services or financial demands on the private party or its sponsors exceed its or their financial capacity causing corporate failure Is subject to a change in ownership |
| Financial risk refers to the following risks: the risk that the financiers (debt and equity) will not provide or continue to provide funding to the project (risk of financial uncertainty); the risk that financial parameters will change prior to the private party fully committing to the project, potentially adversely affecting price (financial parameter risk); and the risk that the financial structure is not sufficiently robust to provide fair returns to debt and equity over the life of the project (and hence calls into question the continuing viability of the project) (risk of robustness of financial structure). |
| Sponsor and financial risks stem from the complex structure involved in these public private partnership arrangements. | Interest rates pre-completion Financing unavailable Further finance Refinancing benefit Tax changes |
| Operating risk is the risk that the process for delivering the contracted services — or an element of that process (including the inputs used within or as part of that process) — will be affected in a way which prevents the private party from delivering the contracted services according to the agreed specifications and/or within the projected costs. |
| Operating risks typically relate to production and operation, availability and quality of inputs, quality and efficiency of management (including contract management) and operation, maintenance and upgrade requirements. | Operating costs may vary from original budgeted projections due to: higher production costs, higher input costs, reduced input quality, unsuitable design, reduced equipment reliability, higher maintenance costs, occupational health and safety issues, unplanned equipment/plant upgrades, inherent defects, technical obsolescence Performance standards may deteriorate below project specifications or may not be maintained due to: reduced input quality, unsuitable design, reduced equipment reliability, inherent defects, force majeure events |
| Market risk is the risk that: demand for a service will vary from that initially projected; or price for a service will vary from that initially projected, so that the total revenue derived from the project over the project term varies from initial expectations. |
| Private businesses and government are exposed to various levels of market risk in delivering services. Various events (see next column) may result in the materialisation of market risk each of which may have demand or price consequences, or both. | General economic downturn Change in government policy Competing substitute products or introduction of new competitors Competitive pricing for alternate services Change in target market composition or demographics Technical obsolescence or innovation Shift in industry activity/focus |
| Industrial relations risk is the risk of any form of industrial action — including strikes, lockouts, work bans, work-to-rules, blockades, picketing, go-slow action and stoppages — occurring in a way which, directly or indirectly, adversely affects commissioning, service delivery or the viability of the project. |
| Industrial relations risk may materialise at both the construction and operational phases of the project, but it is likely to be more pronounced at the construction phase. Where the risk does materialise, it may have a major effect on the economics of a project and may affect both inputs and outputs. | Delay in delivering construction materials and on site stop-work action may cause delay costs, including increased finance and construction costs. Delay through industrial action may also result in loss of revenue to the private party by delaying the start of the payment regime. During the operational phase, industrial action may delay or frustrate service delivery and may cause interface risks to materialise where provision of core services is dependent on the service that is being disrupted. |
| Legislative and government policy risk is the risk that government will exercise its powers and immunities, including but not limited to the power to legislate and determine policy, in a way which negatively impacts on or disadvantages the project. |
| The risk of changes in legislation, changes in government policy and the election of a new government are often viewed by the private party as critical risk factors when contracting with government. The risk of legislative and policy change is complicated further by Australia’s character as a federation, where powers are divided between the Commonwealth and the States. | Government or the contracting agency (on behalf of government) will not have the power to enter the contract or its ability to do so will be limited; From the private party's viewpoint, government will be immune from legal action; No remedy being available at law to prevent government from legislating to affect the rights of the private party (often identified as sovereign risk); The relevant Minister(s) will grant or refuse to grant statutory consents in a way which disadvantages the project; Government will use its power to propose or alter legislation and subordinate instruments, or that Parliament will reject, accept or amend such legislation and subordinate instruments, in a way that negatively impacts on or disadvantages the project; Government will adopt or change policy, including policies with respect to the project, in a way which impacts on the project's mode of operation or alters the relationship between the project and competing public infrastructure; Statutory regulators will exercise their powers to disadvantage the project; and Government will require changes in service specifications or will otherwise interfere with the private party's business operation in a way which negatively impacts on or disadvantages the project. |
| Interface risk is the risk that the method or standard of delivery of the contracted services will prevent or in some way frustrate the delivery of the core services or vice versa. |
| Interface risk arises where a private party and government both provide services from within or in relation to the same infrastructure facility. | Sub-standard ancillary service provision will prejudice government’s ability to deliver its core services. Private parties will encounter circumstances which inhibit their ability to deliver the contracted services to specification or at their projected cost. |

| Network risk is the risk that the network(s) needed for the private party to deliver the contracted services will be removed, not adequately maintained or otherwise changed — including being extended to include additional infrastructure or services not foreseen or anticipated at the date of the contract — in a way that either prevents or frustrates the delivery of the contracted services, affects the quality of the specified outputs or in some other way affects the viability of the project. |
| --- |
| Network risk arises when the contracted services or method of delivery of those services are linked to, rely on or are otherwise affected by certain infrastructure, inputs and other services or methods of delivering the contracted services | The network or part of the network which underpins or complements the provision of the contracted services will be removed, not maintained or otherwise changed so as to prevent or frustrate the private party’s ability to deliver the contracted services. The existing network will be removed, developed or extended to include new systems or services or changed in some other way which, in each case, creates or increases competition with the contracted services, jeopardising project revenues. |
| Force majeure risk is the risk that a specified event entirely outside the control of either party will occur and will result in a delay or default by the private party in the performance of its contractual obligations. |
| Force majeure events traditionally fall into two categories. The first refers to events which can be described as an 'act of God' or a 'superior force'. The second refers to events which can be described as 'political’ | ‘Act of God’ events are: Storms, lightning, cyclones, earthquakes, natural disasters and actions of the elements; Tidal waves, floods and droughts; Landslides and mudslides; and Nuclear, chemical or biological contamination. 'Political' events are: Civil riots, rebellion, revolution, terrorism, civil commotion, insurrections and military and usurped power; Malicious damage; Acts of a public enemy; and War (declared or undeclared). |
| Asset ownership risk is the risk that events such as loss events, technological change, construction of competing facilities or premature obsolescence will occur, with the result that the economic value of the asset may vary, either during or at the end of the contract term, from the value upon which the financial structure of the project is based. |
| Asset ownership risk falls into two categories; during the contract term and at the end of the term | Risks during the contract term: Maintenance and refurbishment risks; Risk of obsolescence; Risk of loss arising from force majeure events; and Risk of loss through contractual default. Risk at end of term: Residual value risk. |

Appendix 3: Risk management checklist

| Stage | Tasks |
| --- | --- |
| Stage 1 Initiation |
| Assemble Risk Management resources Appoint the team leader and ensure a breadth of skills/experience within the team Assign Risk Management responsibilities appropriate to task |
| Stage 2 Proposal familiarisation |
| Specify objectives and criteria Familiarise the team with the proposal, assemble documentation and define the key objectives Assess the proposal in relation to the Agency’s objectives and strategies Determine assessment criteria for proposal |
| Define key elements Define key elements (target 20-50 elements, items or activities) to structure risk analysis |
| Stage 3 Risk analysis |
| Identify risks Prepare a comprehensive schedule of risks for each element Describe each risk and list the main assumptions |
| Assess risk likelihoods and consequences Assemble data on risk and their consequences Assess risk likelihoods Assess risk impacts |
| Identify significant risks Rank risks to reflect impacts and likelihoods Where applicable, estimate risk factors Discard/accept minor risks Identify moderate risks for management measures Identify major risks for detailed risk action planning |
| Stage 4 Risk response planning |
| Identify feasible responses For each moderate and major risk, identify the feasible responses Responses may include: Risk prevention Impact mitigation Risk transfer and insurance Risk acceptance Describe each feasible response and list main assumptions |
| Select the best response Evaluate the benefits and costs for each response Select the preferred response |
| Develop management measures and action schedules Specify Risk Management measures for moderate risks Develop risk action schedules for major risks Actions required (what is to be done?) Resources (what and who?) Responsibilities (who?) Timing (when?) For other projects, collate and summarise risk action schedules and measures |
| Stage 5 Reporting |
| For designated proposals, produce the Risk Management Plan |

Stage 6 Risk Management implementation

Implement measures and action strategies Monitor the implementation Assign responsibilities Timing Undertake periodic review and performance evaluation

*This is an example checklist only and should be adapted to fit specific project needs.

Appendix 4: Risk management case study

Risk management example of Best Practice – Electronic records Pilot Project (Fictional Case Study)

The Department of Portfolio, Program and Project Management Delivery (DPPMD) undertook an Online Records Management Pilot Project with grant funding provided by the State budget process). The objective of the project was to pilot and evaluate the use of government-to-government and government to business electronic document management in two government agencies - the Department of Information and Technology, (DoIT) and the Department of Education and Learning (DoEL).  The pilot provided an opportunity for the two agencies to test out a number of different approaches to moving from a paper less -based records management process to more electronic processes.

The project involved the development of a number of key partnerships with organisations including the Department of Treasury and Finance, Department of Records Management (DoRM), Industrial Suppliers, IT Industry Council, and key suppliers to the pilot agencies.

Summary of Findings

Like many other similar projects undertaken across government, it faced a number of implementation issues. However, the project has now been completed. The learning’s gained throughout the project should be shared throughout government agencies and suppliers to improve future project outcomes.

Major risks, issues and changes which impacted on the project are:

- Scope management,

- Lack of formal controls

- No formal escalation processes,

- Lack of  formal risk management process,

- Process for stakeholder engagement, and

- Lack of Steering Group participation.

Risk management

The results of an initial risk assessment were documented in the Project Business Plan. A separate Risk Register was not maintained throughout the project. The Project Status Report was used as the method for capturing and reporting threats to the project.

Project risk management is an iterative process that needs to be undertaken at each stage of the project life cycle; there are typical risks and strategic decisions/ actions that need to be taken at each project life cycle stage. This did not occur due to poor risk management processes.

Importance of effective and regular risk assessments feeding into the cost estimating process (allocate contingencies to the identified risks, detailed risk analysis is important, e.g. Monte Carlo, three point estimate, etc.) non of this applied to the costing process which contributed to poor benefits realisation estimates envisaged with the online records management.

Both departments struggled with organisational ability to integrate project risk assessment outcomes into organisation-wide risk profiles.

A review of the Project Status Reports shows that the reported risk profile did not appear to change much early in the project. This starts to occur in May 2012 when two new risks were added and in June 2012 as the significance of the difficulties with the departmental requirements became apparent and the likelihood of the risk materialising.

There are no outstanding risks from the project to be forwarded to other parties.

Lessons learnt from the project

- Little effort went into confirming the identified risks of the Project Business case and its suggested actions to mitigate the identified risks.

- Once the risk of failure to manage the project in accordance with the requirements of the PCB was acknowledged as having occurred, the PCB lacked the necessary skills to employ strategies to focus the team on effective corrective actions.

- One stakeholder observed that the major risk to the project was the lack of active involvement by all parties, but remained unconvinced that active management of this risk would have made any difference to the outcome given the poor scope management activities.

Issues Management

- Most stakeholders felt that the key issues had been identified however inadequate mechanisms were put in place to manage them.

- The Project Team developed and utilised an Issues Register to capture and monitor project issues.

Appendix 5: Common elements of a project risk management plan

Project profile/context

Project strategy

Risk profile

overall project risk rating

organisations appetite and tolerance for risk

Risk management policy

Risk management objectives

Project governance and risk management

Risk management responsibilities

Communication and consultation

Stakeholder engagement/management

Relevance to other project management functions

Escalation processes

Risk management methodology for the project

Risk identification

Analysis

qualitative methods?

quantitative methods?

Evaluation

likelihood, consequence, risk level matrices

risk ratings

control effectiveness assessments

Treatments

treatment options

process – cost benefit

treatment selection

treatment plan templates

treatment monitoring

Risk monitoring

Issues management

Preliminary risk assessment and major/strategic risk categories

Strategic risk register (limited detail)

Templates

Risk register/log

# Text boxes

Tips for successful risk management

For the risk management process to be successful, it is imperative to address the

following issues:

Know what you want to get out of the process. It may seem obvious but many people start a risk management process without knowing what they want to get out of it.

Determine ownership. It is imperative for people to be accountable for risks, controls and action plans.

Undertake cost-benefit analysis. Many treatment plans are not cost-effective and will never get done. There must always be an opportunity to reject recommended treatments, and look for alternatives.

Gateway Review teams consistently identify project risk management as an issue in projects in the following areas:

comprehensive identification of project/program risks

thorough analysis and assessment of identified project/program risks by key stakeholders

identification, development of risk treatment and strategies

effective allocation of risk roles and responsibilities

regular monitoring, evaluation and updating of risk management plans and risk registers, and maintenance of risk management processes for the duration of the project/ program

understanding of the risk management processes (ISO:31000) and application in a project management context; and

awareness that risk management is an iterative process throughout the lifecycle of a project, where some risks will disappear and new ones will emerge

Risk assessment can be applied at all stages of the investment lifecycle and should be applied many times with different levels of detail to assist in the decisions that need to be made at each phase.

For example, during Stage 1: Conceptualise, when an opportunity is identified, risk assessment may be used to decide whether to proceed or not. Where several options are available risk assessment can be used to evaluate alternative concepts to help decide which provides the best balance of positive and negative risks.

During Stage 2: Prove (full business case stage) risk assessment contributes to ensuring that system risks are tolerable; contributes to the design refinement process; contributes to cost effectiveness studies and identifies risks impacting upon subsequent lifecycle phases.

As the activity proceeds risk assessment can be used to provide information to

assist in developing procedures for normal and risk event conditions.