## Sheet1
Project | Sector | Total estimated investment | Entity | Budget year | Estimated completion date | Project status | Estimated expenditure to 30.06.2023 | Estimated remaining expenditure | Fixed notes
85 by 2025 (Level Crossing Removal) (metropolitan various) | Transport | $8,832m | Department of Transport and Planning | 2023-24 | qtr 2 2025-26 | Existing | $5,393m | $3,439m | The TEI has decreased by $114.306 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
A Pathway to more acute mental health beds: Responding to the interim report of the Royal Commission into Victoria's Mental Health System (statewide) | Health and human services | $492m | Department of Health | 2023-24 | qtr 3 2024-25 | Existing | $428m | $64m | The estimated completion date has been revised to quarter 3 2024-25 in line with a revised project schedule.
Acquisition of Bendigo GovHub (Bendigo) | Transport | $121m | Department of Transport and Planning | 2023-24 | qtr 4 2022-23 | Completed | $121m | $0m | This initiative moved from the Department of Treasury and Finance to the Department of Transport and Planning due to machinery of government changes.
Additional acute mental health beds in regional Victoria (various) | Health and human services | $196m | Department of Health | 2023-24 | qtr 4 2028-29 | Existing | $5m | $191m | The estimated completion date has been revised to quarter 4 2028-29 in line with a revised project schedule.
Additional VLocity trains (regional various) | Transport | $340m | Victorian Rail Track | 2023-24 | qtr 4 2023-24 | Existing | $316m | $24m
Arden Precinct Redevelopment (metropolitan) | Transport | tbc | Department of Transport and Planning | 2023-24 | tbc | Existing | tbc | tbc | The TEI and estimated completion date for this initiative are not disclosed at this time to ensure negotiations with affected landholders are not prejudiced.
Ballarat Health Services expansion and redevelopment and the new Central Energy Plant (Ballarat) | Health and human services | $596m | Department of Health | 2023-24 | qtr 2 2028-29 | Existing | $62m | $534m | The TEI has increased by $54.188 million due to a revised project scope to include a helipad and a 400-space car park.
Barwon Heads Road Upgrade (Barwon Heads) | Transport | $365m | Department of Transport and Planning | 2023-24 | qtr 2 2023-24 | Existing | $274m | $91m | The TEI includes $292.000 million of Commonwealth Government funding.
Barwon Women's and Children's Hospital (Geelong) | Health and human services | $500m - $525m | Department of Health | 2023-24 | qtr 2 2029-30 | Existing | $9m | tbc | The estimated completion date was previously ‘tbc' and has now been disclosed following further project development. The TEI and remaining expenditure will be confirmed following the completion of the tender process. The TEI includes $50.000 million of Commonwealth Government funding under the Community Health and Hospitals Program agreement.
Bendigo Law Courts Redevelopment (Bendigo) | Justice and emergency services | $152m | Court Services Victoria | 2023-24 | qtr 4 2023-24 | Completed | $129m | $24m
Best Start, Best Life: Infrastructure (statewide) | Education and training | $2,221m | Department of Education | 2023-24 | qtr 4 2027-28 | New | $8m | $2,213m | The TEI includes $1,308.0 million of funding provided as part of the 2022-23 Victorian Economic and Fiscal Update, and $912.8 million published in Budget Paper 3 2023-24. The TEI allocation is for land acquisition and construction of the early learning infrastructure facilities which will be completed by the end of 2027-28. Best Start, Best Life is a ten-year infrastructure program with an overall program completion date of 2032-33.
Better aged care services for regional Victorians (regional various) | Health and human services | $162m | Department of Health | 2023-24 | qtr 1 2028-29 | New | $0m | $162m | This initiative is part of Labor's Financial Statement 2022.
Big Housing Build (statewide) | Health and human services | $3,067m | Director of Housing | 2023-24 | qtr 1 2027-28 | Existing | $1,334m | $1,733m | The estimated completion date has been revised to quarter 1 2027-28 due to the ongoing economic impact of COVID-19 including supply chain disruptions.
Big Housing Build physical improvements (statewide) | Health and human services | $184m | Director of Housing | 2023-24 | qtr 4 2026-27 | Existing | $82m | $102m
Building a better hospital for Melbourne's inner west (Footscray) | Health and human services | $1,999m | Department of Health | 2023-24 | qtr 1 2025-26 | Existing | $1,002m | $996m | This project is a PPP where the upfront capital investment has resulted in additional scope and whole-of-life benefits whilst remaining within the project’s affordability benchmark. The TEI reflects the inclusion of the Victoria University project components which are to be reimbursed by Victoria University.
Building a bigger and better Latrobe Regional Hospital (Traralgon) | Health and human services | $224m | Department of Health | 2023-24 | qtr 4 2023-24 | Existing | $137m | $86m | The TEI has increased by $6.500 million due to this initiative being combined with the 'Mental health and alcohol and other drugs emergency department hubs in regional Victoria (Traralgon)' initiative funded in the 2022-23 Budget.
Building a world class Geelong Performing Arts Centre (Geelong) | Culture, sport and community | $140m | Other PNFC | 2023-24 | qtr 1 2023-24 | Existing | $140m | $0m | The estimated completion date has been revised to quarter 1 2023-24 to reflect the planned public opening date of the Geelong Performing Arts Centre.
Building a world class hospital for Frankston families (Frankston) | Health and human services | $1,118m | Department of Health | 2023-24 | qtr 3 2025-26 | Existing | $249m | $869m | This project is a PPP where the upfront capital investment has resulted in additional scope and whole-of-life benefits whilst remaining within the project’s affordability benchmark. The estimated completion date reflects the completion of main works by the end of 2025, with the remaining refurbishment and other works completed by 2027-28.
Building a world class hospital in Maryborough (Maryborough) | Health and human services | $115m | Department of Health | 2023-24 | qtr 2 2024-25 | Existing | $11m | $104m | The TEI has increased by $15.000 million due to market conditions.
Building works stimulus (statewide) | Health and human services | $175m | Director of Housing | 2023-24 | qtr 4 2023-24 | Existing | $173m | $2m | The TEI has increased by $20.310 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2023-24 due to the ongoing economic impact of COVID-19 including supply chain disruptions.
Car Parks for Commuters (statewide) | Transport | tbc | Victorian Rail Track | 2023-24 | tbc | Existing | $375m | tbc | The TEI includes $132.899 million of Commonwealth Government funding for the delivery of car parks and related infrastructure. This project may be subject to the Commonwealth Infrastructure Investment Program review.
Carlton redevelopment - 246 units/sites (North-West metropolitan) | Health and human services | $146m | Director of Housing | 2023-24 | qtr 2 2023-24 | Existing | $146m | $0m | The project's location has changed from ‘statewide’ to ‘North-West metropolitan’ to better reflect the project’s service area.
Caulfield Rationalisation Works (metropolitan various) | Transport | $237m | Victorian Rail Track | 2023-24 | qtr 4 2025-26 | Existing | $131m | $106m | The TEI has decreased by $3.393 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
City Loop fire and safety upgrade (stage 2) and intruder alarm (Melbourne) | Transport | $465m | Victorian Rail Track | 2023-24 | qtr 2 2023-24 | Existing | $324m | $141m | The TEI has decreased by $4.322 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Clyde Road upgrade (metropolitan southeast) | Transport | tbc | Department of Transport and Planning | 2023-24 | tbc | New | $15m | tbc | The TEI is funded by $243.679 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program Review.
Community Safety Statement (statewide) | Justice and emergency services | $315m | Department of Justice and Community Safety | 2023-24 | various | Existing | $307m | $8m
Cooling our public housing towers (metropolitan) | Health and human services | $136m | Director of Housing | 2023-24 | qtr 4 2026-27 | New | $0m | $136m | This initiative is part of Labor’s Financial Statement 2022.
COVID catch-up plan (statewide) | Health and human services | $200m | Department of Health | 2023-24 | qtr 4 2028-29 | Existing | $82m | $118m | The TEI, cash flows, and estimated completion date were previously ‘tbc' and have now been disclosed following the outcome of commercial negotiations for the leasing of the Frankston Public Surgical Centre. The TEI includes the Frankston Public Surgical Centre lease and additional fit-out costs, funding for additional rapid access hubs previously held in contingency and additional funding for the Surgical Equipment Innovation Fund. The estimated completion date has been updated to quarter 4 2028-29 to reflect the term of the Frankston Public Surgical Centre lease.
Dandenong Corridor Readiness Works (metropolitan various) | Transport | $276m | Victorian Rail Track | 2023-24 | qtr 2 2025-26 | Existing | $191m | $85m | The TEI has decreased by $0.785 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Delivering the Road Safety Action Plan (statewide) | Transport | tbc | Department of Transport and Planning | 2023-24 | tbc | Existing | $89m | tbc | The TEI includes $142.484 million of Commonwealth Government funding and a further $103.067 million of funding from the Transport Accident Commission. This project may be subject to the Commonwealth Infrastructure Investment Program Review.
E-Class Tram Infrastructure Program (metropolitan various) | Transport | $789m | Victorian Rail Track | 2023-24 | qtr 4 2027-28 | Existing | $612m | $177m | The TEI has increased by $47.812 million due to additional project scope and market escalation. The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule.
Emergency Departments Expansion Program – Casey Hospital and Werribee Mercy Hospital (Casey) (Werribee) | Health and human services | $236m | Department of Health | 2023-24 | qtr 4 2026-27 | Existing | $2m | $234m
Emergency Services High-priority infrastructure (statewide) | Justice and emergency services | $126m | Department of Justice and Community Safety | 2023-24 | qtr 4 2024-25 | Existing | $72m | $54m
Essential maintenance and compliance (statewide) | Education and training | $104m | Department of Education | 2023-24 | qtr 4 2025-26 | New | $0m | $104m
Essential maintenance and compliance 2022-23 (statewide) | Education and training | $120m | Department of Education | 2023-24 | qtr 4 2025-26 | Existing | $1m | $119m
Expanding mental health treatment facilities for Victoria's youth (statewide) | Health and human services | $141m | Department of Health | 2023-24 | qtr 4 2024-25 | Existing | $11m | $130m
Forensic Mental Health Expansion Project Stage 1 and 2 (Fairfield) | Health and human services | $462m | Department of Health | 2023-24 | qtr 4 2024-25 | Existing | $71m | $392m | The project name has changed from 'Expanding and improving bed-based forensic mental health services: Thomas Embling Hospital (Fairfield)' when it was published in the 2022-23 Budget. The TEI has increased by $123.897 million due to combining this initiative with the 'Redevelopment of Thomas Embling Hospital - Stage 2 (Fairfield)' initiative funded in the 2022-23 Budget.
FRV Capital Upgrades Program (statewide) | Justice and emergency services | $107m | Fire Rescue Victoria | 2023-24 | qtr 4 2027-28 | Existing | $24m | $83m | The TEI has increased by $3.202 million due to a revised project scope. The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule.
Geelong City Deal (Geelong) | Culture, sport and community | $407m | Department of Jobs, Skills, Industry and Regions | 2023-24 | qtr 4 2025-26 | Existing | $90m | $317m | There has been a net decrease in TEI of $7.250 million, resulting from a $17.100 million reduction in TEI due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards, and a $9.850 million increase in TEI due to additional funding to meet forecast capital costs to deliver the Geelong Convention and Exhibition Centre. The TEI includes $156.000 million of Commonwealth Government funding.
Geelong Fast Rail (regional various) | Transport | tbc | Victorian Rail Track | 2023-24 | tbc | Existing | tbc | tbc | The State and Commonwealth governments have committed $2.000 billion each to the project. This project may be subject to the Commonwealth Infrastructure Investment Program review.
Goulburn Murray Water - Water efficiency project (statewide) | Water | $131m | Goulburn Murray Rural Water Corporation | 2023-24 | qtr 4 2023-24 | Existing | $71m | $60m | The TEI has increased by $8.249 million due to a revised project scope and updated cost information.
Goulburn Valley Health redevelopment - planning and development (Shepparton) | Health and human services | $229m | Department of Health | 2023-24 | qtr 2 2023-24 | Existing | $225m | $5m | The estimated completion date has been revised to quarter 2 2023-24 in line with a revised project schedule.
Goulburn-Murray Water - Water Efficiency Project (statewide) | Water | $131m | Department of Environment, Energy and Climate Action | 2023-24 | qtr 4 2023-24 | Existing | $102m | $29m | The TEI has increased by $37.500 million due to additional Commonwealth Government funding. The TEI includes a total of $131.435 million of Commonwealth Government funding.
Great Ocean Road Renewal (Barwon South West) | Transport | $255m | Department of Transport and Planning | 2023-24 | qtr 4 2024-25 | Existing | $108m | $147m
Hall Road Upgrade (Skye) | Transport | tbc | Department of Transport and Planning | 2023-24 | tbc | Existing | $160m | tbc | The TEI includes $141.252 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program Review.
High Capacity Metro Trains (metropolitan various) | Transport | $2,265m | Victorian Rail Track | 2023-24 | qtr 1 2023-24 | Existing | $2,045m | $219m | The TEI has increased by $16.300 million due to a revised project scope. The TEI includes financing costs.
Homes Victoria Ground Lease Model Project 1 (metropolitan) | Health and human services | $264m | Director of Housing | 2023-24 | qtr 3 2023-24 | Existing | $237m | $27m
Homes Victoria Ground Lease Model Project 2 (metropolitan) | Health and human services | $260m | Director of Housing | 2023-24 | tbc | Existing | $13m | $247m | The estimated completion date will be disclosed following further project development and procurement processes.
Hospital Infrastructure Delivery Fund (statewide) | Health and human services | $320m | Department of Health | 2023-24 | qtr 2 2026-27 | New | $0m | $320m | This Fund is established to plan major investments in hospitals across Victoria. This initiative is part of Labor's Financial Statement 2022. - A new hospital for West Gippsland to put patients first - A new Queen Elizabeth II Hospital in Melbourne’s East - A Hospital Plan for our growing Northern suburbs - A bigger and better Monash Medical Centre - A Hospital Plan for the South-East – Dandenong Hospital - Wonthaggi hospital redevelopment
Hurstbridge Line Upgrade Stage 2 (metropolitan various) | Transport | $598m | Victorian Rail Track | 2023-24 | qtr 3 2025-26 | Completed | $544m | $55m | The TEI has decreased by $4.631 million due to budgeted amounts being recognised as operating instead of capital expenditure, in line with accounting standards.
Improving the Calder Freeway (Calder Park) | Transport | tbc | Department of Transport and Planning | 2023-24 | tbc | Existing | $4m | tbc | The TEI includes $50.000 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program Review.
Ison Road Rail Overpass (Werribee) | Transport | tbc | Department of Transport and Planning | 2023-24 | tbc | Existing | $11m | tbc | The TEI includes $103.600 million announced in the 2022 Victorian Economic and Fiscal Update. The TEI includes $56.900 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program Review.
Kananook Train Maintenance Facility Stage 2 (metropolitan) | Transport | $366m | Victorian Rail Track | 2023-24 | qtr 4 2025-26 | New | $27m | $338m | The TEI includes funding of $12.555 million announced in the 2022 Victorian Economic and Fiscal Update.
Kardinia Park Stadium Stage 5 Redevelopment (Geelong) | Culture, sport and community | $142m | Other PNFC | 2023-24 | qtr 3 2023-24 | Existing | $142m | $0m | The project's location has changed from ‘statewide’ to ‘Geelong’ to better reflect the project’s service area. The TEI has increased by $0.685 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. The project's cashflow reflects the project's funding agreement with the Kardinia Park Stadium Trust to ensure sufficient cashflow to manage the project to the estimated completion date. The estimated completion date has been revised to quarter 3 2023-24 to reflect delays caused by construction industry supply chain issues.
Keeping Victorians moving (metropolitan) | Transport | $173m | Department of Transport and Planning | 2023-24 | qtr 4 2023-24 | Existing | $155m | $18m
Kinder for every three-year-old - funding for facilities to support three-year-old kinder programs (statewide) | Education and training | $208m | Department of Education | 2023-24 | qtr 3 2027-28 | New | $0m | $208m | This initiative is published under the title 'Three-Year-Old Kinder' in Budget Paper 3 2023-24.
Land acquisition 2021-22 (various) | Education and training | $297m | Department of Education | 2023-24 | qtr 1 2024-25 | Existing | $143m | $154m | The TEI has decreased by $4.570 million due to funds being redirected to land acquisition activities announced in the 2023-24 Budget.
Land acquisition 2022-23 (various) | Education and training | $234m | Department of Education | 2023-24 | qtr 4 2024-25 | Existing | $79m | $155m | The TEI has decreased by $2.727 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Level Crossing Removal Program (metropolitan various) | Transport | $6,334m | Department of Transport and Planning | 2023-24 | qtr 4 2024-25 | Completed | $6,295m | $39m | The TEI includes $151.000 million of Commonwealth Government funding for the Main Road, St Albans project. The TEI has decreased by $8.692 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The completion of this initiative acquits the Government's 2015-16 Budget commitment to remove 50 level crossings from the transport network.
M80 Ring Road upgrade ( metropolitan north and west) | Transport | tbc | Department of Transport and Planning | 2023-24 | tbc | Existing | $413m | tbc | The TEI includes $349.130 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program Review.
Maintaining Victoria's road network (statewide) |  | $119m | Department of Transport and Planning | 2023-24 | qtr 4 2023-24 | Existing | $76m | $43m | The estimated completion date has been revised to quarter 4 2023-24 in line with a revised project schedule.
Meeting ambulance response times (statewide) | Justice and emergency services | $169m | Department of Health | 2023-24 | qtr 2 2023-24 | Existing | $146m | $23m | The estimated completion date has been revised to quarter 2 2023-24 in line with a revised project schedule.
Melbourne Arts Precinct Transformation Phase One (Melbourne) | Culture, sport and community | $1,574m | Other PNFC | 2023-24 | qtr 2 2028-29 | Existing | $79m | $1,495m | The TEI has increased by $2.614 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. The estimated completion date was previously ’tbc’ and has now been disclosed following further project development.
Melton Line Upgrade (statewide) | Transport | $641m | Victorian Rail Track | 2023-24 | qtr 4 2028-29 | New | $0m | $641m | The TEI excludes $9.000 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. This initiative is part of Labor’s Financial Statement 2022.
Men's prison system capacity (statewide) | Justice and emergency services | $758m | Department of Justice and Community Safety | 2023-24 | qtr 2 2024-25 | Existing | $520m | $238m | The TEI has decreased by $37.573 million due to a reduced project contingency. The estimated completion date has been revised to quarter 2 2024-25 in line with a revised project schedule.
Metro Tunnel (metropolitan various) | Transport | $12,642m | Victorian Rail Track | 2023-24 | qtr 2 2025-26 | Existing | $10,537m | $2,105m | The TEI has increased by $281.089 million due to COVID-19 related payments. The TEI excludes financing costs.
Metro Tunnel readiness (metropolitan) | Transport | $238m | Victorian Rail Track | 2023-24 | qtr 2 2025-26 | New | $34m | $204m
Metropolitan and regional restoration and maintenance (statewide) | Transport | $195m | Department of Transport and Planning | 2023-24 | qtr 4 2023-24 | Completed | $175m | $20m
Metropolitan Health Infrastructure Fund (metropolitan various) | Health and human services | $187m | Department of Health | 2023-24 | qtr 4 2024-25 | Existing | $95m | $92m | The estimated completion date has been revised to quarter 4 2024-25 in line with a revised project schedule.
Metropolitan Network Modernisation Program (metropolitan various) | Transport | $1,348m | Department of Transport and Planning | 2023-24 | qtr 4 2024-25 | Completed | $1,339m | $10m
Metropolitan rail infrastructure renewal program (metropolitan various) | Transport | $971m | Victorian Rail Track | 2023-24 | qtr 4 2027-28 | Existing | $202m | $769m | As a rolling program of works, the TEI and estimated completion date vary from year to year. The TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2022-23 to 2027-28.
Metropolitan Road and Intersection Upgrades (metropolitan various) | Transport | $117m | Department of Transport and Planning | 2023-24 | qtr 4 2023-24 | Existing | $20m | $97m
Metropolitan road upgrades 2022-23 (metropolitan) | Transport | $101m | Department of Transport and Planning | 2023-24 | qtr 4 2025-26 | Existing | $35m | $66m | The TEI includes $6.700 million of funding from the Wyndham City Council.
Mickleham Road Upgrade – Stage 1 (Greenvale) | Transport | tbc | Department of Transport and Planning | 2023-24 | tbc | Existing | $48m | tbc | The TEI includes $109.540 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program Review.
Modernisation of metropolitan Melbourne Public Sector Residential Aged Care Services Strategy: Stage 3 Kingston Project (Cheltenham) | Health and human services | $135m | Department of Health | 2023-24 | qtr 4 2025-26 | Existing | $3m | $132m
Monash Freeway upgrade - Stage 2 (South-East Melbourne) | Transport | $1,019m | Department of Transport and Planning | 2023-24 | qtr 1 2024-25 | Completed | $977m | $43m | The TEI includes $686.216 million of Commonwealth Government funding.
More help for Victorian mums and dads (statewide) | Health and human services | $123m | Department of Health | 2023-24 | qtr 2 2023-24 | Existing | $73m | $50m
More hospital and aged care beds for Melbourne’s East (Angliss Hospital Expansion Stage 2) (Upper Ferntree Gully) | Health and human services | $112m | Department of Health | 2023-24 | qtr 4 2026-27 | Existing | $0m | $112m
More regional trains - Regional Network Development Plan (regional various) | Transport | $224m | Victorian Rail Track | 2023-24 | qtr 4 2024-25 | Completed | $206m | $18m
More VLocity trains (regional) | Transport | $601m | Victorian Rail Track | 2023-24 | qtr 4 2027-28 | New | $0m | $601m | This initiative is part of Labor’s Financial Statement 2022.
More VLocity trains 2022-23 (regional) | Transport | $250m | Victorian Rail Track | 2023-24 | qtr 4 2026-27 | Existing | $115m | $135m
Murray Basin Rail Project (regional various) | Transport | tbc | Victorian Rail Track | 2023-24 | tbc | Existing | $642m | tbc | The TEI includes $470.400 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program review.
National Water Infrastructure Development Fund - National Partnership Agreement (regional various) | Water | $169m | Department of Environment, Energy and Climate Action | 2023-24 | qtr 4 2025-26 | Existing | $148m | $21m
New Melton Hospital (Cobblebank) | Health and human services | $900m - $1,000m | Department of Health | 2023-24 | qtr 4 2028-29 | Existing | $38m | tbc | The TEI for this initiative will be reported as commercial arrangements are finalised. The estimated completion date was previously ‘tbc’ and has now been disclosed following further project development.
New metropolitan trains (statewide) | Transport | $986m | Victorian Rail Track | 2023-24 | qtr 2 2026-27 | Existing | $132m | $854m
New School Construction 2021-22 (statewide) | Education and training | $488m | Department of Education | 2023-24 | qtr 3 2023-24 | Existing | $455m | $33m | The TEI has increased by $0.499 million due to a revised project scope, funded by a co-contribution from Tarneit Senior College. This is offset by a TEI decrease of $4.270 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
New schools construction (statewide) | Education and training | $573m | Department of Education | 2023-24 | qtr 3 2025-26 | New | $0m | $573m | To open in 2025: - Clyde North Primary School (Interim Name) - Clyde North Secondary School (Interim Name) - Pakenham North West Primary School (Interim Name) - Riverdale North Primary School (Interim Name) - Thompsons West Primary School (Interim Name) - Wollert Central Primary School (Interim Name) To open in 2026: - Fishermans Bend Primary School (Interim Name) - Lockerbie Secondary School (Interim Name) - Point Cook South P-9 (Interim Name) New schools planning and early works - to open in 2026: - Casey Central Primary School (Interim Name) - Lockerbie Specialist School (Interim Name) - Point Cook South Specialist school (Interim Name) New schools - additional stages: - Clyde Secondary College - Greenvale Secondary College
New Schools Construction 2019-20 (statewide) | Education and training | $605m | Department of Education | 2023-24 | qtr 2 2023-24 | Completed | $605m | $1m | The TEI includes $0.509 million in co-contributions from schools.
New Schools Construction 2022-23 (statewide) | Education and training | $728m | Department of Education | 2023-24 | qtr 1 2025-26 | Existing | $250m | $478m | The TEI has increased by $201.090 million, of which $180.295 million is due to market escalation in the construction sector and $20.795 million is reprioritised from the ‘New Schools and additional stages' initiative funded in the Building Works package and the Bass Coast College initiative.
New Tarneit railway station (Tarneit) | Transport | $124m | Victorian Rail Track | 2023-24 | qtr 4 2025-26 | New | $0m | $124m | The TEI includes funding of $124.000 million announced in the 2022 Victorian Economic and Fiscal Update.
New trains for Sunbury (metropolitan various) | Transport | $1,789m | Victorian Rail Track | 2023-24 | qtr 2 2024-25 | Existing | $968m | $821m | The TEI has decreased by $180.000 million due to cost savings and by $4.200 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
New VLocity carriages for the regional network (regional various) | Transport | $251m | Victorian Rail Track | 2023-24 | qtr 4 2024-25 | Completed | $235m | $15m
New Wyndham Law Court Development (Werribee) | Justice and emergency services | $271m | Court Services Victoria | 2023-24 | qtr 3 2024-25 | Existing | $63m | $208m | The estimated completion date has been revised to quarter 3 2024-25 in line with a revised project schedule.
New youth justice facility (metropolitan) | Justice and emergency services | $420m | Department of Justice and Community Safety | 2023-24 | qtr 3 2023-24 | Completed | $407m | $13m
Next Generation Trams (metropolitan various) | Transport | $1,407m | Victorian Rail Track | 2023-24 | qtr 4 2028-29 | Existing | $224m | $1,183m | The TEI has decreased by $61.050 million due to the transfer of scope to be delivered by the ‘Tram Infrastructure upgrades (metropolitan various)' initiative.
North East Link – Primary Package (Tunnels) and State Toll Co (Greensborough) | Transport | $14,034m | State Tolling Corporation | 2023-24 | qtr 2 2028-29 | Existing | $2,419m | $11,615m | The TEI includes the $11.100 billion contract with the Spark consortium to deliver the Primary Package and other costs associated with the operations of the State Tolling Corporation. The project includes a share of $1.750 billion of Commonwealth Government funding. The TEI excludes financing costs associated with the Primary Package. The State Tolling Corporation is responsible for providing funding contributions to the ‘North East Link – Primary Package (Tunnels)' initiative. This project may be subject to the Commonwealth Infrastructure Investment Pipeline review.
North East Link (State and Freeway Packages) (Greensborough) | Transport | tbc | Department of Transport and Planning | 2023-24 | tbc | Existing | tbc | tbc | North East Link is supported by $15.400 billion of asset funding and is being delivered through a series of works packages. The TEI and estimated expenditure will be reported as procurement processes and commercial arrangements are finalised. The project includes a share of $1.750 billion of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program Review.
Northern Hospital inpatient expansion - Stage 2 (Epping) | Health and human services | $163m | Department of Health | 2023-24 | qtr 2 2024-25 | Completed | $162m | $1m
Pakenham Roads upgrade (Pakenham) | Transport | tbc | Department of Transport and Planning | 2023-24 | tbc | New | $34m | tbc | The TEI is funded by $391.495 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program Review.
Prahran campus site purchase and master planning (Prahran) | Education and training | $142m | Department of Jobs, Skills, Industry and Regions | 2023-24 | qtr 2 2022-23 | Completed | $142m | $0m | The TEI includes funding of $142.050 million announced in the 2022 Victorian Economic and Fiscal Update. This initiative moved from the former Department of Education and Training to the Department of Jobs, Skills, Industry and Regions due to machinery of government changes.
Princes Highway East Duplication Stage 3 (regional various) | Transport | tbc | Department of Transport and Planning | 2023-24 | tbc | Existing | $207m | tbc | The TEI includes $202.600 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program Review.
Public housing renewal program (statewide) | Health and human services | $185m | Director of Housing | 2023-24 | qtr 2 2024-25 | Existing | $102m | $83m
Public Transport Ticketing Asset Renewal (statewide) | Transport | $544m | Victorian Rail Track | 2023-24 | qtr 4 2026-27 | Existing | $4m | $540m | The TEI, estimated expenditure and estimated completion date are now disclosed following the completion of the procurement process.
Purchase of a site on Poplar Road, Parkville (Parkville) | Transport | $212m | Department of Transport and Planning | 2023-24 | qtr 3 2022-23 | Completed | $212m | $0m | The TEI is composed of funding announced in the 2022 Victorian Economic and Fiscal Update. This initiative moved from the former Department of Jobs, Precincts and Regions to the Department of Transport and Planning due to machinery of government changes.
Ready for school: Kinder for every three-year-old 2019-20 (statewide) | Education and training | $280m | Department of Education | 2023-24 | qtr 4 2023-24 | Existing | $116m | $165m | The TEI has increased by $1.142 million due to a revised project scope, funded by a $0.576 million co-contribution from the schools and a $0.566 million co-contribution from local councils. This is offset by a TEI decrease of $2.932 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Redevelopment of Royal Melbourne Hospital and Royal Women's Hospital (Arden/Parkville) | Health and human services | $2,338m | Department of Health | 2023-24 | qtr 4 2031-32 | New | $3m | $2,335m | This initiative was announced in the 2022 Victorian Economic and Fiscal Update.
Regional Health Infrastructure Fund (regional various) | Health and human services | $250m | Department of Health | 2023-24 | qtr 1 2024-25 | Existing | $235m | $15m | The estimated completion date has been revised to quarter 1 2024-25 in line with a revised project schedule.
Regional Health Infrastructure Fund 2019-20 (regional various) | Health and human services | $100m | Department of Health | 2023-24 | qtr 4 2023-24 | Existing | $55m | $45m
Regional Health Infrastructure Fund 2020-21 (regional various) | Health and human services | $120m | Department of Health | 2023-24 | qtr 4 2024-25 | Existing | $58m | $62m | The estimated completion date has been revised to quarter 4 2024-25 in line with a revised project schedule.
Regional Health Infrastructure Fund 2022-23 (regional various) | Health and human services | $300m | Department of Health | 2023-24 | qtr 4 2025-26 | Existing | $17m | $283m
Regional Rail Revival - Bendigo/Echuca Line Upgrade (regional various) | Transport | tbc | Victorian Rail Track | 2023-24 | tbc | Existing | $126m | tbc | The TEI includes $159.108 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program review.
Regional Rail Revival - Gippsland Line Upgrade Stage 1 (regional various) | Transport | tbc | Victorian Rail Track | 2023-24 | tbc | Existing | $467m | tbc | The TEI includes $449.400 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program review.
Regional Rail Revival - Shepparton Corridor Upgrade - Stage 2 (Shepparton) | Transport | $313m | Victorian Rail Track | 2023-24 | qtr 4 2024-25 | Completed | $283m | $30m | The TEI has decreased by $1.052 million due to budgeted amounts being recognised as operating instead of capital expenditure, in line with accounting standards. VLocity trains were delivered in quarter 2 2022-23, with final commissioning to introduce the remaining Stage 2 infrastructure into service in quarter 4 2022-23.
Regional Rail Revival - Shepparton Line Upgrade - Stage 3 (Shepparton) | Transport | tbc | Victorian Rail Track | 2023-24 | tbc | Existing | $93m | tbc | The TEI includes $320.000 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program review.
Regional Rail Revival - Warrnambool and Geelong Line Upgrade (regional various) | Transport | $283m | Victorian Rail Track | 2023-24 | qtr 4 2024-25 | Completed | $270m | $13m | The TEI has increased by $32.900 million reprioritised from Waurn Ponds Track Duplication - Stage 2 (regional various). The estimated completion date has been revised to quarter 4 2022-23 in line with a revised project schedule. The TEI includes $226.345 million of Commonwealth Government funding.
Regional Rail Revival - Warrnambool Line Upgrade - Stage 2 (regional various) | Transport | tbc | Victorian Rail Track | 2023-24 | tbc | Existing | $53m | tbc | The TEI includes $208.000 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program review.
Regional Rail Revival - Waurn Ponds Track Duplication - Stage 2 (regional various) | Transport | tbc | Victorian Rail Track | 2023-24 | tbc | Existing | $204m | tbc | The TEI includes $754.000 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program review.
Regional rail sustainability 2021-22 (statewide) | Transport | $465m | Victorian Rail Track | 2023-24 | qtr 4 2024-25 | Existing | $213m | $252m
Regional rail sustainability 2022-23 (statewide) | Transport | $205m | Victorian Rail Track | 2023-24 | qtr 4 2025-26 | Existing | $91m | $113m
Relocatable Buildings Program – providing relocatable buildings to meet growing demand (statewide) | Education and training | $147m | Department of Education | 2023-24 | qtr 4 2023-24 | New | $0m | $147m
Road blitz to get families home sooner and safer (statewide) | Transport | $674m | Department of Transport and Planning | 2023-24 | qtr 4 2028-29 | New | $4m | $670m | The TEI includes $170.000 million of Commonwealth Government funding. This initiative is part of Labor’s Financial Statement 2022.
Road maintenance and renewal (statewide) | Transport | $1,250m | Department of Transport and Planning | 2023-24 | qtr 4 2032-33 | New | $0m | $1,250m
Road maintenance blitz (statewide) | Transport | $109m | Department of Transport and Planning | 2023-24 | qtr 2 2023-24 | Completed | $78m | $30m
Road Safety Strategy (statewide) | Transport | tbc | Department of Transport and Planning | 2023-24 | tbc | Existing | $230m | tbc | The TEI includes $183.300 million of Commonwealth Government funding and funding from the Transport Accident Commission. This project may be subject to the Commonwealth Infrastructure Investment Program Review.
Road Safety Strategy 2013-2022 (statewide) | Transport | $628m | Department of Transport and Planning | 2023-24 | qtr 4 2025-26 | Completed | $628m | $0m | This initiative is funded by the Transport Accident Commission.
Rolling stock maintenance and disposal programs (statewide) | Transport | $123m | Victorian Rail Track | 2023-24 | qtr 1 2025-26 | Existing | $40m | $83m | The TEI has decreased by $2.300 million which has been reprioritised to ‘High Capacity Metro Trains (metropolitan various)'.
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | Health and human services | $318m | Department of Health | 2023-24 | qtr 4 2023-24 | Completed | $315m | $3m
Rural and Regional PSRACS Revitalisation Strategy Stage 1 2022-23 (regional various) | Health and human services | $143m | Department of Health | 2023-24 | qtr 4 2027-28 | Existing | $1m | $142m
School upgrades - growth for 2022 (metropolitan various) | Education and training | $131m | Department of Education | 2023-24 | qtr 2 2023-24 | Existing | $121m | $10m | The TEI has increased by $0.647 million, of which $0.096 million is due to a revised project scope funded by co-contributions from schools, and $0.551 million funded from a third party for necessary re-tendering. The TEI includes $0.246 million in total co-contributions from the schools. The estimated completion date has been revised to quarter 2 2023-24 in line with a revised project schedule.
South Dynon Train Maintenance Facility Stage 1 (statewide) | Transport | $122m | Victorian Rail Track | 2023-24 | qtr 1 2023-24 | Existing | $66m | $56m | The project name has changed from 'South Dynon train maintenance facility (statewide)' when it was published in the 2022-23 Budget. The TEI was previously 'tbc' and has now been disclosed following the completion of the procurement process.
South Dynon Train Maintenance Facility Stage 2 (statewide) | Transport | $297m | Victorian Rail Track | 2023-24 | qtr 4 2025-26 | New | $10m | $287m | The TEI includes funding of $10.200 million announced in the 2022 Victorian Economic and Fiscal Update.
Special school upgrades 2022-23 (statewide) | Education and training | $326m | Department of Education | 2023-24 | qtr 2 2025-26 | Existing | $11m | $315m
State Basketball Centre redevelopment (Knox) | Culture, sport and community | $128m | Other PNFC | 2023-24 | qtr 1 2024-25 | Existing | $123m | $5m | The estimated completion date has been revised to quarter 1 2024-25 in line with a staged project schedule. The TEI includes a $27.000 million contribution from the Knox City Council.
Suburban Parks Program (Creating a Ring of New Parkland) (metropolitan) | Environment | $192m | Department of Environment, Energy and Climate Action | 2023-24 | qtr 4 2023-24 | Existing | $180m | $12m
Suburban Rail Loop - Airport (metropolitan various) | Transport | tbc | Victorian Rail Track | 2023-24 | tbc | Existing | $630m | tbc | The State and Commonwealth governments have committed $5.000 billion each to the project. This project may be subject to the Commonwealth Infrastructure Investment Program review.
Suburban Rail Loop East - Development, Initial and Early Works (metropolitan various) | Transport | $2,372m | Victorian Rail Track | 2023-24 | qtr 4 2024-25 | Existing | $672m | $1,699m | The project name has changed from ‘Suburban Rail Loop - Initial and Early Works (metro various)' when it was published in the 2022-23 Budget. The TEI has increased by $11.913 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards.
Suburban Rail Loop East - Main Works (metro various) | Transport | tbc | Victorian Rail Track | 2023-24 | tbc | Existing | tbc | tbc | The Suburban Rail Loop East is expected to cost between $30.000–$34.500 billion and is targeting delivery by 2035. The TEI, estimated expenditure and estimated completion date will be disclosed following the procurement of the main works packages. The TEI includes $2.200 billion of Commonwealth Government funding.
Suburban Roads Upgrade – Northern Roads Upgrade and South Eastern Roads Upgrade (statewide) | Transport | tbc | Department of Transport and Planning | 2023-24 | tbc | Existing | $1,661m | tbc | The TEI includes $1,140.000 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program Review.
Sunshine Station Masterplan (Sunshine) |  | tbc | Victorian Rail Track | 2023-24 | tbc | Existing | tbc | tbc | The TEI, estimated expenditure and estimated completion date will be disclosed following the completion of the procurement process.
TAC Victoria's Road Safety Strategy, Towards Zero 2016-2020 (TZ2) (regional various) | Transport | $237m | Department of Transport and Planning | 2023-24 | qtr 4 2024-25 | Completed | $196m | $41m
Targeted Road Safety Works (statewide) | Transport | $106m | Department of Transport and Planning | 2023-24 | qtr 2 2024-25 | Existing | $53m | $52m | The estimated completion date has been revised to quarter 2 2024-25 due to delays in the supply of materials.
Technology and resources to support Victoria's fines system (statewide) | Justice and emergency services | $142m | Department of Justice and Community Safety | 2023-24 | qtr 4 2024-25 | Existing | $74m | $68m
Ten new community hospitals to give patients the best care (statewide) | Health and human services | $675m | Department of Health | 2023-24 | qtr 4 2024-25 | Existing | $146m | $529m
Train radio system upgrade (metropolitan) | Transport | $173m | Victorian Rail Track | 2023-24 | qtr 4 2027-28 | Existing | $26m | $147m
Tram infrastructure upgrades (metropolitan various) | Transport | $429m | Victorian Rail Track | 2023-24 | qtr 4 2025-26 | Existing | $37m | $391m | The TEI has increased by $61.050 million due to the transfer of scope from the ‘Next Generation Trams (metropolitan various)' initiative.
Twenty-five more level crossing removals by 2030 (Level Crossing Removal) (metropolitan various) | Transport | $6,522m | Department of Transport and Planning | 2023-24 | qtr 4 2029-30 | New | $84m | $6,438m | The TEI includes funding of $6,522.100 million announced in the 2022 Victorian Economic and Fiscal Update.
Victorian Heart Hospital (Clayton) | Health and human services | $577m | Department of Health | 2023-24 | qtr 2 2024-25 | Completed | $573m | $4m
Warrnambool Base Hospital redevelopment (incl Warrnambool Logistics Hub) (Warrnambool) | Health and human services | $384m | Department of Health | 2023-24 | qtr 4 2026-27 | Existing | $34m | $350m | The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule.
West Gate Tunnel (metropolitan various) | Transport | $10,154m | Department of Transport and Planning | 2023-24 | qtr 2 2025-26 | Existing | $7,990m | $2,164m | The TEI has decreased by $58.212 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards.
Western Highway duplication - Ballarat to Stawell (regional various) | Transport | tbc | Department of Transport and Planning | 2023-24 | tbc | Existing | $589m | tbc | The TEI includes $499.380 million of Commonwealth Government funding. This project may be subject to the Commonwealth Infrastructure Investment Program review.
Western Plains Correctional Centre (Lara) | Justice and emergency services | $1,069m | Department of Justice and Community Safety | 2023-24 | qtr 4 2023-24 | Completed | $1,026m | $43m | The TEI has decreased by $49.402 million.
Western Port Highway (Skye) | Transport | $114m | Department of Transport and Planning | 2023-24 | qtr 2 2024-25 | Completed | $106m | $7m | The TEI includes $57.500 million of Commonwealth Government funding.
Women’s prison system capacity (statewide) | Justice and emergency services | $153m | Department of Justice and Community Safety | 2023-24 | qtr 3 2023-24 | Completed | $126m | $26m | The TEI has decreased by $36.300 million.
Wonthaggi Hospital emergency department expansion (Wonthaggi) | Health and human services | $115m | Department of Health | 2023-24 | qtr 4 2023-24 | Completed | $114m | $1m