## State Capital Program
State Capital Program
Overview
The State Capital Program (Budget Paper No. 4) provides an overview of the capital investments the Government will deliver in the coming financial year.
Budget Paper No. 4 includes:
· individual state capital programs and projects currently under way;
· programs of work to commence in 2018-19; and
· programs expected to be completed in 2017-18.
The information is current as at 27 April 2018.
Below are definitions of key terms to further assist understanding of the State Capital Program and the attached dataset.
Definition of key terms
Government Infrastructure Investment – represents the sum of purchases of non-financial assets, net cash flows from investments in financial assets for policy purposes, and sales of non-financial assets (net Government infrastructure investment which is sourced from the general government cash flow statement). In addition, Investment in Government Infrastructure also includes public private partnerships infrastructure investment.
PPP Infrastructure Investment – represents the annual capital expenditure cash flows modelled in the Financial Model forming part of a public private partnership (PPP) contract, exclusive of capitalised interest and any Victorian Government capital contribution. This amount is separately calculated and is not sourced from a particular line of a financial statement. The value of this line varies from year to year depending on the number, size and timing of projects being delivered as PPPs. The list of PPP projects currently underway is contained in Budget Paper No. 4, table 3.
Published: May 2019

## Chapter 2
Asset Initiatives
Department of Education and Training
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Early childhood development
Child Link – funding for Child Link Program (statewide) | 18530 | 0 | 18530 | 0 | qtr 4 2019-20
Ready for school: kinder for every three-year-old – funding for facilities to support three-year-old kinder programs (statewide) | 282965 | 0 | 54479 | 228486 | qtr 4 2022-23
School education
Accessible Buildings Program (statewide) | 10000 | 0 | 10000 | 0 | qtr 4 2019-20
Albert Park College and the Victorian College of the Arts Secondary School – modernisation – funding to plan for the committed upgrade of school facilities (Albert Park) | 1250 | 0 | 875 | 375 | qtr 3 2020-21
Alexandra Primary School – Asbestos Safety Program – modular buildings program (Alexandra) | 3147 | 0 | 1416 | 1731 | qtr 2 2020-21
Altona North Primary School – modernisation – upgrade existing school facilities (Altona North) | 3830 | 0 | 268 | 3562 | qtr 4 2021-22
Altona P-9 College – modernisation – upgrade existing school facilities (Altona) | 4746 | 0 | 332 | 4414 | qtr 4 2021-22
Ararat Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Ararat) | 55 | 0 | 55 | 0 | qtr 3 2020-21
Auburn High School – modernisation – upgrade existing school facilities (Hawthorn East) | 5500 | 0 | 385 | 5115 | qtr 4 2021-22
Avoca Primary School – modernisation – upgrade existing school facilities (Avoca) | 300 | 0 | 21 | 279 | qtr 1 2021-22
Baimbridge College – modernisation – funding to plan for the committed upgrade of existing school facilities (Hamilton) | 840 | 0 | 588 | 252 | qtr 3 2020-21
Bairnsdale Secondary College – modernisation – funding to plan for the committed upgrade of existing school facilities (Bairnsdale) | 140 | 0 | 98 | 42 | qtr 3 2020-21
Ballarat High School – modernisation – funding to plan for the committed upgrade of existing school facilities (Ballarat) | 800 | 0 | 560 | 240 | qtr 3 2020-21
Baxter Primary School – Asbestos Safety Program – modular buildings program (Baxter) | 2581 | 0 | 1161 | 1420 | qtr 2 2020-21
Bayswater Primary School – Asbestos Safety Program – modular buildings program (Bayswater) | 1390 | 0 | 1390 | 0 | qtr 4 2019-20
Beechworth Secondary College – modernisation – upgrade existing school facilities (Beechworth) | 9384 | 0 | 1971 | 7413 | qtr 1 2022-23
Bellarine Secondary College – modernisation – funding to plan for the committed upgrade of existing school facilities (Drysdale) | 893 | 0 | 625 | 268 | qtr 3 2020-21
Bellbrae Primary School – modernisation – upgrade existing school facilities (Bellbrae) | 9100 | 0 | 910 | 8190 | qtr 4 2021-22
Benalla P-12 College – modernisation – upgrade existing school facilities (Benalla) | 12064 | 0 | 844 | 11220 | qtr 1 2022-23
Boisdale Consolidated School – Asbestos Safety Program – modular buildings program (Boisdale) | 1360 | 0 | 1008 | 352 | qtr 2 2020-21
Boronia Heights Primary School – modernisation – upgrade existing school facilities (Boronia) | 1321 | 0 | 92 | 1229 | qtr 3 2021-22
Brandon Park Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Wheelers Hill) | 680 | 0 | 476 | 204 | qtr 3 2020-21
Brentwood Secondary College – modernisation – upgrade existing school facilities (Glen Waverley) | 4600 | 0 | 322 | 4278 | qtr 4 2021-22
Brunswick North West Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Brunswick West) | 623 | 0 | 436 | 187 | qtr 3 2020-21
Cann River P-12 College – Asbestos Safety Program – modular buildings program (Cann River) | 2057 | 0 | 2057 | 0 | qtr 4 2019-20
Churchill Primary School – modernisation – upgrade existing school facilities through the modular buildings program (Churchill) | 2634 | 0 | 1185 | 1449 | qtr 2 2020-21
Clarinda Primary School – Asbestos Safety Program – modular buildings program (Clarinda) | 3038 | 0 | 1367 | 1671 | qtr 2 2020-21
Clifton Hill Primary School – modernisation – funding to plan for the committed upgrade of school facilities (Clifton Hill) | 1276 | 0 | 893 | 383 | qtr 3 2020-21
Clifton Springs Primary School – planning for schools 2019-20 (Clifton Springs) | 500 | 0 | 250 | 250 | qtr 3 2020-21
Clyde Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Clyde) | 2280 | 0 | 1596 | 684 | qtr 3 2020-21
Cobram Secondary College – Asbestos Safety Program – modular buildings program (Cobram) | 3392 | 0 | 1527 | 1865 | qtr 2 2020-21
Copperfield College – Stage 2 – modernisation – upgrade existing school facilities (Delahey) | 6500 | 0 | 455 | 6045 | qtr 3 2021-22
Cowes Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Cowes) | 550 | 0 | 385 | 165 | qtr 3 2020-21
Cranbourne Secondary College – modernisation – funding to plan for the committed upgrade of existing school facilities (Cranbourne) | 662 | 0 | 463 | 199 | qtr 3 2020-21
Cranbourne South Primary School – modernisation – upgrade existing school facilities (Cranbourne South) | 5900 | 0 | 413 | 5487 | qtr 4 2021-22
Cranbourne West Primary School – modernisation – upgrade existing school facilities (Cranbourne) | 700 | 0 | 49 | 651 | qtr 3 2021-22
Dandenong High School – modernisation – upgrade existing school facilities (Dandenong) | 8460 | 0 | 592 | 7868 | qtr 1 2022-23
Delacombe Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Delacombe) | 650 | 0 | 455 | 195 | qtr 3 2020-21
Derinya Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Frankston South) | 480 | 0 | 336 | 144 | qtr 3 2020-21
Diamond Creek East Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Diamond Creek) | 360 | 0 | 252 | 108 | qtr 3 2020-21
Diamond Valley College – modernisation – upgrade existing school facilities (Diamond Creek) | 3100 | 0 | 310 | 2790 | qtr 3 2021-22
Dromana Secondary College – Asbestos Safety Program – modular buildings program (Dromana) | 2362 | 0 | 2362 | 0 | qtr 4 2019-20
Dunkeld Consolidated School – Asbestos Safety Program – modular buildings program (Dunkeld) | 1092 | 0 | 491 | 601 | qtr 2 2020-21
East Loddon P-12 College – modernisation – funding to plan for the committed upgrade of existing school facilities (Dingee) | 450 | 0 | 315 | 135 | qtr 3 2020-21
Echuca Regeneration Project – Stage 2 – education plan – funding to deliver previously planned works in the education plan (Echuca) | 16720 | 650 | 11123 | 4947 | qtr 1 2022-23
Edgars Creek Secondary College – Stage 2 – funding for construction works (Wollert) | 22800 | 0 | 2280 | 20520 | qtr 2 2022-23
Edithvale Primary School – Asbestos Safety Program – modular buildings program (Edithvale) | 672 | 0 | 672 | 0 | qtr 4 2019-20
Eltham North Primary School – modernisation – upgrade existing school facilities (Eltham North) | 450 | 0 | 32 | 418 | qtr 1 2021-22
Epsom Primary School – modernisation – upgrade existing school facilities (Epsom) | 500 | 0 | 35 | 465 | qtr 4 2020-21
Essential facilities for mental health in schools (statewide) | 3000 | 0 | 3000 | 0 | qtr 4 2019-20
Essential maintenance and compliance (statewide) | 15000 | 0 | 12000 | 3000 | qtr 4 2020-21
Euroa Secondary College – Asbestos Safety Program – modular buildings program (Euroa) | 3178 | 0 | 1430 | 1748 | qtr 2 2020-21
Exford Primary School – modernisation – upgrade existing school facilities (Exford) | 6246 | 0 | 1936 | 4310 | qtr 4 2021-22
Fairfield Primary School – modernisation – upgrade existing school facilities (Fairfield) | 7000 | 0 | 5250 | 1750 | qtr 3 2020-21
Fitzroy North Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Fitzroy North) | 900 | 0 | 630 | 270 | qtr 3 2020-21
Footscray Learning Precinct – funding to deliver previously planned works in the education plan (Seddon) | 20246 | 0 | 5792 | 14454 | qtr 3 2021-22
Frankston North Education Precinct – Stage 2 – education plan – funding to deliver previously planned works in the education plan (Frankston) | 11268 | 0 | 4366 | 6902 | qtr 3 2021-22
Geelong High School – modernisation – upgrade existing school facilities (East Geelong) | 2200 | 0 | 902 | 1298 | qtr 3 2021-22
George Street Primary School – Hamilton – Asbestos Safety Program – modular buildings program (Hamilton) | 2273 | 0 | 1023 | 1250 | qtr 2 2020-21
Gladstone Park Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Gladstone Park) | 252 | 0 | 177 | 75 | qtr 3 2020-21
Gladstone Views Primary School – modernisation – upgrade existing school facilities (Gladstone Park) | 3126 | 0 | 219 | 2907 | qtr 4 2021-22
Glen Huntly Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Glen Huntly) | 500 | 0 | 350 | 150 | qtr 3 2020-21
Glenroy Secondary College – modernisation – upgrade existing school facilities through the modular buildings program (Glenroy) | 9215 | 0 | 6650 | 2565 | qtr 2 2020-21
Greensborough Secondary College – modernisation – funding to plan for the committed upgrade of existing school facilities (Greensborough) | 995 | 0 | 696 | 299 | qtr 3 2020-21
Hallam Primary School – Asbestos Safety Program – modular buildings program (Hallam) | 3586 | 0 | 1614 | 1972 | qtr 2 2020-21
Hampton Park Secondary College – modernisation – upgrade existing school facilities (Hampton Park) | 3900 | 0 | 390 | 3510 | qtr 3 2021-22
Heyfield Primary School – Asbestos Safety Program – modular buildings program (Heyfield) | 3025 | 0 | 1361 | 1664 | qtr 2 2020-21
Horsham Primary School – Asbestos Safety Program – modular buildings program (Horsham) | 2128 | 0 | 957 | 1171 | qtr 2 2020-21
Huntingdale Primary School – Asbestos Safety Program – modular buildings program (Oakleigh South) | 5033 | 0 | 5033 | 0 | qtr 4 2019-20
Inclusive Schools Fund – funding for additional rounds of the Inclusive Schools Fund (statewide) | 10000 | 0 | 5000 | 5000 | qtr 4 2020-21
Inglewood Primary School – modernisation – upgrade existing school facilities (Inglewood) | 150 | 0 | 11 | 139 | qtr 1 2021-22
Jacana School for Autism – Asbestos Safety Program – modular buildings program (Jacana) | 966 | 0 | 966 | 0 | qtr 4 2019-20
Kensington Primary School – modernisation – upgrade existing school facilities (Kensington) | 200 | 0 | 14 | 186 | qtr 1 2021-22
Kew High School – modernisation – funding to plan for the committed upgrade of existing school facilities (Kew East) | 1084 | 0 | 759 | 325 | qtr 3 2020-21
Koo Wee Rup Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Koo Wee Rup) | 250 | 0 | 175 | 75 | qtr 3 2020-21
Koonung Secondary College – modernisation – upgrade existing school facilities (Mont Albert North) | 6050 | 0 | 424 | 5626 | qtr 4 2021-22
Lalor East Primary School – Asbestos Safety Program – modular buildings program (Thomastown) | 8900 | 0 | 6029 | 2871 | qtr 2 2020-21
Land Acquisition Fund – acquire future school sites (statewide) | 45958 | 0 | 2100 | 43858 | qtr 4 2020-21
Lang Lang Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Lang Lang) | 154 | 0 | 108 | 46 | qtr 3 2020-21
Macleod College – modernisation – funding to plan for the committed upgrade of existing school facilities (Macleod) | 493 | 0 | 345 | 148 | qtr 3 2020-21
Marong Primary School – modernisation – upgrade existing school facilities (Marong) | 6403 | 0 | 448 | 5955 | qtr 3 2021-22
Matthew Flinders Girls Secondary College – modernisation – upgrade existing school facilities (Geelong) | 800 | 0 | 560 | 240 | qtr 4 2020-21
Miners Rest Primary School – modernisation – funding to prepare for the next stage of committed works (Miners Rest) | 1710 | 0 | 1197 | 513 | qtr 3 2020-21
Monbulk College – modernisation – funding to plan for the committed upgrade of existing school facilities (Monbulk) | 935 | 0 | 655 | 280 | qtr 3 2020-21
Monbulk Primary School – modernisation – upgrade existing school facilities (Monbulk) | 7100 | 0 | 497 | 6603 | qtr 4 2021-22
Montmorency Secondary College – modernisation – funding to plan for the committed upgrade of existing school facilities (Montmorency) | 1610 | 0 | 1127 | 483 | qtr 3 2020-21
Mordialloc College – modernisation – funding to plan for the committed upgrade of existing school facilities (Mordialloc) | 856 | 0 | 599 | 257 | qtr 3 2020-21
Mortlake P-12 College – Asbestos Safety Program – modular buildings program (Mortlake) | 1176 | 0 | 529 | 647 | qtr 2 2020-21
Mount Clear College – modernisation – upgrade existing school facilities (Mount Clear) | 5500 | 0 | 550 | 4950 | qtr 3 2021-22
Mount Rowan Secondary College – modernisation – upgrade existing school facilities (Ballarat) | 3596 | 0 | 360 | 3236 | qtr 2 2021-22
Mullum Primary School – Asbestos Safety Program – modular buildings program (Ringwood) | 5174 | 0 | 3774 | 1400 | qtr 2 2020-21
Murrumbeena Primary School – modernisation – upgrade existing school facilities (Murrumbeena) | 1100 | 0 | 77 | 1023 | qtr 3 2021-22
Narre Warren North Primary School – modernisation – upgrade existing school facilities through the modular buildings program (Narre Warren North) | 4513 | 0 | 2031 | 2482 | qtr 2 2020-21
Nathalia Secondary College – Asbestos Safety Program – modular buildings program (Nathalia) | 1862 | 0 | 1862 | 0 | qtr 4 2019-20
Neerim District Secondary College – Asbestos Safety Program – modular buildings program (Neerim South) | 4090 | 0 | 1840 | 2250 | qtr 2 2020-21
New Gisborne Primary School – modernisation – upgrade existing school facilities (New Gisborne) | 3100 | 0 | 217 | 2883 | qtr 3 2021-22
New school construction (statewide) To open in 2020 (additional works): – Beveridge Primary School (new campus of the existing Beveridge Primary School) – Botanic Ridge Primary School – Casey Fields (Five Ways) Primary School – Clyde North East Primary School – Craigieburn South Secondary School – Davis Creek Primary School – Lucas Primary School – Wyndham South (Riverwalk) Primary School To open in 2021: – Armstrong Creek Secondary College – Cranbourne West Secondary and Special School – Docklands Primary School – Edgars Creek Primary School – Eynesbury Station Primary School – Greenvale North West Primary School – Merrifield West Primary School – Pakenham Henry Road Secondary School – Rockbank North Primary School – Thoroughbred Primary School – Timbertop (Officer North West) Primary School – Truganina South East Primary School – Wollahra Primary School To open in 2022: – Bass Coast Junior Secondary School – Fishermans Bend Secondary School – Fitzroy Gasworks new campus – McKinnon Secondary College – new campus | 624831 | 2000 | 351976.9 | 270854.1 | qtr 3 2021-22
New School Planning Fund – planning for new schools (statewide) | 2000 | 0 | 2000 | 0 | qtr 4 2019-20
Newcomb Park Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Newcomb) | 320 | 0 | 224 | 96 | qtr 3 2020-21
Newcomb Secondary College – modernisation – funding to plan for the committed upgrade of existing school facilities (Newcomb) | 600 | 0 | 420 | 180 | qtr 3 2020-21
Noble Park English Language School – Asbestos Safety Program – modular buildings program (Noble Park) | 3392 | 0 | 1527 | 1865 | qtr 2 2020-21
Oberon Primary School – Stage 2 – modernisation – upgrade existing school facilities (Belmont) | 950 | 0 | 390 | 560 | qtr 2 2021-22
Oberon South Primary School – Asbestos Safety Program – modular buildings program (Belmont) | 3390 | 0 | 3390 | 0 | qtr 4 2019-20
Orbost Secondary College – Asbestos Safety Program – modular buildings program (Orbost) | 3480 | 0 | 1566 | 1914 | qtr 2 2020-21
Osborne Primary School – Asbestos Safety Program – modular buildings program (Mount Martha) | 7984 | 0 | 6211 | 1773 | qtr 2 2020-21
Parkdale Secondary College – modernisation – funding to plan for the committed upgrade of existing school facilities (Mordialloc) | 967 | 0 | 677 | 290 | qtr 3 2020-21
Parkhill Primary School – modernisation – upgrade existing school facilities (Ashwood) | 4000 | 0 | 280 | 3720 | qtr 4 2021-22
Pascoe Vale South Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Pascoe Vale South) | 100 | 0 | 70 | 30 | qtr 3 2020-21
Patterson River Secondary College – modernisation – funding to plan for the committed upgrade of existing school facilities (Seaford) | 800 | 0 | 560 | 240 | qtr 3 2020-21
Phoenix P-12 Community College – modernisation – funding to plan for the committed upgrade of existing school facilities (Sebastopol) | 1177 | 0 | 824 | 353 | qtr 3 2020-21
Planned Removal Program – funding to continue the removal of asbestos containing material in government schools (statewide) | 72826 | 0 | 49826 | 23000 | qtr 4 2020-21
Port Melbourne Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Port Melbourne) | 784 | 0 | 549 | 235 | qtr 3 2020-21
Preston Primary School – modernisation – upgrade existing school facilities (Preston) | 400 | 0 | 280 | 120 | qtr 3 2020-21
Red Hill Consolidated School – modernisation – upgrade existing school facilities (Red Hill) | 3200 | 0 | 224 | 2976 | qtr 4 2021-22
Relocatable Buildings Program – providing relocatable buildings to meet growing demand (statewide) | 101273 | 0 | 101273 | 0 | qtr 4 2019-20
Research Primary School – modernisation – funding to deliver previously planned works (Research) | 5700 | 0 | 570 | 5130 | qtr 3 2021-22
Reservoir High School – Asbestos Safety Program – modular buildings program (Reservoir) | 3129 | 0 | 1408 | 1721 | qtr 2 2020-21
Reservoir Primary School – Asbestos Safety Program – modular buildings program (Reservoir) | 713 | 0 | 713 | 0 | qtr 4 2019-20
Reservoir Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Reservoir) | 379 | 0 | 265 | 114 | qtr 3 2020-21
Ringwood North Primary School – Asbestos Safety Program – modular buildings program (Ringwood North) | 3013 | 0 | 3013 | 0 | qtr 4 2019-20
Rollins Primary School – Asbestos Safety Program – modular buildings program (Bell Post Hill) | 3460 | 0 | 3460 | 0 | qtr 4 2019-20
Rosehill Secondary College – modernisation – upgrade existing school facilities through the modular buildings program (Niddrie) | 4513 | 0 | 4513 | 0 | qtr 4 2019-20
Sale Primary School – Asbestos Safety Program – modular buildings program (Sale) | 1274 | 0 | 573 | 701 | qtr 2 2020-21
Sandringham College – planning for schools 2019-20 (Sandringham) | 500 | 0 | 250 | 250 | qtr 3 2020-21
School Pride and Sports Fund – funding for additional rounds of the School Pride and Sports Fund (statewide) | 10000 | 0 | 5000 | 5000 | qtr 4 2020-21
Skye Primary School – modernisation – upgrade existing school facilities (Skye) | 7800 | 0 | 546 | 7254 | qtr 1 2022-23
South Yarra Primary School – modernisation – upgrade existing school facilities (South Yarra) | 6000 | 0 | 6000 | 0 | qtr 3 2019-20
Southern Autistic School – modernisation – funding to prepare for the next stage of committed works (East Bentleigh) | 740 | 0 | 0 | 740 | qtr 4 2020-21
St Albans East Primary School – Asbestos Safety Program – modular buildings program (St Albans) | 8169 | 0 | 5805 | 2364 | qtr 2 2020-21
St Helena Secondary College – modernisation – funding to plan for the committed upgrade of existing school facilities (Eltham North) | 1347 | 0 | 943 | 404 | qtr 3 2020-21
St Kilda Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (St Kilda) | 503 | 0 | 352 | 151 | qtr 3 2020-21
Staughton College – modernisation – funding to plan for the committed upgrade of existing school facilities (Melton South) | 650 | 0 | 455 | 195 | qtr 3 2020-21
Strathmore Secondary College – Stage 2 – modernisation – upgrade existing school facilities (Strathmore) | 7337 | 0 | 734 | 6603 | qtr 3 2021-22
Sunshine College – modernisation – upgrade existing school facilities (Sunshine) | 12751 | 0 | 12751 | 0 | qtr 4 2019-20
Terang College – Asbestos Safety Program – modular buildings program (Terang) | 1771 | 0 | 1771 | 0 | qtr 4 2019-20
The Grange P-12 College – modernisation – funding to deliver previously planned works (Hoppers Crossing) | 9500 | 0 | 950 | 8550 | qtr 4 2021-22
Timbarra P-9 College – modernisation – funding to plan for the committed upgrade of existing school facilities (Berwick) | 290 | 0 | 203 | 87 | qtr 3 2020-21
Traralgon (Kosciuszko Street) Primary School – modernisation – upgrade existing school facilities through the modular buildings program (Traralgon) | 2890 | 0 | 2890 | 0 | qtr 4 2019-20
Tucker Road Bentleigh Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Bentleigh) | 452 | 0 | 316 | 136 | qtr 3 2020-21
Upwey High School – Next stage modernisation – upgrade existing school facilities (Upwey) | 2700 | 0 | 2700 | 0 | qtr 4 2019-20
Urquhart Park Primary School – Asbestos Safety Program – modular buildings program (Newington) | 1503 | 0 | 676 | 827 | qtr 2 2020-21
Victoria University Secondary College – modernisation – funding to deliver previously planned works (St Albans) | 23946 | 0 | 2395 | 21551 | qtr 2 2022 -23
Viewbank Primary School – modernisation – upgrade existing school facilities through the modular buildings program (Viewbank) | 3817 | 0 | 1718 | 2099 | qtr 2 2020-21
Wales Street Primary School – modernisation – upgrade existing school facilities (Thornbury) | 4100 | 0 | 287 | 3813 | qtr 1 2022-23
Warringa Park School – modernisation – upgrade existing school facilities (Hoppers Crossing) | 12400 | 0 | 5084 | 7316 | qtr 4 2020-21
Watsonia Primary School – modernisation – upgrade existing school facilities (Watsonia) | 2087 | 0 | 146 | 1941 | qtr 4 2021-22
Waverley Meadows Primary School – modernisation – upgrade existing school facilities (Wheelers Hill) | 1100 | 0 | 77 | 1023 | qtr 3 2021-22
Wellington Secondary College – modernisation – upgrade existing school facilities (Mulgrave) | 10500 | 0 | 735 | 9765 | qtr 1 2022-23
White Hills Primary School – modernisation – funding to deliver previously planned works (White Hills) | 4600 | 0 | 460 | 4140 | qtr 3 2021-22
Williamstown High School – modernisation – funding to plan for the committed upgrade of existing school facilities (Williamstown) | 137 | 0 | 96 | 41 | qtr 3 2020-21
Windsor Primary School – modernisation – funding to plan for the committed upgrade of existing school facilities (Windsor) | 477 | 0 | 334 | 143 | qtr 3 2020-21
Winters Flat Primary School – Asbestos Safety Program – modular buildings program (Castlemaine) | 2916 | 0 | 2613 | 303 | qtr 2 2020-21
Yarra Ranges Special Developmental School – Stage 2 – modernisation – upgrade existing school facilities (Mount Evelyn) | 3451 | 0 | 1726 | 1725 | qtr 3 2021-22
Technical and further education
Box Hill Institute Integrated Centre for Sustainable Construction Technologies – funding for new facilities (Lilydale) | 10200 | 0 | 6030 | 4170 | qtr 2 2020-21
GOTAFE Health and Community Services Training Facility – funding for new facilities and re-use of existing facilities (Seymour) | 2540 | 0 | 800 | 1740 | qtr 2 2020-21
South West TAFE Library and Learning Hub – funding for new facilities (Warrnambool) | 20250 | 0 | 2700 | 17550 | qtr 3 2021-22
The Gordon Culinary School – funding for new and refurbishing existing facilities (Geelong) | 23500 | 0 | 5000 | 18500 | qtr 4 2020-21
Total new projects | 1746061 | 2650 | 822092.9 | 921321.1
The total may not add due to rounding.
Source: Department of Education and Training
Asset Initiatives
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Early Childhood Development
Davis Creek P6 Early learning facility 2018-19 (Tarneit) | 3000 | 427 | 1973 | 600 | qtr 3 2019-20
Botanic Ridge P6 Early learning facility 2018-19 (Botanic Ridge) | 5901 | 4186 | 1715 | 0 | qtr 3 2019-20
TEI includes co-contribution from local government.
Early Childhood Facilities 2017-18 (statewide) | 11600 | 6630 | 4430 | 540 | qtr 2 2020-21
TEI includes co-contribution from non-government organisations.
Wyndham South (Riverwalk) P6 Early learning facility 2018-19 (Werribee) | 3000 | 1208 | 1792 | 0 | qtr 3 2019-20
School Education
Abbotsford Primary School 2018-19 (Abbotsford) | 8282 | 6788 | 1458 | 36 | qtr 2 2019-20
TEI includes co-contribution from the school.
Albert Park Primary School 2018-19 (Albert Park) | 900 | 301 | 599 | 0 | qtr 2 2020-21
Albion Primary School 2018-19 (Albion) | 1300 | 478 | 657 | 165 | qtr 3 2020-21
Alphington Primary School 2017-18 (Alphington) | 4520 | 203 | 3865 | 452 | qtr 3 2019-20
Ardmona Primary School 2018-19 – Stage 2 (Ardmona) | 500 | 429 | 71 | 0 | qtr 4 2019-20
Armstrong Creek 7-12 2018-19 – Stage 1 (Armstrong Creek) | 3900 | 1552 | 1948 | 400 | qtr 2 2019-20
Estimated completion date has been revised to reflect a more accurate forecast.
Armstrong Creek West P6 2018-19 (Mount Duneed) | 20200 | 17953 | 2247 | 0 | qtr 3 2019-20
Ascot Vale Primary School 2017-18 (Ascot Vale) | 1759 | 1587 | 172 | 0 | qtr 2 2019-20
Ashby Primary School 2017-18 (Geelong West) | 2849 | 1205 | 1644 | 0 | qtr 2 2019-20
TEI includes co-contribution from the school.
Ballam Park Primary School 2018-19 (Frankston) | 800 | 50 | 613 | 137 | qtr 2 2020-21
Ballarat High School 2014-15 (Ballarat) | 7813 | 6568 | 1245 | 0 | qtr 1 2019-20
Ballarat High School 2018-19 – Stage 2 (Ballarat) | 4000 | 163 | 3769 | 68 | qtr 3 2020-21
Ballarat Secondary College – Mount Rowan Campus 2017-18 (Wendouree) | 6030 | 2355 | 3072 | 603 | qtr 4 2019-20
Ballarat Secondary College – Woodmans Hill Campus 2017-18 (Ballarat East) | 3665 | 3477 | 188 | 0 | qtr 3 2019-20
TEI includes co-contribution from the school.
Banyule Primary School 2017-18 (Rosanna) | 1224 | 984 | 240 | 0 | qtr 2 2019-20
TEI includes co-contribution from the school.
Banyule Primary School 2018-19 – Stage 2 (Rosanna) | 3470 | 2771 | 699 | 0 | qtr 4 2019-20
Barwon Valley School 2018-19 (Belmont) | 2100 | 592 | 1144 | 364 | qtr 3 2020-21
Bayside Special Developmental School 2017-18 (Moorabbin) | 11460 | 10871 | 589 | 0 | qtr 3 2019-20
TEI includes co-contribution from the school.
Bell Primary School 2017-18 (Preston) | 2000 | 782 | 1218 | 0 | qtr 1 2020-21
Bellbrae Primary School 2017-18 (Bellbrae) | 754 | 131 | 450 | 173 | qtr 1 2019-20
Belvedere Park Primary School 2018-19 (Seaford) | 1400 | 69 | 764 | 567 | qtr 3 2020-21
Bentleigh West Primary School 2018-19 (Bentleigh) | 450 | 26 | 408 | 16 | qtr 2 2020-21
Berwick Secondary College 2018-19 (Berwick) | 1300 | 103 | 1048 | 149 | qtr 3 2020-21
Beveridge West P6 2018-19 (Beveridge) | 19700 | 7638 | 12062 | 0 | qtr 3 2019-20
Big Hill Primary School 2017-18 (Big Hill) | 2010 | 1237 | 675 | 98 | qtr 4 2019-20
Estimated completion date has been revised to reflect a more accurate forecast.
Bimbadeen Heights Primary School 2016-17 (Mooroolbark) | 5300 | 4675 | 625 | 0 | qtr 2 2019-20
Estimated completion date has been revised to reflect a more accurate forecast.
Boisdale Consolidated School 2018-19 (Boisdale) | 400 | 91 | 309 | 0 | qtr 1 2020-21
Bonbeach Primary School 2018-19 (Bonbeach) | 6300 | 306 | 3646 | 2348 | qtr 4 2020-21
Botanic Ridge P6 2018-19 (Botanic Ridge) | 16500 | 4371 | 12129 | 0 | qtr 3 2019-20
Bourchier Street Primary School 2017-18 (Shepparton) | 1407 | 1262 | 145 | 0 | qtr 2 2019-20
Box Hill High School 2018-19 (Box Hill) | 500 | 35 | 465 | 0 | qtr 2 2020-21
Brauer Secondary College 2016-17 (Warrnambool) | 4000 | 1796 | 1804 | 400 | qtr 4 2019-20
Estimated completion date has been revised to reflect a more accurate forecast.
Brunswick North Primary School 2017-18 (Brunswick West) | 3320 | 2932 | 371 | 17 | qtr 3 2019-20
Brunswick South West Primary School 2018-19 (Brunswick West) | 4100 | 191 | 3012 | 897 | qtr 4 2020-21
Bundoora Primary School 2018-19 – Stage 2 (Bundoora) | 2707 | 103 | 1965 | 639 | qtr 2 2020-21
Estimated completion date has been revised to reflect a more accurate forecast.
Cardross Primary School 2018-19 (Cardross) | 800 | 321 | 479 | 0 | qtr 2 2020-21
Carisbrook Primary School 2017-18 (Carisbrook) | 2443 | 2396 | 47 | 0 | qtr 2 2019-20
TEI includes co-contribution from the school.
Carnegie Primary School 2017-18 (Carnegie) | 1500 | 1338 | 162 | 0 | qtr 1 2019-20
Carrum Downs Secondary College 2017-18 (Carrum Downs) | 3010 | 1424 | 1586 | 0 | qtr 2 2019-20
Carrum Primary School 2018-19 (Carrum) | 1000 | 153 | 847 | 0 | qtr 2 2020-21
Casey Fields (Five Ways) P6 2018-19 (Cranbourne East) | 20100 | 7764 | 12336 | 0 | qtr 3 2019-20
Casterton Primary School 2018-19 (Casterton) | 300 | 65 | 234 | 1 | qtr 1 2020-21
Castlemaine North Primary School 2017-18 (Castlemaine) | 1206 | 1200 | 6 | 0 | qtr 2 2019-20
Castlemaine Primary School 2017-18 (Castlemaine) | 502 | 455 | 47 | 0 | qtr 1 2019-20
Castlemaine Secondary College 2018-19 – Stage 3 (Castlemaine) | 11750 | 407 | 8070 | 3273 | qtr 3 2020-21
Centre for Higher Education Studies 2018-19 (South Yarra) | 27500 | 5526 | 4362 | 17612 | qtr 2 2021-22
Ceres Primary School 2018-19 – Stage 2 (Ceres) | 600 | 522 | 13 | 65 | qtr 3 2019-20
Charles La Trobe P12 College 2018-19 (West Heidelberg) | 6242 | 3251 | 2991 | 0 | qtr 4 2019-20
TEI includes co-contribution from the school.
Chelsea Heights Primary School 2018-19 (Chelsea Heights) | 4500 | 24 | 3 | 4473 | qtr 4 2020-21
Chilwell Primary School 2017-18 (Newtown) | 2410 | 741 | 1669 | 0 | qtr 2 2019-20
Clyde North East P6 2018-19 (Clyde North) | 20800 | 8056 | 12744 | 0 | qtr 3 2019-20
Coburg High School 2017-18 (Coburg) | 1900 | 1877 | 23 | 0 | qtr 2 2019-20
Coburg North Primary School 2017-18 (Coburg) | 6727 | 5302 | 1345 | 80 | qtr 3 2019-20
TEI includes co-contribution from the school.
Collingwood College 2017-18 (Collingwood) | 7190 | 5817 | 1373 | 0 | qtr 3 2019-20
TEI includes co-contribution from the school.
Copperfield College 2018-19 (Delahey) | 3500 | 244 | 2789 | 467 | qtr 3 2020-21
Corryong College 2017-18 (Corryong) | 2363 | 987 | 1089 | 287 | qtr 2 2019-20
TEI includes co-contribution from the school.
Craigieburn South 7-12 2018-19 – Stage 1 (Craigieburn) | 24000 | 13206 | 10794 | 0 | qtr 3 2019-20
Cranbourne Secondary College 2016-17 (Cranbourne) | 9000 | 6630 | 2284 | 86 | qtr 1 2019-20
Estimated completion date has been revised to reflect a more accurate forecast.
Dandenong West Primary School 2018-19 (Dandenong) | 5100 | 2420 | 2680 | 0 | qtr 4 2019-20
Davis Creek P6 2018-19 (Tarneit) | 20100 | 8203 | 7877 | 4020 | qtr 3 2019-20
Derrinallum P12 College 2018-19 (Derrinallum) | 900 | 81 | 724 | 95 | qtr 2 2020-21
Diamond Valley College 2018-19 – Stage 2 (Diamond Creek) | 1800 | 115 | 1494 | 191 | qtr 4 2019-20
Dimboola Memorial Secondary College 2018-19 (Dimboola) | 600 | 77 | 523 | 0 | qtr 2 2020-21
Dinjerra Primary School 2018-19 (Braybrook) | 7449 | 5113 | 847 | 1489 | qtr 3 2019-20
TEI includes co-contribution from the school.
Don Valley Primary School 2018-19 (Don Valley) | 170 | 112 | 58 | 0 | qtr 3 2019-20
Donald High School 2016-17 (Donald) | 3500 | 1690 | 1610 | 200 | qtr 1 2019-20
Estimated completion date has been revised to reflect a more accurate forecast.
Dunolly Primary School 2018-19 (Dunolly) | 161 | 7 | 154 | 0 | qtr 1 2019-20
East Bentleigh Primary School 2018-19 (East Bentleigh) | 5000 | 451 | 4407 | 142 | qtr 4 2020-21
Edithvale Primary School 2018-19 (Edithvale) | 750 | 86 | 664 | 0 | qtr 2 2020-21
Eltham High School (Eltham) | 1507 | 486 | 870 | 151 | qtr 2 2019-20
Elwood College 2018-19 – Stage 2 (Elwood) | 600 | 420 | 180 | 0 | qtr 1 2019-20
Epping Secondary College 2018-19 (Epping) | 3000 | 101 | 2462 | 437 | qtr 3 2020-21
Euroa Secondary College 2018-19 (Euroa) | 950 | 52 | 463 | 435 | qtr 3 2020-21
Footscray Learning Precinct 2017-18 (Footscray) | 10636 | 8411 | 1121 | 1104 | qtr 4 2019-20
Footscray Learning Precinct 2018-19 – Stage 2 (Seddon) | 29275 | 8233 | 10487 | 10555 | qtr 3 2020-21
Frankston High School 2017-18 (Frankston) | 1000 | 763 | 237 | 0 | qtr 2 2019-20
Estimated completion date has been revised to reflect a more accurate forecast.
Frankston North Education Plan 2018-19 – Stage 1 (Frankston) | 15000 | 1205 | 5300 | 8495 | qtr 4 2020-21
Frankston Special Developmental School 2018-19 (Frankston) | 815 | 302 | 113 | 400 | qtr 3 2020-21
Geelong East Primary School 2017-18 (Geelong East) | 1025 | 54 | 971 | 0 | qtr 2 2019-20
Geelong High School 2016-16 (Geelong) | 12700 | 5026 | 7547 | 127 | qtr 3 2019-20
TEI includes co-contribution from the school.
George Street Primary School 2018-19 (Hamilton) | 200 | 142 | 58 | 0 | qtr 2 2020-21
Gisborne Primary School 2017-18 (Gisborne) | 1628 | 1389 | 239 | 0 | qtr 2 2019-20
Gisborne Primary School 2018-19 – Stage 2 (Gisborne) | 10000 | 3723 | 2051 | 4226 | qtr 4 2020-21
Gladstone Park Primary School 2018-19 (Gladstone Park) | 1500 | 76 | 1127 | 297 | qtr 3 2020-21
Glenallen School 2018-19 – Stage 2 (Glen Waverley) | 700 | 381 | 307 | 12 | qtr 4 2019-20
Greenhills Primary School 2018-19 (Greensborough) | 2200 | 183 | 1679 | 338 | qtr 3 2020-21
Hamlyn Banks Primary School 2017-18 (Hamlyn Heights) | 1557 | 859 | 690 | 8 | qtr 2 2019-20
Hampton Park Secondary College 2018-19 (Hampton Park) | 2620 | 84 | 1920 | 616 | qtr 3 2020-21
Hawkesdale P12 College 2018-19 (Hawkesdale) | 2000 | 149 | 1822 | 29 | qtr 4 2020-21
Heathmont College 2018-19 (Heathmont) | 5500 | 187 | 2908 | 2405 | qtr 4 2020-21
Heywood District Secondary College 2018-19 (Heywood) | 600 | 41 | 559 | 0 | qtr 2 2020-21
Highton Primary School 2018-19 (Highton) | 1600 | 84 | 1162 | 354 | qtr 3 2020-21
Hoddles Creek Primary School 2018-19 (Hoddles Creek) | 90 | 0 | 90 | 0 | qtr 2 2019-20
Huntingdale Primary School 2018-19 (Oakleigh South) | 400 | 40 | 360 | 0 | qtr 4 2019-20
Inclusive Schools Fund 2018-19 (statewide) | 10000 | 8000 | 2000 | 0 | qtr 4 2019-20
Ivanhoe Primary School 2018-19 – Stage 2 (Ivanhoe) | 4500 | 769 | 2922 | 809 | qtr 2 2020-21
Kalianna Special School 2017-18 (Bendigo) | 10076 | 4347 | 5729 | 0 | qtr 1 2020-21
Kaniva College 2018-19 (Kaniva) | 2300 | 175 | 2125 | 0 | qtr 3 2020-21
Karingal Primary School 2018-19 (Frankston) | 515 | 360 | 155 | 0 | qtr 1 2020-21
Keilor Heights Primary School 2017-18 (Keilor East) | 522 | 512 | 10 | 0 | qtr 1 2019-20
Kerang Primary School 2018-19 (Kerang) | 400 | 51 | 339 | 10 | qtr 2 2020-21
Keysborough South P6 2018-19 (Keysborough) | 18900 | 15792 | 3108 | 0 | qtr 3 2019-20
Kialla West Primary School 2017-18 (Kialla West) | 955 | 787 | 168 | 0 | qtr 1 2019-20
Kingsley Park Primary School 2018-19 (Frankston) | 780 | 47 | 717 | 16 | qtr 2 2020-21
Koo Wee Rup Secondary College 2018-19 (Koo Wee Rup) | 850 | 86 | 764 | 0 | qtr 2 2020-21
Kurnai College 2015-16 (Morwell) | 8299 | 6437 | 1862 | 0 | qtr 2 2019-20
Estimated completion date has been revised to reflect a more accurate forecast. TEI includes co-contribution from the school.
Kurnai College 2017-18 (Morwell) | 1507 | 49 | 1454 | 4 | qtr 1 2020-21
Estimated completion date has been revised to reflect a more accurate forecast.
Lalor Gardens Primary School 2018-19 (Lalor) | 4095 | 3851 | 234 | 10 | qtr 3 2019-20
TEI includes co-contribution from the school.
Land acquisition 2017-18 (statewide) | 70450 | 62751 | 7699 | 0 | ongoing
Land acquisition 2018-19 (statewide) | 296545 | 245924 | 50621 | 0 | qtr 4 2019-20
TEI includes co-contributions from Victorian State Government entities.
LaTrobe Valley Schools building upgrade – 2016-17 | 6000 | 3617 | 2383 | 0 | qtr 4 2019-20
Launching Place Primary School 2018-19 (Launching Place) | 500 | 63 | 433 | 4 | qtr 1 2020-21
Leopold Primary School 2017-18 (Leopold) | 3304 | 1880 | 1424 | 0 | qtr 3 2019-20
TEI includes co-contribution from the school.
Lilydale and Upper Yarra Secondary Schools Plan 2018-19 – Stage 1 (Lilydale) | 20000 | 5765 | 14235 | 0 | qtr 4 2020-21
Lilydale West Primary School 2017-18 (Lilydale) | 2110 | 1742 | 368 | 0 | qtr 2 2019-20
Lismore Primary School 2018-19 (Lismore) | 110 | 0 | 110 | 0 | qtr 3 2019-20
Lucas Primary School 2018-19 (Lucas) | 17100 | 6754 | 10346 | 0 | qtr 3 2019-20
Lyndale Secondary College 2017-18 (Dandenong North) | 6000 | 5309 | 691 | 0 | qtr 2 2019-20
Lyndale Secondary College 2018-19 – Stage 2 (Dandenong North) | 3800 | 1356 | 2444 | 0 | qtr 3 2019-20
Manor Lakes College 2016-17 – Stage 5 (Wyndham Vale) | 10900 | 7428 | 3351 | 121 | qtr 2 2019-20
Estimated completion date has been revised to reflect a more accurate forecast.
Mansfield Primary School 2017-18 (Mansfield) | 2192 | 1660 | 518 | 14 | qtr 2 2019-20
TEI includes co-contribution from the school.
Mansfield Secondary College 2018-19 – Stage 2 (Mansfield) | 4850 | 233 | 4404 | 213 | qtr 2 2020-21
Matthew Flinders Girls Secondary College 2016-17 (Geelong) | 7019 | 5081 | 1425 | 513 | qtr 2 2019-20
Estimated completion date has been revised to reflect a more accurate forecast. TEI includes co-contribution from the school.
Melba College 2018-19 – Stage 3 (Croydon) | 14546 | 3114 | 11432 | 0 | qtr 1 2020-21
TEI includes co-contributions from the school, Victorian State Government entities and non-government organisations.
Melton West Primary School 2018-19 (Melton) | 6400 | 3571 | 2829 | 0 | qtr 3 2019-20
Merino Consolidated School 2018-19 (Merino) | 170 | 34 | 135 | 1 | qtr 3 2019-20
Merri Creek Primary School 2017-18 (Fitzroy North) | 4220 | 1595 | 2625 | 0 | qtr 3 2019-20
TEI includes co-contribution from the school.
Mildura West Primary School 2018-19 (Mildura) | 1800 | 48 | 1318 | 434 | qtr 3 2020-21
Monash Special Developmental School 2018-19 (Wheelers Hill) | 1900 | 78 | 1388 | 434 | qtr 3 2020-21
Monbulk College 2017-18 (Monbulk) | 7578 | 5436 | 1035 | 1107 | qtr 2 2019-20
Monbulk College 2018-19 – Stage 3 (Monbulk) | 8510 | 1340 | 3269 | 3901 | qtr 4 2020-21
Montmorency South Primary School 2017-18 (Montmorency) | 8300 | 7814 | 486 | 0 | qtr 4 2019-20
Montrose Primary School 2018-19 (Montrose) | 3820 | 155 | 2825 | 840 | qtr 4 2020-21
Moolap Primary School 2018-19 (Moolap) | 600 | 55 | 542 | 3 | qtr 2 2020-21
Moonee Ponds West Primary School 2017-18 (Moonee Ponds) | 575 | 176 | 399 | 0 | qtr 1 2019-20
TEI includes co-contribution from the school.
Mooroolbark College 2018-19 (Mooroolbark) | 7000 | 259 | 2365 | 4376 | qtr 4 2020-21
Moreland Primary School 2018-19 (Coburg) | 600 | 40 | 545 | 15 | qtr 1 2020-21
Mortlake P12 College 2018-19 (Mortlake) | 950 | 46 | 900 | 4 | qtr 2 2020-21
Mount Clear College 2018-19 – Stage 2 (Mount Clear) | 3000 | 134 | 1197 | 1669 | qtr 1 2020-21
Mount Duneed Regional Primary School 2017-18 (Mount Duneed) | 2245 | 1600 | 645 | 0 | qtr 2 2019-20
TEI includes co-contribution from the school.
Mount Erin Secondary College 2017-18 (Frankston South) | 2130 | 1687 | 443 | 0 | qtr 2 2019-20
Mount Erin Secondary College 2018-19 – Stage 2 (Frankston South) | 1800 | 1 | 1286 | 513 | qtr 1 2020-21
Mulgrave Primary School 2018-19 (Mulgrave) | 3800 | 891 | 1689 | 1220 | qtr 4 2020-21
Narre Warren South P12 College 2017-18 (Narre Warren South) | 5020 | 3326 | 1694 | 0 | qtr 3 2019-20
Narre Warren South P12 College 2018-19 – Stage 2 (Narre Warren South) | 400 | 200 | 200 | 0 | qtr 1 2019-20
Nepean Special School 2018-19 (Seaford) | 1300 | 64 | 978 | 258 | qtr 3 2020-21
Newtown Primary School 2017-18 (Newtown) | 2010 | 1247 | 763 | 0 | qtr 2 2019-20
Northcote Primary School 2017-18 (Northcote) | 3160 | 902 | 2258 | 0 | qtr 4 2019-20
Northern Bay P12 College 2018-19 (Corio) | 1500 | 355 | 1133 | 12 | qtr 4 2020-21
Northern College of the Arts and Technology 2018-19 (Preston) | 9000 | 6984 | 2016 | 0 | qtr 2 2019-20
Northern School For Autism 2018-19 (Reservoir) | 2200 | 131 | 1910 | 159 | qtr 3 2020-21
Oakleigh Primary School 2018-19 (Oakleigh) | 9111 | 4494 | 4077 | 540 | qtr 1 2020-21
TEI includes co-contribution from the school.
Oberon High School 2016-17 (Belmont) | 2500 | 20 | 1180 | 1300 | qtr 4 2020-21
Estimated completion date has been revised to reflect a more accurate forecast.
Oberon Primary School 2017-18 (Belmont) | 1407 | 177 | 1230 | 0 | qtr 2 2019-20
Oberon South Primary School 2018-19 (Belmont) | 1200 | 32 | 875 | 293 | qtr 3 2020-21
Orbost North Primary School 2018-19 (Orbost) | 130 | 21 | 109 | 0 | qtr 3 2019-20
Orbost Secondary College 2018-19 (Orbost) | 900 | 134 | 766 | 0 | qtr 3 2020-21
Ormond Primary School 2018-19 (Ormond) | 2300 | 159 | 1500 | 641 | qtr 3 2020-21
Orrvale Primary School 2017-18 (Orrvale) | 1768 | 1553 | 207 | 8 | qtr 2 2019-20
Pascoe Vale Girls Secondary College 2018-19 (Pascoe Vale) | 4300 | 811 | 2932 | 557 | qtr 3 2020-21
TEI includes co-contribution from the school.
Pascoe Vale Primary School 2018-19 (Pascoe Vale) | 3000 | 170 | 2178 | 652 | qtr 3 2020-21
Patterson Lakes Primary School 2018-19 (Patterson Lakes) | 2200 | 78 | 1613 | 509 | qtr 3 2020-21
Planning for schools 2018-19 (statewide) | 15490 | 3908 | 11582 | 0 | qtr 4 2020-21
TEI includes reclassification of some cost as operating expenditure.
Point Cook South Senior Secondary School 2018-19 (Point Cook) | 53000 | 37285 | 15715 | 0 | qtr 3 2019-20
Port Melbourne Primary School 2017-18 (Port Melbourne) | 5520 | 2208 | 3312 | 0 | qtr 1 2019-20
TEI includes co-contribution from the school.
Preston High School 2018-19 – Stage 2 (Preston) | 10625 | 2627 | 5008 | 2990 | qtr 1 2021-22
Reservoir East Primary School 2018-19 (Reservoir) | 6300 | 5192 | 1004 | 104 | qtr 2 2019-20
Richmond Primary School 2018-19 (Richmond) | 200 | 72 | 128 | 0 | qtr 4 2019-20
Riddells Creek Primary School 2018-19 (Riddells Creek) | 2200 | 769 | 1322 | 109 | qtr 3 2020-21
Ringwood Secondary College 218-19 – Stage 2 (Ringwood) | 5500 | 813 | 3442 | 1245 | qtr 2 2020-21
Romsey Regeneration 2018-19 (Romsey) | 3200 | 99 | 2101 | 1000 | qtr 3 2020-21
Rowellyn Park Primary School 2018-19 (Carrum Downs) | 5700 | 331 | 3446 | 1923 | qtr 4 2020-21
Roxburgh College 2018-19 (Roxburgh Park) | 3000 | 133 | 2161 | 706 | qtr 3 2020-21
Sandringham East Primary School 2018-19 (Sandringham) | 7800 | 6332 | 1468 | 0 | qtr 3 2019-20
School Pride and Sport Fund 2018-19 (statewide) | 10000 | 4647 | 5353 | 0 | qtr 4 2019-20
School Pride and Sports Fund 2016-17 (statewide) | 16011 | 10911 | 5100 | 0 | qtr 4 2019-20
TEI includes co-contribution from the school.
School Pride and Sports Fund 2017-18 (statewide) | 5913 | 5422 | 491 | 0 | qtr 4 2020-21
TEI includes co-contribution from the school.
Seaford North Primary School 2017-18 (Seaford) | 5020 | 2008 | 3012 | 0 | qtr 3 2019-20
Seaford Primary School 2018-19 (Seaford) | 5300 | 170 | 3860 | 1270 | qtr 2 2020-21
Seymour College 2018-19 (Seymour) | 6881 | 4281 | 2600 | 0 | qtr 3 2019-20
Shared facilities fund 2016-17 (statewide) | 50000 | 28649 | 9000 | 12351 | qtr 4 2020-21
Shepparton Education Plan 2018-19 – Stage 1 (Shepparton) | 20500 | 1100 | 7400 | 12000 | qtr 3 2021-22
Spensley Street Primary School 2018-19 (Clifton Hill) | 550 | 59 | 462 | 29 | qtr 2 2020-21
Spotswood Primary School 2017-18 (Spotswood) | 1407 | 1329 | 71 | 7 | qtr 3 2019-20
Spring Gully Primary School 2017-18 (Bendigo) | 5240 | 5157 | 83 | 0 | qtr 1 2019-20
TEI includes co-contribution from the school.
Spring Gully Primary School 2018-19 – Stage 2 (Bendigo) | 2170 | 874 | 1296 | 0 | qtr 2 2019-20
Estimated completion date has been revised to reflect a more accurate forecast.
Springvale Rise Primary School 2018-19 (Springvale) | 1700 | 88 | 1349 | 263 | qtr 2 2020-21
St Helena Secondary College 2018-19 (Eltham North) | 3820 | 914 | 2850 | 56 | qtr 4 2020-21
St Kilda Primary School 2018-19 (St Kilda) | 5460 | 199 | 3985 | 1276 | qtr 4 2020-21
Stawell Secondary College 2018-19 (Stawell) | 4000 | 1227 | 2195 | 578 | qtr 3 2020-21
Strathmore Secondary College 2018-19 (Strathmore) | 13800 | 6728 | 4247 | 2825 | qtr 4 2019-20
Sunbury and Macedon Ranges Specialist School - Bullengarook Senior Campus 2018-19 (Bullengarook) | 4200 | 121 | 3088 | 991 | qtr 4 2020-21
Sunbury and Macedon Ranges Specialist School - Sunbury Campus 2018-19 (Sunbury) | 10800 | 3077 | 3154 | 4569 | qtr 4 2020-21
Sunbury College 2017-18 (Sunbury) | 4800 | 2356 | 2356 | 88 | qtr 2 2019-20
Sunbury Downs Secondary College 2017-18 (Sunbury) | 3920 | 1496 | 2424 | 0 | qtr 3 2019-20
Sunbury Heights Primary School 2018-19 (Sunbury) | 700 | 53 | 519 | 128 | qtr 2 2020-21
Sunbury Primary School 2018-19 (Sunbury) | 3500 | 114 | 3035 | 351 | qtr 4 2020-21
Sunshine North Primary School 2018-19 (Sunshine North) | 300 | 21 | 227 | 52 | qtr 4 2019-20
Surfside Primary School 2018-19 (Ocean Grove) | 1300 | 105 | 1090 | 105 | qtr 2 2020-21
Swan Hill Primary School 2017-18 (Swan Hill) | 502 | 439 | 63 | 0 | qtr 1 2019-20
Tallarook Primary School 2018-19 (Tallarook) | 150 | 31 | 119 | 0 | qtr 3 2019-20
Tarwin Valley Primary School 2018-19 (Meeniyan) | 500 | 33 | 455 | 12 | qtr 2 2020-21
Taylors Hill Secondary College 2017-18 (Taylors Hill) | 23306 | 22515 | 791 | 0 | qtr 3 2019-20
TEI includes co-contribution from local government.
Teesdale Primary School 2018-19 (Teesdale) | 300 | 295 | 5 | 0 | qtr 1 2020-21
The Alpine School 2018-19 (Launching Place) | 6500 | 762 | 5362 | 376 | qtr 1 2020-21
Thornbury High School 2017-18 (Thornbury) | 5000 | 3660 | 1340 | 0 | qtr 1 2020-21
Torquay P-6 College 2018-19 (Torquay) | 1900 | 126 | 1405 | 369 | qtr 3 2020-21
Traralgon Secondary and Special School Regeneration 2018-19 – Stage 1 (Traralgon) | 6000 | 321 | 2749 | 2930 | qtr 4 2020-21
Upwey High School 2018-19 – Stage 2 (Upwey) | 13900 | 220 | 7935 | 5745 | qtr 4 2020-21
Upwey High School 2017-18 (Upwey) | 10000 | 9456 | 272 | 272 | qtr 2 2021-22
Wallington Primary School 2018-19 (Wallington) | 400 | 37 | 361 | 2 | qtr 4 2019-20
Wandong Primary School 2017-18 (Wandong) | 1379 | 744 | 506 | 129 | qtr 2 2019-20
Estimated completion date has been revised to reflect a more accurate forecast. TEI includes co-contribution from the school.
Wangaratta District Specialist School and Appin Park Primary School Regeneration 2018-19 (Wangaratta) | 2200 | 182 | 1855 | 163 | qtr 3 2020-21
Warrnambool College 2016-17 (Warrnambool) | 4600 | 2600 | 1600 | 400 | qtr 4 2019-20
Estimated completion date has been revised to reflect a more accurate forecast.
Warrnambool East Primary School 2017-18 (Warrnambool) | 2626 | 1619 | 705 | 302 | qtr 2 2019-20
TEI includes co-contribution from the school.
Warrnambool Special Developmental School 2018-19 – Stage 2 (Warrnambool) | 14600 | 10441 | 4159 | 0 | qtr 3 2019-20
Warrnambool West Primary School 2018-19 (Warrnambool) | 250 | 186 | 64 | 0 | qtr 4 2019-20
Waverley Meadows Primary School 2018-19 – Stage 2 (Wheelers Hill) | 600 | 0 | 600 | 0 | qtr 4 2019-20
Waverley Meadows Primary School 2017-18 (Wheelers Hill) | 854 | 544 | 310 | 0 | qtr 2 2019-20
Wellington Secondary College 2017-18 (Mulgrave) | 6293 | 6110 | 183 | 0 | qtr 1 2019-20
TEI includes co-contribution from the school.
Westall Schools Regeneration 2018-19 (Clayton South) | 12300 | 3674 | 8476 | 150 | qtr 1 2020-21
Western Autistic School – Niddrie Campus 2018-19 (Laverton) | 8500 | 342 | 3486 | 4672 | qtr 4 2020-21
TEI includes co-contribution from the school.
Winton Primary School 2018-19 (Winton) | 90 | 0 | 90 | 0 | qtr 3 2019-20
Wonthaggi Secondary College senior campus 2017-18 (Wonthaggi) | 30042 | 21528 | 8514 | 0 | qtr 4 2019-20
TEI includes co-contributions from the school, Victorian State Government entities and local government.
Wyndham South (Riverwalk) P6 2018-19 (Werribee) | 23700 | 14831 | 8869 | 0 | qtr 3 2019-20
Yarra Ranges Special Developmental School 2017-18 (Mount Evelyn) | 500 | 386 | 114 | 0 | qtr 2 2019-20
Estimated completion date has been revised to reflect a more accurate forecast.
Yarrabah School 2017-18 (Aspendale) | 20768 | 12863 | 7726 | 179 | qtr 2 2020-21
TEI includes co-contribution from the school.
Yarrabah School 2018-19 – Stage 2 (Aspendale) | 500 | 4 | 496 | 0 | qtr 1 2020-21
Technical and further education
TAFE Facilities Modernisation Program – 2018-19 | 120430 | 11500 | 59725 | 49205 | ongoing
Total existing projects | 1764843 | 921060 | 641562 | 202221
Total Education and Training projects | 3510904 | 923710 | 1463654.9 | 1123542.1
Other capital expenditure | na | na | 294250.9059 | na | various
Total 2019-20 Education and Training capital expenditure |  |  | 1757905.8059
Source: Department of Education and Training
Completed projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Aberfeldie Primary School 2016-17 (Essendon) | 1085 | 944 | qtr 4 2019-20
TEI includes co-contribution from the school.
Aberfeldie Primary School 2018-19 – Stage 2 (Essendon) | 1485 | 1292 | qtr 4 2021-22
TEI includes co-contribution from the school.
Aitken Hill Primary School 2017-18 (Craigieburn) | 13806 | 11735 | qtr 4 2020-21
Aitken Hill Primary School 2018-19 – Stage 2 (Craigieburn) | 6700 | 5606 | qtr 3 2020-21
TEI includes reclassification of some cost as operating expenditure.
Aldercourt Primary School 2017-18 (Frankston North) | 352 | 302 | qtr 3 2020-21
Asbestos Removal Program 2017-18 (statewide) | 84400 | 84400 | qtr 3 2020-21
TEI includes co-contribution from the school.
Ballarat Secondary College 2016-17 (Ballarat East) | 3000 | 2610 | qtr 1 2020-21
Banyan Fields Primary School 2017-18 (Carrum Downs) | 75 | 65 | qtr 4 2019-20
Baringa Special School 2016-17 (Moe) | 3490 | 3036 | qtr 1 2020-21
TEI includes co-contribution from the school.
Belmont High School 2016-17 (Belmont) | 5226 | 4546 | qtr 2 2020-21
TEI includes co-contribution from the school.
Benalla P-12 College 2016-17 (Benalla) | 3500 | 3045 | qtr 1 2020-21
Berendale School 2016-17 (Hampton East) | 2200 | 1914 | qtr 1 2020-21
Berwick Fields Primary School 2017-18 (Berwick) | 251 | 218 | qtr 4 2019-20
Boronia Heights Primary School 2017-18 (Boronia) | 1507 | 1311 | qtr 2 2020-21
Brighton Secondary College 2014-15 (Brighton East) | 8981 | 7804 | qtr 4 2019-20
TEI includes co-contribution from the school.
Broadford Secondary College 2016-17 (Broadford) | 4139 | 3601 | qtr 2 2020-21
TEI includes co-contribution from the school.
Brunswick Secondary College 2015-16 (Brunswick) | 10062 | 8553 | qtr 1 2020-21
TEI includes co-contribution from the school.
Burnside Primary School 2017-18 (Burnside) | 13806 | 11735 | qtr 3 2020-21
Burnside Primary School 218-19 – Stage 2 (Burnside) | 5559 | 4836 | qtr 3 2020-21
TEI includes reclassification of some cost as operating expenditure.
Camberwell Primary School 2014-15 (Camberwell) | 1509 | 1313 | qtr 1 2020-21
TEI includes co-contribution from the school.
Carnegie Primary School 2016-17 (Carnegie) | 4000 | 3480 | qtr 2 2020-21
Ceres Primary School 2017-18 (Ceres) | 653 | 572 | qtr 4 2020-21
Cheltenham Secondary College 2016-17 (Cheltenham) | 6519 | 5637 | qtr 2 2020-21
TEI includes co-contribution from the school.
Chisholm Institute Frankston Campus – Centre for Advanced Manufacturing and Trade 2014-15 (Frankston) | 21900 | 21900 | qtr 4 2019-20
Cobains Primary School 2017-18 (Cobains) | 800 | 683 | qtr 4 2020-21
Deans Marsh Primary School 2017-18 (Deans Marsh) | 492 | 414 | qtr 3 2020-21
Delacombe Primary School 2015-16 (Delacombe) | 2051 | 1784 | qtr 1 2020-21
TEI includes co-contribution from the school.
Diamond Valley College 2016-17 (Diamond Creek) | 2025 | 1762 | qtr 1 2020-21
TEI includes co-contribution from the school.
Diamond Valley Special Developmental School 2017-18 (Greensborough) | 75 | 65 | qtr 4 2019-20
Donburn Primary School 2017-18 (Doncaster East) | 1306 | 1126 | qtr 4 2020-21
Drouin Secondary College 2016-17 (Drouin) | 4500 | 3915 | qtr 2 2020-21
Elphinstone Primary School 2017-18 (Elphinstone) | 221 | 192 | qtr 3 2020-21
Essendon East Keilor District College 2015-16 (Keilor East) | 10390 | 8832 | qtr 1 2020-21
TEI includes co-contribution from the school.
Fairfield Primary School 2017-18 (Fairfield) | 2500 | 2175 | qtr 4 2020-21
Fountain Gate Secondary College 2017-18 (Narre Warren) | 4500 | 3896 | qtr 4 2020-21
Geelong High School 2014-15 (Geelong) | 9200 | 8004 | qtr 2 2021-22
TEI includes co-contribution from the school.
Glenallen School 2016-17 (Glen Waverley) | 2009 | 1748 | qtr 1 2020-21
TEI includes co-contribution from the school.
Gleneagles Secondary College 2017-18 (Endeavour Hills) | 502 | 402 | qtr 3 2020-21
Grovedale College 2016-17 (Grovedale) | 7300 | 6351 | qtr 2 2020-21
TEI includes co-contribution from the school.
Harrietville Primary School 2017-18 (Harrietville) | 291 | 251 | qtr 3 2020-21
Highvale Secondary College 2016-17 (Glen Waverley) | 5000 | 4153 | qtr 2 2020-21
Inclusive schools fund 2015-16 (statewide) | 10060 | 10060 | qtr 3 2020-21
Inclusive schools fund 2016-17 (statewide) | 10000 | 8000 | qtr 3 2020-21
Ivanhoe Primary School 2016-17 (Ivanhoe) | 2000 | 1740 | qtr 1 2020-21
Jamieson Primary School 2017-18 (Jamieson) | 201 | 175 | qtr 3 2020-21
Kambrya College 2016-17 (Berwick) | 3162 | 2748 | qtr 1 2020-21
TEI includes co-contribution from the school.
Keysborough Secondary College 2016-17 (Springvale South) | 13251 | 11263 | qtr 4 2019-20
TEI includes co-contribution from the school.
Kongwak Primary School 2018-19 (Kongwak) | 100 | 96 | qtr 2 2021-22
Kurunjang Primary School 2017-18 (Melton) | 1140 | 992 | qtr 1 2021-22
TEI includes co-contribution from the school.
Land acquisition 2016-17 (statewide) | 117000 | 107790 | qtr 3 2020-21
Lindenow Primary School 2017-18 (Lindenow) | 904 | 786 | qtr 4 2020-21
TEI includes co-contribution from the school.
Lockwood Primary School 2017-18 (Lockwood) | 613 | 533 | qtr 4 2020-21
Mansfield Secondary College 2016-17 (Mansfield) | 3000 | 2610 | qtr 1 2020-21
Maroondah Education Plan 2015-16 (Croydon/Ringwood) | 11641 | 9895 | qtr 3 2020-21
TEI includes co-contribution from the school.
Maroondah Education Plan 2016-17 (Croydon/Ringwood) | 18023 | 15320 | qtr 1 2020-21
McClelland Secondary College 2016-17 (Frankston) | 6832 | 5943 | qtr 2 2020-21
TEI includes co-contribution from the school.
Melton Secondary College 2017-18 (Melton) | 2505 | 2109 | qtr 2 2020-21
TEI includes co-contribution from the school.
Montmorency Secondary College 2016-17 (Montmorency) | 12600 | 10710 | qtr 4 2019-20
Moonambel Primary School 2017-18 (Moonambel) | 121 | 105 | qtr 1 2020-21
Mount Clear College 2016-17 (Mount Clear) | 2798 | 2434 | qtr 1 2020-21
TEI includes co-contribution from the school.
Nelson Park School 2016-17 (Bell Park) | 2500 | 2173 | qtr 1 2020-21
Newlands Primary School 2017-18 (Preston West) | 754 | 613 | qtr 4 2020-21
Newport Lakes Primary School 2016-17 (Newport) | 3016 | 2564 | qtr 1 2020-21
TEI includes co-contribution from the school.
Newstead Primary School 2017-18 (Newstead) | 151 | 128 | qtr 4 2019-20
Noble Park Secondary College 2015-16 (Noble Park) | 5000 | 4350 | qtr 1 2020-21
Northcote High School 2015-16 (Northcote) | 3730 | 3174 | qtr 4 2019-20
TEI includes co-contribution from the school.
Northcote High School 2016-17 (Northcote) | 1500 | 1270 | qtr 4 2019-20
Northern College of Technology and Arts 2016-17 (Preston) | 2038 | 1773 | qtr 1 2020-21
TEI includes co-contribution from the school.
Ocean Grove Primary School 2016-17 (Ocean Grove) | 4000 | 3480 | qtr 2 2020-21
Pakenham North East Primary School 2017-18 (Pakenham) | 13806 | 11735 | qtr 3 2020-21
Pakenham North East Primary School 2018-19 – Stage 2 (Pakenham) | 9833 | 8426 | qtr 3 2020-21
TEI includes reclassification of some cost as operating expenditure.
Parktone Primary School 2016-17 (Parkdale) | 4004 | 3440 | qtr 2 2020-21
TEI includes co-contribution from the school.
Pascoe Vale South Primary School 2016-17 (Pascoe Vale South) | 3500 | 3045 | qtr 1 2020-21
Penshurst Primary School 2017-18 (Penshurst) | 60 | 51 | qtr 1 2020-21
Phoenix P-12 Community College 2015-16 (Sebastopol) | 11156 | 9482 | qtr 4 2019-20
TEI includes co-contribution from the school.
Planning for schools 2015-16 (statewide) | 2149 | 1994 | qtr 3 2020-21
Planning for schools 2016-17 (statewide) | 11000 | 11000 | qtr 3 2020-21
Planning for schools 2017-18 (statewide) | 7002 | 7002 | qtr 1 2022-23
Portland Secondary College 2016-17 (Portland) | 2000 | 1732 | qtr 1 2020-21
Portland South Primary School 2017-18 (Portland) | 111 | 97 | qtr 1 2020-21
Prahran High School 2017-18 (Prahran) | 36824 | 31785 | qtr 2 2020-21
TEI includes reclassification of some cost as operating expenditure.
Preston High School 2017-18 (Preston) | 4961 | 4316 | qtr 3 2020-21
TEI includes reclassification of some cost as operating expenditure.
Queenscliff Primary School 2017-18 (Queenscliff) | 211 | 184 | qtr 3 2020-21
Red Cliffs Secondary College 2016-17 (Red Cliffs) | 7000 | 6156 | qtr 2 2020-21
Richmond West Primary School 2018-19 (Richmond) | 1080 | 940 | qtr 4 2020-21
Rochester Secondary College 2016-17 (Rochester) | 5040 | 4384 | qtr 2 2020-21
TEI includes co-contribution from the school.
Rosanna Golf Links Primary School 2014-15 (Rosanna) | 5730 | 4975 | qtr 4 2019-20
Rutherglen High School 2016-17 (Rutherglen) | 1600 | 1349 | qtr 4 2019-20
Sanctuary Lakes P9 2018-19 – Stage 2 (Point Cook) | 3053 | 2656 | qtr 3 2020-21
TEI includes reclassification of some cost as operating expenditure.
Sanctuary Lakes South P9 2017-18 (Point Cook) | 13806 | 11735 | qtr 3 2020-21
Seaspray Primary School 2017-18 (Seaspray) | 190 | 165 | qtr 4 2019-20
Silverton Primary School 2016-17 (Noble Park North) | 2100 | 1813 | qtr 1 2020-21
South Melbourne Park Primary School 2017-18 (Albert Park) | 21607 | 17718 | qtr 2 2020-21
TEI includes reclassification of some cost as operating expenditure.
Sunbury and Macedon Ranges Specialist School 2016-17 (Sunbury) | 4000 | 3480 | qtr 2 2020-21
Sunshine College 2014-15 (Sunshine) | 6299 | 5480 | qtr 3 2020-21
Sunshine College 2016-17 (Sunshine) | 10370 | 8815 | qtr 3 2020-21
TEI includes co-contribution from the school.
TAFE Rescue Fund 2015-16 (statewide) | 100000 | 100000 | qtr 3 2020-21
Taradale Primary School (Taradale)-2017-18 | 281 | 244 | qtr 3 2020-21
Tarneit Senior Secondary College 2016-17 – Stage 2 (Tarneit) | 12131 | 10309 | qtr 1 2020-21
TEI includes co-contribution from the school.
Tech Schools Program 2016-17 (statewide) | 61594 | 57494 | qtr 1 2020-21
The Basin Primary School 2016-17 (The Basin) | 1500 | 1305 | qtr 4 2019-20
Truganina East P9 2018-19 – Stage 2 (Truganina) | 4671 | 4064 | qtr 3 2020-21
TEI includes reclassification of some cost as operating expenditure.
Truganina East P9 2017-18 (Tarneit) | 13806 | 11735 | qtr 3 2020-21
Tucker Road Bentleigh Primary School 2016-17 (Bentleigh) | 3000 | 2610 | qtr 1 2020-21
Tungamah Primary School 2017-18 (Tungamah) | 100 | 87 | qtr 4 2019-20
Valkstone Primary School 2017-18 (Bentleigh East) | 3767 | 3278 | qtr 3 2020-21
TEI includes co-contribution from the school.
Viewbank College 2015-16 (Rosanna) | 12050 | 10233 | qtr 1 2020-21
Warracknabeal Secondary College 2016-17 (Warracknabeal) | 4023 | 3500 | qtr 2 2020-21
TEI includes co-contribution from the school.
Warracknabeal Special Development School 2016-17 (Warracknabeal) | 2006 | 1745 | qtr 1 2020-21
TEI includes co-contribution from the school.
Warragul Regional College 2016-17 (Warragul) | 5800 | 5046 | qtr 2 2020-21
Warrnambool Special Developmental School 2015-16 (Warrnambool) | 5000 | 4350 | qtr 4 2019-20
Werribee Secondary College 2015-16 (Werribee) | 7000 | 6090 | qtr 1 2020-21
Wheelers Hill Secondary College 2017-18 (Wheelers Hill) | 3520 | 3062 | qtr 3 2020-21
Whittington Primary School 2016-17 (Whittington) | 1816 | 1444 | qtr 4 2019-20
TEI includes co-contribution from the school.
Whittington Primary School 2015-16 (Whittington) | 5000 | 4089 | qtr 1 2020-21
William Ruthven Secondary College 2015-16 (Reservoir) | 11212 | 9467 | qtr 4 2019-20
TEI includes co-contribution from the school.
Winchelsea Primary School 2017-18 (Winchelsea) | 379 | 329 | qtr 3 2020-21
TEI includes co-contribution from the school.
Woodend Primary School 2016-17 (Woodend) | 2050 | 1784 | qtr 1 2020-21
TEI includes co-contribution from the school.
Wunghnu Primary School 2017-18 (Wunghnu) | 70 | 57 | qtr 4 2019-20
Yaapeet Primary School 2017-18 (Yaapeet) | 70 | 60 | qtr 1 2020-21
Yarrambat Park Primary School 2018-19 – Stage 2 (Doreen) | 5201 | 4524 | qtr 3 2020-21
TEI includes reclassification of some cost as operating expenditure.
Yarrambat Park Primary School 2017-18 (Yarrambat) | 13806 | 11735 | qtr 3 2020-21
Estimated to be completed after publication date and before 30 June 2019 | Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Bacchus Marsh College 2016-17 (Bacchus Marsh) | 4144 | 3522 | qtr 1 2020-21
TEI includes co-contribution from the school.
Beaufort Secondary College 2015-16 (Beaufort) | 5000 | 4899 | qtr 2 2020-21
Bentleigh Secondary College 2015-16 (Bentleigh East) | 9600 | 8160 | qtr 1 2020-21
Branxholme-Wallacedale Community School 2017-18 (Branxholme) | 352 | 298 | qtr 3 2020-21
Bundoora Primary School 2017-18 (Bundoora) | 3559 | 3543 | qtr 3 2020-21
TEI includes co-contribution from the school.
Camberwell High School 2016-17 (Canterbury) | 5292 | 5075 | qtr 1 2020-21
TEI includes co-contribution from the school.
Campbellfield Heights Primary School 2017-18 (Campbellfield) | 402 | 399 | qtr 3 2020-21
Carlton Primary School 2016-17 (Carlton) | 13900 | 11815 | qtr 3 2020-21
Croxton Special School 2016-17 (Northcote) | 5000 | 4976 | qtr 2 2020-21
Daylesford Secondary College 2015-16 (Daylesford) | 10000 | 8930 | qtr 1 2020-21
Dimboola Primary School 2017-18 (Dimboola) | 472 | 401 | qtr 3 2020-21
Docklands Primary School 2018-19 – Stage 1 (Docklands) | 18800 | 15778 | qtr 3 2020-21
TEI includes co-contribution from Victorian State Government entities.
Fawkner Primary School 2017-18 (Fawkner) | 352 | 322 | qtr 3 2020-21
Heatherwood School 2016-17 (Donvale) | 5371 | 4566 | qtr 2 2020-21
TEI includes co-contribution from the school.
Highvale Primary School 2017-18 (Glen Waverley) | 603 | 599 | qtr 3 2020-21
Hughesdale Primary School 2017-18 (Hughesdale) | 3656 | 3333 | qtr 3 2020-21
TEI includes co-contribution from the school.
Irymple Secondary College 2016-17 (Irymple) | 7000 | 6917 | qtr 2 2020-21
Kyneton Secondary College 2015-16 (Kyneton) | 5000 | 4250 | qtr 3 2020-21
Laharum Primary School 2017-18 (Laharum) | 472 | 470 | qtr 3 2020-21
Lara Lake Primary School 2017-18 (Lara Lake) | 1809 | 1594 | qtr 1 2021-22
Lilydale Primary School 2017-18 (Lilydale) | 804 | 639 | qtr 4 2020-21
Lynall Hall Community School and Richmond High School 2017-18 (Richmond) | 3039 | 2584 | qtr 3 2020-21
TEI includes co-contribution from the school.
McKinnon Secondary College 2018-19 – Stage 1 (East Bentleigh) | 4100 | 3075 | qtr 3 2020-21
Melton Specialist School 2016-17 (Melton) | 5401 | 4591 | qtr 1 2020-21
TEI includes co-contribution from the school.
Mooroopna Park Primary School 2017-18 (Mooroopna) | 322 | 274 | qtr 3 2020-21
TEI includes co-contribution from the school.
Moriac Primary School 2018-19 – Stage 2 (Moriac) | 500 | 450 | qtr 3 2020-21
Mount Macedon Primary School 2017-18 (Mount Macedon) | 492 | 418 | qtr 3 2020-21
TEI includes co-contribution from the school.
North Geelong Secondary College 2016-17 (North Geelong) | 4375 | 3719 | qtr 2 2020-21
TEI includes co-contribution from the school.
Relocatable Building Program 2018-19 (statewide) | 84270 | 71630 | qtr 3 2020-21
TEI includes co-contribution from Victorian State Government entities.
Richmond High School 2016-17 (Richmond) | 41461 | 35242 | qtr 1 2020-21
TEI includes co-contribution from non-government organisations and reclassification of some costs as operating expenditure.
Strathmore Primary School 2015-16 (Strathmore) | 5700 | 4845 | qtr 3 2020-21
Sunshine College 2015-16 (Sunshine) | 10000 | 8500 | qtr 3 2020-21
Sunshine Special Development School 2016-17 (Sunshine) | 3055 | 2597 | qtr 1 2020-21
TEI includes co-contribution from the school.
Victorian School Asbestos Program 2018-19 (statewide) | 45000 | 38250 | qtr 3 2020-21
Department of Environment Land Water and Planning
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Creating a Ring of New Parkland in Our Growing Suburbs | 74300 | 0 | 7325 | 66975 | qtr 4 2022- 23
Funds will be held in central contingency with the allocation subject to approval by government.
Historic Boost for camping in Victoria’s Great Outdoors (statewide) | 70420 | 0 | 17605 | 52815 | qtr 4 2022- 23
Managing Bushfire Risk (statewide) | 12543 | 0 | 8113 | 4430 | qtr 4 2022- 23
Next steps in reimagining Melbourne's iconic waterways (metro various) | 2000 | 0 | 2000 | 0 | qtr 4 2019- 20
Protecting the future of Hanging Rock (Woodend) | 1400 | 0 | 1400 | 0 | qtr 4 2019- 20
Total new projects | 160663 | 0 | 36443 | 124220
Source: Department of Environment Land Water and Planning
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Bringing our Environment Protection Authority into the modern era (statewide) | 18451 | 9601 | 8150 | 700 | qtr 4 2020- 21
Climate ready Victorian infrastructure – critical coastal protection assets (statewide) | 15000 | 9187 | 3750 | 2063 | qtr 4 2020-21
The project completion date has been revised to reflect the updated project schedule.
Enhancing Victoria’s liveability through improvements to the parks and reserves estate (statewide) | 21504 | 1504 | 8000 | 12000 | qtr 4 2022- 23
Melbourne strategic assessment (metropolitan various) | 330900 | 36914.3 | 10000 | 283985.7 | qtr 2 2053- 54
Non-potable irrigation water for Melbourne Gardens (metropolitan various) | 3713 | 1379 | 2334 | 0 | qtr 4 2019- 20
National Water Sports Centre and Melbourne Cable Park infrastructure upgrades (metropolitan various) | 3000 | 2250 | 750 | 0 | qtr 4 2019- 20
The project cash flow has been revised in line with the updated project schedule.
Providing planning certainty for managed growth (statewide) | 8000 | 0 | 8000 | 0 | qtr 4 2019- 20
Recycled irrigation water for Cranbourne Gardens (Cranbourne) | 3250 | 2600 | 650 | 0 | qtr 4 2019- 20
Reducing bushfire risk (statewide) | 44000 | 22000 | 11000 | 11000 | qtr 4 2020- 21
Revitalising Central Geelong (Geelong) | 3261 | 300 | 2961 | 0 | qtr 4 2019- 20
The project completion date has been revised to reflect the anticipated timing of property settlement. The TEI includes $0.500m from the City of Greater Geelong.
Revitalising infrastructure in the State’s parks estate (statewide) | 20000 | 15000 | 5000 | 0 | qtr 4 2019- 20
Securing the benefits of parks for all Victorians (statewide) | 13000 | 3250 | 3250 | 6500 | qtr 4 2021- 22
Walking together – A partnership to improve community connection and access to country (statewide) | 750 | 150 | 150 | 450 | qtr 4 2021- 22
Water for Victoria – Entitlements and planning (statewide) | 8200 | 4700 | 3500 | 0 | qtr 4 2019- 20
Water security for East Grampians (Grampians) | 32000 | 10000 | 17000 | 5000 | qtr 4 2020- 21
Water Security for Mitiamo (Mitiamo) | 10200 | 200 | 10000 | 0 | qtr 4 2019- 20
Total existing projects | 535229 | 119035.3 | 94495 | 321698.7
Total Environment Land Water and Planning projects | 695892 | 119035 | 130938 | 445919
Other capital expenditure | na | na | 12564 | na | various
Total 2019-20 Environment Land Water and Planning capital expenditure |  |  | 143508.996
Source: Department of Environment Land Water and Planning
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Estimated to be completed after publication date and before 30 June 2019
Establishment of Land Use Victoria (metropolitan various) | 6458.1 | 6458.1 | qtr 4 2018- 19
Land acquisition at Jacksons Hill (Sunbury) | 20000 | 20000 | qtr 4 2018- 19
National Water Infrastructure Development Fund – National Partnership Agreement (regional various) | 39000 | 39000 | qtr 4 2018- 19
The project is funded by the Commonwealth.
New facilities for parks and reserves (statewide) | 5000 | 5000 | qtr 4 2018- 19
New Parks and Open Space for suburban Melbourne (metropolitan various) | 2100 | 2100 | qtr 4 2018- 19
Project name changed from ’Improving the Olinda Precinct’.
Reforming Local Government Planning (statewide) | 4926 | 4926 | qtr 4 2018- 19
Sports and recreation opportunities in our parks (metropolitan various) | 18350 | 18350 | qtr 4 2018- 19
The project was reported last year as completed project under ’Other Public Non-Financial Corporations’. The TEI has increased by $12.350 million to include a transfer of funding from the Department of Health and Human Services for this project.
Strengthening the protection of our forests and wildlife through more effective regulation, compliance and enforcement (statewide) | 4348 | 4348 | qtr 4 2018- 19
The TEI has been revised from $6.000 million to $4.348 million. The decrease is the result of $1.652 million reclassified to output.
Upgrade Land Victoria’s property administration systems (metropolitan various) | 17366 | 17366 | qtr 4 2018- 19
The TEI has been revised from $35.081 million to $17.366 million due to the commercialisation of Land Use Victoria. The estimated completion date has been revised to quarter 4, 2018-19.
Source: Department of Environment Land Water and Planning
Department of Health and Human Services
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
A proudly multicultural Victoria – aged care (statewide) | 21750 | .. | 200 | 21550 | qtr 4 2020- 21
Building a better hospital for Melbourne’s inner west (Footscray) | 1495000 | 0 | tbc | tbc | qtr 4 2024- 25
Cash flows to be confirmed. TEI includes $65 million provided in previous budgets and excludes financing costs.
Building a new rehabilitation centre for Bendigo (Bendigo) | 59500 | 0 | 3133 | 56367 | qtr 4 2022- 23
Building a world class hospital for Frankston families (Frankston) | 6000 | 0 | 6000 | 0 | qtr 4 2019- 20
World-class care for Wangaratta patients (Wangaratta) | 2400 | 0 | 1200 | 1200 | qtr 4 2019- 20
Ten new community hospitals to give patients the best care (statewide) | 2000 | 0 | 2000 | 0 | qtr 4 2019- 20
Priority will be given to acquire land at Phillip Island.
Clinical technology refresh 2019-20 (statewide) | 13000 | 0 | 13000 | 0 | qtr 4 2019- 20
Engineering infrastructure and medical equipment replacement program 2019-20 (statewide) | 60000 | 0 | 60000 | 0 | qtr 4 2019- 20
Relocation of Barwon Health clinical facilities (Geelong) | 20000 | 0 | 2000 | 18000 | qtr 4 2023- 24
Building a Bigger and Better Latrobe Regional Hospital (Traralgon) | 7000 | 0 | 7000 | 0 | qtr 4 2019- 20
More help for Victorian mums and dads (statewide) | 123000 | .. | 9225 | 113775 | qtr 2 2023-24
Planning for new Children’s Emergency Departments (statewide) | 5940 | 0 | 2970 | 2970 | qtr 4 2019- 20
Planning for the Angliss Hospital expansion (Upper Ferntree Gully) | 4556 | 0 | 86 | 4470 | qtr 4 2022- 23
Backing our paramedics to keep saving lives (statewide) | 54900 | 0 | 8000 | 46900 | qtr 4 2022- 23
Regional Health Infrastructure Fund 2019-20 (regional various) | 100000 | 0 | 50000 | 50000 | qtr 4 2020- 21
Royal Children’s Hospital expansion (Parkville) | 31400 | 0 | 7000 | 24400 | qtr 4 2021- 22
Rural residential aged care facilities renewal 2019-20 | 10000 | 0 | 10000 | 0 | qtr 4 2019- 20
This project is funded from the Regional Health Infrastructure Fund and not included in the totals.
Wantirna Aged Care Redevelopment (Wantirna) | 81580 | 0 | 6000 | 75580 | qtr 4 2022- 23
Total new projects | 2088026 | 0 | 177814 | 415212
Source: Department of Health and Human Services
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Ambulance Station Upgrades 2015-16 (statewide) | 20000 | 18749.7 | 1250 | 0 | qtr 2 2020- 21
The project’s cashflow has been revised in line with a revised project schedule.
Ambulance Victoria Station Upgrades 2016-17 (statewide) | 20000 | 7766 | 7234 | 5000 | qtr 1 2021- 22
The project’s cashflow has been revised in line with a revised project schedule.
Austin Health – critical infrastructure works (Heidelberg) | 70616 | 54128 | 16488 | 0 | qtr 4 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Ballarat Health Services expansion and redevelopment (Ballarat) | 461600 | 800 | 5800 | 455000 | qtr 4 2025- 26
Barwon Health – North (Geelong) | 33080 | 24416 | 8664 | 0 | qtr 1 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Casey Hospital Expansion (Berwick) | 139780 | 120277 | 19503 | 0 | qtr 4 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Engineering infrastructure replacement program (statewide) | 50000 | 47011.6 | 2988 | 0 | qtr 2 2019- 20
This initiative combines programs funded in the 2017-18 Budget and the 2018-19 Budget. The project’s cashflow has been revised in line with a revised project schedule.
Establishing Support and Safety Hubs (statewide) | 80812 | 30173 | 16237 | 34402 | qtr 4 2020- 21
The project’s TEI has increased by $14.534 million due to the redirection of project output funding for capital purposes.
Family violence information sharing system reform (statewide) | 39187 | 8126 | 31061 | 0 | qtr 4 2019-20
Fixated Threat Assessment Centre (statewide) | 1500 | 750 | 750 | 0 | qtr 4 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Forensic Mental Health Bed-based Services Expansion (Fairfield) | 40000 | 3275 | 20000 | 16725 | qtr 4 2019- 20
Cashflow has been revised in line with a revised project schedule.
Forensic mental health implementation plan – priority service reforms (Fairfield) | 5942 | 875.8 | 5066 | 0 | qtr 4 2019- 20
The project has received additional funding and the TEI has increased from $3.900 million to support additional work that was identified to improve the Orygen Youth Health intensive care area. The cashflow has been revised in line with a new project schedule.
Getting Ready for the National Disability Insurance Scheme (statewide) | 25383 | 17641 | 7742 | 0 | qtr 4 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Goulburn Valley Health redevelopment – planning and development (Shepparton) | 171234 | 63349 | 80136 | 27749 | qtr 4 2020- 21
The project’s cashflow has been revised in line with a revised project schedule.
Grampians Prevention and Recovery Care (PARC) Services (Ballarat) | 6000 | 647 | 4553 | 800 | qtr 4 2020- 21
The project’s cashflow has been revised in line with a revised project schedule.
Health Service Violence Prevention Fund (statewide) | 20000 | 19507.2 | 493 | 0 | qtr 2 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Joan Kirner Women’s and Children’s Hospital (St Albans) | 200000 | 184897 | 15103 | 0 | qtr 4 2019- 20
The project’s cashflow has been revised in line with a revised project schedule. Construction of the hospital is now complete and is scheduled to open in May 2019.
Medical equipment replacement program (statewide) | 70000 | 63765.4 | 6235 | 0 | qtr 2 2019- 20
The project’s cashflow has been revised in line with a revised project schedule. Initiative combines programs funded in the 2017-18 Budget and 2018-19 Budget.
Meeting Ambulance Response Times (statewide) | 69386 | 34272 | 5000 | 30114 | qtr 4 2019-20
The project’s cashflow has been revised in line with a revised project schedule.
Mental Health & alcohol and other drugs facilities renewal 2017-18 (statewide) | 10000 | 7200 | 2800 | 0 | qtr 2 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Mental Health & alcohol and other drugs facilities renewal 2018-19 (statewide) | 10000 | 2300 | 7700 | 0 | qtr 2 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Modernisation of metro public sector residential aged care (Kew) | 57570 | 29686.4 | 24498 | 3385.6 | qtr 2 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Monash Medical Centre – Expansion and upgrades (Clayton) | 71000 | 4457 | 28000 | 38543 | qtr 4 2021- 22
The project’s TEI has increased from $63.200 million in last year’s budget due to changes to project scope.
Monash Medical Centre – infrastructure upgrades (Clayton) | 12799 | 4920 | 5000 | 2879 | qtr 4 2020- 21
The project’s cashflow has been revised in line with a revised project schedule.
New Regional Alcohol and Drug Residential Rehabilitation Facilities (regional various) | 40600 | 0 | 10000 | 30600 | qtr 4 2020- 21
The project’s cashflow has been revised in line with a revised project schedule.
Northern Hospital inpatient expansion – Stage 2 (Epping) | 162672 | 26268 | 50000 | 86404 | qtr 1 2021- 22
The project’s cashflow has been revised in line with a revised project schedule.
Out-of-home care residential capacity (statewide) | 8000 | 2723 | 5277 | 0 | qtr 4 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Redesign and renovation of out-of-home care properties (statewide) | 6270 | 4815 | 1455 | 0 | qtr 2 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Reforming clinical mental health services (Melbourne) | 40000 | 789 | 12711 | 26500 | qtr 4 2022- 23
The project’s TEI has been reduced by $8.100 million due to internal reprioritisation. The cashflow has been revised in line with a revised project schedule.
Regional Health Infrastructure Fund (regional various) | 250000 | 176291.9 | 73708 | 0 | qtr 4 2019- 20
The project’s TEI has been revised to reflect the additional funding of $50 million provided in the 2018-19 Budget. The cashflow has been revised in line with a revised project schedule.
Royal Melbourne Hospital – critical infrastructure works (Parkville) | 40000 | 16811 | 11439 | 11750 | qtr 4 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Royal Victorian Eye and Ear Hospital redevelopment (Melbourne) | 274557 | 199588 | 61939 | 13030 | qtr 2 2021- 22
The project’s TEI has increased to reflect the additional joint funding between the department and the Royal Victorian Eye and Ear Hospital. The cashflow has been revised in line with a revised project schedule.
Safe Digital Clinical Systems - Parkville Precinct EMR (Parkville) | 123800 | 12222 | 59236.6 | 52341.4 | qtr 4 2020- 21
Project name changed from Electronic medical records in Parkville (Parkville) published in the 2018-19 budget papers.
Statewide Child and Family Mental Health Intensive Treatment Centre (statewide) | 7300 | 55 | 4000 | 3245 | qtr 4 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Sunshine Hospital Emergency Department (St Albans) | 29600 | 500 | 14400 | 14700 | qtr 4 2021- 22
The project’s cashflow has been revised in line with a revised project schedule.
Supporting demand for ambulance services (statewide) | 3345 | 650 | 2695 | 0 | qtr 2 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
The Alfred Hospital urgent infrastructure (Prahran) | 69500 | 1500 | 10000 | 58000 | qtr 4 2023- 24
The project’s cashflow has been revised in line with a revised project schedule.
Footscray Hospital – planning and critical infrastructure (Footscray) | 15000 | 6777 | 8223 | 0 | qtr 4 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Victorian Heart Hospital (Clayton) | 564000 | 71772.7 | 72227 | 420000.3 | qtr 2 2022- 23
The project’s TEI has increased by $21.000 million to reflect change design requirements by Monash University. The cashflow has been revised in line with a new project schedule.
Western Health Urgent Infrastructure Works (Footscray and Sunshine) | 61335 | 27808 | 16803 | 16724 | qtr 4 2020- 21
The project’s cashflow has been revised in line with a revised project schedule.
Women’s Prevention and Recovery Care (PARC) Service (metropolitan various) | 8400 | 478.3 | 5563 | 2358.7 | qtr 4 2019- 20
The project’s cashflow has been revised in line with a revised project schedule.
Wonthaggi Hospital emergency department expansion (Wonthaggi) | 115000 | 2000 | 30000 | 83000 | qtr 4 2022- 23
Youth Prevention and Recovery Care Service (metropolitan Melbourne) | 11900 | 30 | 4970 | 6900 | qtr 1 2020- 21
The project’s cashflow has been revised in line with a revised project schedule.
Total existing projects | 3517168 | 1300069 | 776947.6 | 1440151
Total Health and Human Services projects | 5605194 | 1300069 | 954761.6 | 1855363
Other capital expenditure | na | na | 176911.695 | na | various
Total 2019-20 Health and Human Services capital expenditure |  |  | 1131673.295
Source: Department of Health and Human Services
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Alcohol and Drug Residential Rehabilitation Services – Stage 1 (Grampians) | 6000 | 5840.7 | qtr 2 2018- 19
The project’s cashflow has been revised in line with a revised project schedule.
Increasing critical care capacity 2017-18 (statewide) | 2200 | 2200 | qtr 4 2018- 19
Level 13 Fitout Victorian Comprehensive Cancer Centre (Melbourne) | 11985 | 11985 | qtr 4 2018- 19
Rapid expansion of residential rehabilitation (statewide) | 8300 | 8300 | qtr 4 2018- 19
Estimated to be completed after publication date and before 30 June 2019
Angliss Hospital intensive care unit and short stay unit (Upper Ferntree Gully) | 20000 | 19521 | qtr 4 2018- 19
The project’s cashflow has been revised in line with a revised project schedule.
Cladding rectification works (statewide) | 10000 | 10000 | qtr 4 2018- 19
Clinical Technology Refresh (statewide) | 12000 | 12000 | qtr 4 2018- 19
Establishment of an Aboriginal-led community facility (Latrobe) | 2000 | 2000 | qtr 4 2018- 19
Geelong Hospital – major upgrade (Geelong) | 118170 | 114362 | qtr 4 2018- 19
The project’s cashflow has been revised in line with a revised project schedule.
Homelessness and rough sleeping action plan (statewide) | 2200 | 2200 | qtr 4 2018- 19
The project’s cashflow has been revised in line with a revised project schedule.
Increasing critical care capacity 2018-19 (statewide) | 2500 | 2500 | qtr 4 2018- 19
Maroondah Breast Cancer Centre (East Ringwood) | 9687 | 9686.8 | qtr 4 2018- 19
TEI is lower than published in 2018-19 budget papers to reflect actual project expenditure.
Medically supervised injecting room (Richmond) | 2035 | 2610 | qtr 4 2018- 19
Meeting demand for health services (statewide) | 2500 | 2500
Olivia Newton-John Cancer Wellness and Research Centre (Heidelberg) | 7250 | 7250 | qtr 4 2018- 19
This project was announced after the 2018-19 Budget and therefore did not appear in the 2018-19 Budget.
Orygen Youth Mental Health (Parkville) | 65000 | 56501 | qtr 4 2018- 19
The project’s cashflow has been revised in line with a revised project schedule.
Thomas Embling Hospital expansion (Fairfield) | 23343 | 21534 | qtr 4 2018- 19
The project’s TEI has increased by $4.000 million compared to last year’s budget papers due to two new additional female bedrooms. The cashflow has been revised in line with a revised project schedule.
Werribee Mercy Hospital – acute expansion (Werribee) | 85000 | 82062 | qtr 4 2018- 19
The project’s cashflow has been revised in line with a revised project schedule.
Source: Department of Health and Human Services
Department of Jobs Precincts and Regions
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Creative Victoria Cultural Facilities Maintenance Fund (statewide) | 5000 | 0 | 5000 | .. | qtr 4 2019-20
Exhibition and experience program renewal – Museums Victoria (statewide) | 4500 | 0 | 4500 | .. | qtr 4 2019-20
Regional Development in Victoria (regional various) | 40600 | 0 | 10150 | 30450 | qtr 4 2022-23
Victoria: The Basketball Capital of Australia – Melbourne Arena Upgrade (Melbourne) | 13000 | 0 | 6500 | 6500 | qtr 4 2020-21
Total new projects | 63100 | 0 | 26150 | 36950
Source: Department of Jobs Precincts and Regions
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Arts And Cultural Facilities Maintenance Fund (statewide) | 9980 | 9680 | 300 | 0 | qtr 4 2019-20
TEI reduced by $6.796 million due to conversion of funding to output for maintenance works.
Australian Centre for the Moving Image redevelopment (Melbourne) | 39804 | 9518 | 30286 | 0 | qtr 4 2019-20
This includes $5.000 million of funding from other sources.
Ballarat GovHub (Ballarat) | 19340 | 0 | 14220 | 5120 | qtr 4 2020-21
Bendigo GovHub (Bendigo) | 16000 | 0 | 2750 | 13250 | qtr 4 2021-22
Geelong City Deal (Geelong) | 312316 | 4600 | 37793 | 269923 | qtr 4 2021-23
This is the Victorian and Commonwealth Government’s share of the Geelong City Deal. Delays in expenditure partially due to negotiations with Commonwealth.
Latrobe Valley GovHub (Morwell) | 3000 | 0 | 3000 | 0 | qtr 4 2019-20
The estimated completion date has been revised.
Lysterfield Lake Park – Land Purchase (Lysterfield) | 3000 | 2040 | 60 | 900 | qtr 4 2035-36
Modernising Earth Resources Management (statewide) | 2197 | 1797 | 400 | 0 | qtr 2 2019-20
The TEI and estimated completion date has been revised.
Melbourne Arts Precinct transformation (Melbourne) | 101500 | 26738 | 72762 | 2000 | qtr 4 2020-21
This project incorporates the Reimagining Arts Centre Melbourne project and the National Gallery of Victoria Contemporary initiative. This project also incorporates the previously published Arts Centre Melbourne critical works project.
Royal Exhibition Building Protection and Promotion Project (Carlton) | 20000 | 19000 | 1000 | 0 | qtr 2 2019-20
The estimated completion date has been revised.
Sports and recreation opportunities in our parks (metropolitan various) | 15350 | 13600 | 1750 | 0 | qtr 4 2019-20
The estimated completion date has been revised.
State Library of Victoria redevelopment (Melbourne) | 95100 | 82913 | 12167 | 20 | qtr 4 2020-21
The TEI reflects a revised project scope.
Total existing projects | 637587 | 169886 | 176488 | 291213
Total Jobs Precincts and Regions projects | 700687 | 169886 | 202638 | 328163
Other capital expenditure | na | na | -42287.337 | na | various
Other capital expenditure includes projects being undertaken in the Department of Jobs, Precincts and Regions funded through the Department, as well as investment to maintain and upgrade the existing asset base. This is offset by factors including funding held in contingency pending confirmation of project implementation planning and funding from other sources.
Total 2019-20 Jobs Precincts and Regions capital expenditure |  |  | 160350.663
Source: Department of Jobs Precincts and Regions
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Collections Storage Victoria – Phase 1 (statewide) | 21480 | 21480 | qtr 2 2018-19
Museum Victoria Exhibition Renewal (Carlton) | 18000 | 18000 | qtr 4 2018-19
Melbourne Exhibition Centre Stage 2 Development (Southbank) | 168700 | 168700 | qtr 1 2018 -19
The estimated completion date has been revised. TEI reflects the state capital construction component only.
Parkville Gardens (Commonwealth Games Village) – social housing component – Construction (Parkville) | 31918.954 | 31918.954 | qtr 2 2018 -19
Revised TEI due to projects’ self-funded revenue model.
Estimated to be completed after publication date and before 30 June 2019
Ballarat West Employment Zone (Ballarat) | 30169 | 30169 | qtr 4 2019-20
Guaranteeing Victoria’s food export future – BioSecurity (statewide) | 4867 | 4867 | qtr 4 2018-19
The estimated completion date has been revised.
Supporting Victorian small businesses (statewide) | 500 | 500 | qtr 4 2018-19
Source: Department of Jobs Precincts and Regions
Department of Justice and Community Safety
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Improving Court access through additional audio-visual technology (statewide) | 1685 | 0 | 456 | 1229 | qtr 4 2022-23
Men’s prison system capacity (statewide) | 1255372 | 37000 | 489454 | 728918 | qtr 4 2022-23
Road safety package - new road safety camera infrastructure and safety campaign (statewide) | 32129 | 0 | 5722 | 26407 | qtr 4 2022-23
Establishing a National Disability Insurance Scheme worker screening service (statewide) | 1500 | 1500 | 0 | 0 | qtr 4 2018-19
Victorian State Emergency Service facilities (statewide) | 21100 | 0 | 21100 | 0 | qtr 4 2019-20
Women’s prison system capacity (statewide) | 188900 | 0 | 15000 | 173900 | qtr 4 2021-22
Total new projects | 1500686 | 38500 | 531732 | 930454
Source: Department of Justice and Community Safety
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Additional drug tests on our roads (statewide) | 5503 | 2151 | 3352 | 0 | qtr 4 2019-20
This initiative is funded by the Transport Accident Commission. Cash flow has been revised in line with a revised project schedule.
Chisholm Road prison project (Chisholm Road) | 689450 | 36199 | 253036 | 400215 | qtr 4 2021-22
Previously known as Lara Prison precinct expansion published in 2018-19 budget papers. Cash flow has been revised in line with a revised project schedule.
Community Corrections – Contributing to a Safer Community (statewide) | 65796 | 44396 | 16711 | 4689 | qtr 4 2020-21
Cash flow has been revised in line with a revised project schedule.
Community Safety Statement (statewide) | 327564 | 126506 | 130296 | 70762 | various
TEI has been revised due to changes in project scope, with additional resources allocated to police operations.
Critical Infrastructure and Services – Supporting Recent Prison Expansion (statewide) | 66298 | 64198 | 2100 | 0 | qtr 1 2020-21
TEI, cash flow and timing has been revised in line with a revised project schedule and change to scope.
Critical Police Equipment and Training (statewide) | 1146 | 0 | 1146 | 0 | qtr 4 2019-20
Cash flow and timing has been revised in line with a revised project schedule.
Critical Police Stations (statewide) | 19100 | 18753 | 347 | 0 | qtr 4 2019-20
Emergency services high-priority infrastructure (statewide) | 33411 | 9289 | 14409 | 9713 | qtr 4 2020-21
TEI funding includes the Victorian State Emergency Services headquarters and critical assets initiative and the Victoria State Emergency Services Northcote Unit relocation. The estimated completion date and cash flow has been revised in line with a revised project scope.
Engineers registration scheme (statewide) | 610 | 0 | 310 | 300 | qtr 4 2020-21
Cash flow and timing has been revised in line with a revised project schedule.
Essential services to manage growth in prisons (statewide) | 74252 | 34320 | 39932 | 0 | qtr 4 2019-20
Cash flow has been revised in line with a revised project schedule.
ESTA baseline funding (statewide) | 14496 | 6213 | 8283 | 0 | qtr 4 2019-20
Cash flow has been revised in line with a revised project schedule.
Forensic mental health implementation plan: Priority service reforms (statewide) | 684 | 181 | 362 | 141 | qtr 4 2020-21
This initiative is led by the Department of Health and Human Services and relates to the DJCS and Victoria Police components only. Cash flow and timing has been revised in line with a revised project schedule.
Future emergency alert (statewide) | 7699 | 3729 | 3970 | 0 | qtr 4 2019-20
TEI has increased by $3.235 million due to additional government funding approval after the 2018-19 Budget. Cash flow and timing has been revised in line with a revised project schedule.
Improved regulation of Victoria’s gambling and liquor industries (statewide) | 1600 | 1005 | 595 | 0 | qtr 4 2019-20
Cash flow has been revised in line with a revised project schedule.
Infringement Management and Services (IMES) Reform Project IT solution (statewide) | 63335 | 63335 | 0 | 0 | qtr 4 2019-20
Project was previously published as forecast to be completed by 30 June 2018, however project delivery has continued in 2018-19 with a revised TEI.
Mental Health for emergency services personnel and volunteers (statewide) | 1000 | 0 | 500 | 500 | qtr 4 2020-21
Cash flow and timing has been revised in line with a revised project schedule.
Mobile camera replacement program (statewide) | 17061 | 5661 | 11400 | 0 | qtr 4 2019-20
Cash flow and timing has been revised in line with a revised project schedule.
Mobile Police Stations (statewide) | 5000 | 1000 | 1000 | 3000 | qtr 4 2021-22
New youth justice facility (Cherry Creek) | 278409 | 41228 | 147181 | 90000 | qtr 4 2020 -21
Police Prosecutors (statewide) | 2830 | 234 | 2596 | 0 | qtr 4 2019-20
Prison capacity expansion (Melbourne) | 124356 | 73329 | 50027 | 1000 | qtr 2 2020-21
TEI, cash flow and timing has been revised in line with a revised project scope.
Prison system capacity expansion and security upgrades (Melbourne) | 23004 | 12205 | 10799 | 0 | qtr 4 2019-20
Cash flow has been revised in line with a revised project schedule.
Public Safety – Police Response (statewide) | 121956 | 117807 | 4149 | 0 | various
Public Safety – Regional and Rural Police Stations (statewide) | 31010 | 30610 | 400 | 0 | qtr 1 2019-20
Cash flow has been revised in line with a revised project schedule.
Remediation of connectivity in emergency services operational communications (statewide) | 6288 | 3144 | 3144 | 0 | qtr 4 2019-20
State Emergency Communication Centre (metropolitan) | 24300 | 8422 | 13910 | 1968 | qtr 4 2020-21
Cash flow has been revised in line with a revised project schedule.
Strengthening of youth justice precincts (statewide) | 56106 | 44039 | 12067 | 0 | qtr 4 2019-20
The project completion date has been revised to reflect revised project scope.
Targeting Organised Crime and Cyber Criminals (statewide) | 2319 | 2310 | 9 | 0 | qtr 4 2019-20
Victorian State Emergency Services critical assets (statewide) | 4457 | 2400 | 2057 | 0 | qtr 4 2019-20
Project name changed from Victorian State Emergency Services headquarters and critical assets published in 2018-19 budget papers. TEI, cashflow and schedule has changed due to consolidation of headquarters and other projects under the project management of high-priority infrastructure.
Volunteer marine search and rescue (Melbourne) | 6590 | 3295 | 3295 | 0 | qtr 1 2019-20
Cash flow and timing has been revised in line with a revised project schedule.
Total existing projects | 2075630 | 755959 | 737383 | 582288
Total Justice and Community Safety projects | 3576316 | 794459 | 1269115 | 1512742
Other capital expenditure | na | na | -255920.8286 | na | various
Other capital expenditure includes ongoing replacement of operating equipment, vehicles and facilities. This is offset by funding held in contingency pending confirmation of project schedule
Total 2019-20 Justice and Community Safety capital expenditure |  |  | 1013194.1714
Source: Department of Justice and Community Safety
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Management of serious sex offenders (regional various) (statewide) | 52530 | 52530 | qtr 4 2018- 19
TEI has reduced due to $0.250 million redirection to the Corrections System Capacity initiative.
New booze and drug buses (statewide) | 11180 | 11180 | qtr 4 2018- 19
Estimated to be completed after publication date and before 30 June 2019
Australian Communications and Media Authority compliance (statewide) | 1361 | 1361 | qtr 4 2018- 19
TEI has reduced to $1.361 million with $1.967 million transferred to output funding for contracted service payments.
Corrections System Capacity (Melbourne) | 7180 | 7180 | qtr 4 2019- 20
This project was approved after the publication of the 2018-19 budget papers and is expected to be completed by 30 June 2019. TEI includes funding redirection from the Critical Infrastructure and Services – Supporting Recent Prison Expansion, the Management of Serious Offenders, Corrections Remand Upgrades initiative and the departmental annual provision.
Management of serious offenders (statewide) | 26680 | 25457 | qtr 4 2019- 20
TEI has reduced due to $2.500 million having been redirected to the Prison Capacity Expansion initiative.
Melbourne CBD security measures (East Melbourne) | 4178 | 4178 | qtr 4 2018- 19
Sustainable public advocate services for Victorians with a disability (Carlton) | 331 | 331 | qtr 4 2018- 19
Women’s prison capacity strategy (statewide) | 91572 | 91572 | qtr 4 2019- 20
Youth Justice secure bed expansion (metropolitan various) | 79562 | 79562 | qtr 4 2019- 20
Source: Department of Justice and Community Safety
Department of Premier and Cabinet
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Addressing the security and workplace requirements of government buildings (Melbourne) | 400 | 400 | .. | .. | qtr 4 2018-19
Best practice integrity oversight (Melbourne) | 491 | 431 | 29 | 31 | qtr 4 2020-21
Total new projects | 891 | 831 | 29 | 31
Source: Department of Premier and Cabinet
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Public Record Office Victoria asset maintenance and renewal program (North Melbourne) | 3618 | 2618 | 1000 | .. | qtr 4 2019-20
The estimated completion date has been revised.
Security and building upgrades for government buildings (Melbourne) | 13559 | 10899 | 2660 | .. | qtr 4 2019-20
TEI includes funding provided for security and building upgrades in the 2017-18 and 2018-19 Budget.
Enhancing public sector capability (Melbourne) | 1380 | 980 | 400 | .. | qtr 4 2019-20
The estimated completion date has been revised.
Total existing projects | 18557 | 14497 | 4060 | ..
Total Premier and Cabinet projects | 19448 | 15328 | 4089 | 31
Other capital expenditure | na | na | 10103.219 | na | various
Total 2019-20 Premier and Cabinet capital expenditure |  |  | 14192.219
Source: Department of Premier and Cabinet
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Estimated to be completed after publication date and before 30 June 2019
Public Record Office Victoria digital archive (North Melbourne) | 4062 | 4062 | qtr 4 2018-19
Source: Department of Premier and Cabinet
Department of Transport
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
75 by 2025 (Level Crossing Removal) (metropolitan various) | 6550000 | 0 | 230021 | 6319979 | qtr 2 2025-26
Barwon Heads Road upgrade (Barwon Heads) | 318300 | 0 | 400 | 317900 | tbc
Better boating fund and free boat ramp launching and parking (statewide) | 39600 | 0 | 27000 | 12600 | tbc
Building a new St Kilda Pier for locals to enjoy (St Kilda) | 50300 | 0 | 851 | 49449 | tbc
Go Fishing Victoria – Target One Million Phase Two (statewide) | 7000 | 0 | 7000 | 0 | tbc
Hall Road Upgrade (Skye) | 169000 | 0 | 400 | 168600 | tbc
Intelligent Transport System asset availability and resilience program (metropolitan various) | 4647 | 0 | 2788 | 1859 | qtr 4 2020-21
Keeping Ballarat Moving (regional various) | 58642 | 0 | 9580 | 49062 | qtr 4 2021-22
Keeping Freight Moving (regional various) | 10894 | 0 | 10444 | 450 | qtr 4 2020-21
TEI includes $5.900 million announced in the 2018-19 Budget.
Local Road and Intersection Upgrades (statewide) | 47320 | 0 | 7100 | 40220 | qtr 4 2022-23
Metropolitan road maintenance (metropolitan various) | 36505 | .. | 12180 | 24325 | qtr 4 2020-21
Narre Warren North Road upgrade (Narre Warren North) | 38300 | 0 | 400 | 37900 | tbc
New bike lanes on St Kilda Road (metropolitan various) | 27300 | 450 | 7292 | 19558 | qtr 4 2022-23
North East Link | 15640286 | tbc | tbc | tbc | qtr 4 2026-27
TEI includes $143.765 million in funding announced in previous budgets and excludes $150.011 million due to certain expenditure being recognised as expensed State costs (rather than capitalised) in accordance with relevant accounting standards. TEI excludes financing costs. Funding profile is not reported at this time due to commercial sensitivity of the live tender process.
Regional road maintenance (regional various) | 67795 | .. | 22620 | 45175 | qtr 4 2020-21
South Road upgrade (Moorabbin) | 30000 | 0 | 400 | 29600 | tbc
Walking and cycling upgrades – Stage 2 (metropolitan various) | 15000 | 0 | 5200 | 9800 | qtr 4 2021-22
Western Port Highway (Skye) | 54300 | 0 | 400 | 53900 | tbc
Total new projects | 23165189 | 450 | 344076 | 7180377
Source: Department of Transport
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Walking and cycling upgrades - Stage 2 (statewide) | 22250 | 1709 | 15441 | 5100 | qtr 4 2020-21
Initiative is funded by the Transport Accident Commission.
Additional Regional Bus Services (regional various) | 3000 | 874 | 2126 | 0 | qtr 4 2019-20
The estimated completion date has been revised to quarter 4 2019-20 to reflect the introduction of new routes and timetable changes on multiple existing routes.
Box Hill to Ringwood Bikeway (metropolitan various) | 14193.2 | 11431.4 | 2462 | 300 | qtr 4 2019-20
The estimated completion date has been revised to quarter 4 2019-20 due to the Laburnum section of the project still to be agreed with key stakeholders.
Bridge strengthening and upgrades (statewide) | 10243 | 6719 | 3524 | 0.1 | qtr 4 2019-20
TEI has been reduced by $5.900 million due to works delivered through the Keeping Freight Moving initiative. The estimated completion date has been revised to quarter 4 2019-20 due to works completed ahead of schedule.
Bridge strengthening for freight efficiency (statewide) | 76599 | 61645.7 | 4039 | 10914.3 | qtr 4 2020-21
TEI includes $32.507 million of Commonwealth funding. The estimated completion date has been extended to quarter 4 2020-21 to meet planning permit conditions.
Building Our Regions (regional various) | 48820 | 44873.1 | 3618.5 | 328 | qtr 4 2019-20
The estimated completion date has been revised to quarter 4 2019-20 due to extended community consultation.
Carrum Promenade revitalisation (metropolitan various) | 49999 | 15581 | 31569 | 2849 | qtr 3 2019-20
TEI excludes $0.001 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards. The estimated completion date has been brought forward to quarter 3 2019-20.
Chandler Highway upgrade (Alphington, Kew) | 100015 | 91800.6 | 7685 | 529.4 | qtr 1 2019-20
The estimated completion date has been revised to quarter 1 2019-20 due to unexpected asbestos.
Continuing Towards Zero (regional various) | 149200 | 6000 | 118201 | 24999 | qtr 4 2020-21
This initiative is funded by the Transport Accident Commission. The estimated completion date has been revised to quarter 4 2020-21 due to extended community engagement.
Darebin Trail – Farm Link Road (Darebin) | 3200 | 265 | 250 | 2685 | qtr 4 2020-21
Drysdale bypass (Drysdale) | 117377 | 66563 | 43503 | 7311 | qtr 4 2019-20
Hallam Road upgrade (Hampton Park) | 53514 | 24985 | 25555 | 2974 | qtr 4 2019-20
TEI has increased by $8.500 million due to market escalation.
Implementation of the Australian Disability Parking Scheme (statewide) | 5955.3 | 3293.3 | 2662 | 0 | qtr 1 2019-20
The estimated completion date has been revised to quarter 1 2019-20 due to extended community engagement on implementation plan.
Kilmore Bypass (Kilmore) | 33270.1 | 13270.1 | 11000 | 9000 | qtr 4 2020-21
The estimated completion date has been revised to quarter 4 2020-21 due to a delay on the implementation of Public Acquisition Overlay.
Level Crossing Removal Program (metropolitan various) | 6759019 | 3958293 | 1015153 | 1785573 | qtr 2 2022-23
TEI includes $151.000 million of Commonwealth funding for Main Road St Albans, and excludes $119.753 million recognised as operating instead of capital in line with accounting standards.
Metropolitan Network Modernisation Program (metropolitan various) | 1392221 | 802075 | 208947.1 | 381198.9 | qtr 2 2022-23
These works comprise a range of network improvements, such as station works, power, signalling and other infrastructure upgrades and future-proofing works, that are being delivered jointly with the Level Crossing Removal Program.
M80 Ring Road upgrade (north and west metropolitan region) | 673077 | 66244 | 52840 | 553993 | qtr 3 2022-23
TEI includes $336.540 million of Commonwealth funding. The estimated completion date has been revised to quarter 3 2022-23 due to procurement timing.
Metro bus service improvements (statewide) | 5349 | 1931 | 2144 | 1274 | qtr 2 2020-21
The estimated completion date has been revised to quarter 2 2020-21 to reflect the procurement of an operator, additional buses and enabling infrastructure works for the Victoria Park-Melbourne University Package.
Metropolitan and regional restoration and maintenance (statewide) | 195200 | 100440 | 92864 | 1896 | qtr 4 2019-20
Monash Freeway upgrade – Stage 2 (South East Melbourne) | 684424 | 35313.3 | 207127 | 441983.7 | qtr 4 2022-23
TEI includes $483.800 million of Commonwealth funding.
Mordialloc Freeway (Braeside) | 375000 | 57650.6 | 209926.7 | 107422.7 | qtr 2 2022-23
More train, tram and bus services (metropolitan various) | 9711 | 3562.3 | 6148.7 | 0 | qtr 4 2019-20
The estimated completion date has been revised to quarter 4 2019-20 to reflect an altered delivery schedule.
MR4 – Enhanced Operating Performance Regime (EOPR) – IT system upgrades (metropolitan various) | 7200 | 3560.7 | 3639.3 | 0 | qtr 4 2019-20
Narrow seal roads program – South Western Victoria (regional various) | 37200 | 25775 | 11425 | 0 | qtr 4 2019-20
Optimising transport network performance – congestion package (statewide) | 102543 | 97385.8 | 4904.6 | 252.6 | qtr 4 2019-20
TEI has increased by $20.083 million due to the complexity of delivering the project scope. The estimated completion date has been revised to quarter 4 2019-20 due to extended community consultation and interface with other projects.
Optimising transport network performance and productivity (metropolitan various) | 27992.8 | 20803.3 | 6240 | 949.5 | qtr 2 2019-20
TEI has increased by $0.192 million to deliver the truck curfew on Beach Road. The estimated completion date has been revised to quarter 2 2019-20 due to rescoping of the project to align with the tram task force outcomes.
Plenty Road upgrade – Stage 2 (South Morang) | 143409 | 11296.9 | 36724 | 95388.1 | qtr 2 2020-21
TEI has increased by $40.000 million due to market escalation. The estimated completion date has been revised to quarter 2 2020-21 due to procurement requirements.
Port-Rail shuttle (metropolitan intermodal system) (metropolitan various) | 58000 | 8297.2 | 37426 | 12276.8 | qtr 4 2020-21
TEI includes $38.000 million of Commonwealth funding.
Princes Highway duplication project – Winchelsea to Colac (regional various) | 349192.6 | 281829.8 | 23300 | 44062.8 | qtr 2 2019-20
TEI includes $181.735 million of Commonwealth funding. The estimated completion date has been revised to quarter 2 2019-20 due to design changes and archaeological discoveries.
Regional and metropolitan road upgrade (statewide) | 33450.1 | 4343 | 19688 | 9419.1 | qtr 4 2020-21
TEI has increased by $2.510m to deliver new heavy vehicle safety and productivity projects. TEI includes $5.350m of Commonwealth funding.
Regional overtaking lanes (regional various) | 48376 | 38719 | 9657 | .. | qtr 4 2019-20
TEI has increased by $0.300 million due to community consultation for the Midland Highway Barjarg overtaking lane project.
Regional road upgrades (regional various) | 42231 | 35062 | 7140 | 29 | qtr 4 2019-20
TEI has increased by $0.625 million. TEI includes $11.160 million of Commonwealth funding.
Road and rail minor works – roads (statewide) | 39617.1 | 38807.6 | 809 | .. | qtr 1 2019-20
The estimated completion date has been revised to quarter 4 2019-20 due to power relocation, extra drainage works and complex ground condition.
Road Safety Strategy 2013-2022 (statewide) | 664091.6 | 564933.3 | 44283 | 54875.3 | qtr 2 2022-23
TEI has reduced by $47.241 million, with $25.000 million transferred to the Road Safety Toward Zero program and $22.241 million to Active Transport program. Initiative is funded by the Transport Accident Commission.
Road Safety Towards Zero (statewide) | 290998.6 | 250955 | 31691 | 8352.6 | qtr 4 2020-21
TEI has increased by $25.000 million due to funding transferred from the Road Safety Strategy 2013-22 (statewide) program. Initiative is funded by the Transport Accident Commission.
Rural and Regional Roads Package | 593548.3 | 205015.9 | 148912 | 239620.4
– Calder Highway upgrade (regional various) | 19231 | 5768 | 5463 | 8000 | qtr 4 2021-22
TEI includes $9.615 million of Commonwealth funding. The estimated completion date has been revised to quarter 4 2021-22 due to the land acquisition process.
– Echuca-Moama bridge (Echuca) | 134903 | 33414 | 32135 | 69354 | qtr 4 2021-22
TEI includes $46.000 million of Commonwealth funding and excludes contribution from New South Wales.
– Forrest-Apollo Bay Road upgrade (regional various) | 9615 | 6615 | 3000 | 0.3 | qtr 4 2019-20
TEI includes $4.807 million of Commonwealth funding.
– Great Alpine Road improvement works (regional various) | 17308.7 | 10237.4 | 5361 | 1710.4 | qtr 4 2020-21
TEI includes $8.654 million of Commonwealth funding. The estimated completion date has been revised to quarter 4 2020-21 to reflect a more accurate schedule of works.
– Great Ocean Road improvement works (Surf Coast) | 48075.9 | 19553 | 10833 | 17689.9 | qtr 4 2021-22
TEI includes $24.038 million of Commonwealth funding.
– Green Triangle Package (south west regional Victoria) | 38461.6 | 31461.6 | 7000 | 0 | qtr 4 2019-20
TEI includes $19.231 million of Commonwealth funding.
– Hyland Highway Road improvement works (Gippsland region) | 9614.2 | 4907.8 | 2960 | 1746.4 | qtr 3 2020-21
TEI includes $4.807 million of Commonwealth funding. The estimated completion date has been revised to quarter 3 2020-21 to reflect a more accurate schedule of works.
– Improving the South Gippsland Highway (Gippsland region) | 48080 | 3766.2 | 13000 | 31313.8 | qtr 4 2021-22
TEI includes $24.040 million of Commonwealth funding. The estimated completion date has been revised to quarter 4 2021-22 due to environmental approvals and subsequent tender award.
– Kiewa Valley Highway (regional various) | 7692 | 3535.1 | 3677 | 479.9 | qtr 2 2020-21
TEI includes $3.846 million of Commonwealth funding.
– Monaro Highway Road improvement works (Gippsland region) | 9614.1 | 6548.3 | 2000 | 1065.8 | qtr 4 2019-20
TEI includes $4.807 million of Commonwealth funding.
– Murray Valley Highway upgrade (regional various) | 19231 | 8316.5 | 10914 | 0.5 | qtr 4 2019-20
TEI includes $9.615 million of Commonwealth funding.
– Phillip Island – Improving the main infrastructure corridor (Phillip Island) | 6731 | 3035 | 2696 | 1000 | qtr 3 2020-21
TEI includes $3.365 million of Commonwealth funding. The estimated completion date has been revised to quarter 3 2020-21 to reflect a more accurate schedule of works.
– Princes Highway East – upgrades east of Sale (Gippsland region) | 48061.8 | 18833 | 14000 | 15228.8 | qtr 4 2020-21
TEI includes $24.031 million of Commonwealth funding. The estimated completion date has been revised to quarter 4 2020-21 to reflect a more accurate schedule of works.
– Princes Highway West upgrades – Colac to South Australia border (regional various) | 38462 | 20061.8 | 9400 | 9000.2 | qtr 3 2020-21
TEI includes $19.231 million of Commonwealth funding.
– Rutherglen alternative truck route (Rutherglen) | 3846 | 697.6 | 500 | 2648 | qtr 4 2020-21
TEI includes $1.923 million of Commonwealth funding.
– Shepparton heavy vehicle alternative freight route upgrades (Shepparton) | 19231 | 4864.5 | 11001 | 3365.5 | qtr 3 2019-20
TEI includes $9.615 million of Commonwealth funding.
– Western Highway – Beaufort bypass – Planning and preconstruction (regional various) | 48077 | 3149.3 | 6920 | 38007.7 | qtr 4 2021-22
TEI includes $24.039 million of Commonwealth funding.
– Western Highway – Stawell to South Australian border (Grampians) | 19236 | 17364 | 1872 | 0 | qtr 4 2019-20
TEI includes $9.618 million of Commonwealth funding. The estimated completion date has been revised to quarter 4 2019-20 to reflect a more accurate schedule of works.
– Western Highway – Ararat bypass – Planning and preconstruction (regional various) | 48077 | 2887.8 | 6180 | 39009.2 | qtr 4 2021-22
TEI includes $24.039 million of Commonwealth funding.
School Area Safety (statewide) | 5000 | 4082.9 | 857 | 60.1 | qtr 4 2019-20
The estimated completion date has been revised to quarter 4 2019-20 due to a delay in current schedule of works.
Shepparton bypass (regional various) | 7640 | 510 | 7130 | 0 | qtr 4 2019-20
The estimated completion date has been revised to quarter 4 2019-20.
South Western Victoria road improvement package (regional various) | 53000 | 28135.8 | 13703 | 11161.2 | qtr 4 2020-21
Strong bridges, stronger economy (statewide) | 35065.3 | 19431.7 | 15492 | 141.6 | qtr 4 2019-20
TEI has decreased by $0.060m due to a re-allocation of funding to output for the delivery of Murray Valley Highway Patho Creek project. TEI includes $7.827 million of Commonwealth funding.
Suburban Roads Upgrade – Northern Roads Upgrade & South Eastern Roads Upgrade (metropolitan) | 2268800 | 63430 | 241161.7955 | 1964208.2045 | qtr 2 2023-24
TEI includes estimated PPP financial liabilities. TEI includes $1,140 million of Commonwealth funding. The estimated completion date has been revised to quarter 2 2023-24.
Urban Congestion Package | 136264.9 | 38841.9 | 72564.6 | 24858.4
– Canterbury Road upgrade (metropolitan various) | 19231.5 | 1981 | 8550 | 8700.5 | qtr 4 2020-21
TEI includes $19.231 million of Commonwealth funding. The estimated completion date has been revised to quarter 4 2020-21 due to extended community consultation and environmental assessments.
– Geelong Road – Millers Road intersection upgrade (Brooklyn) | 4615 | 699.8 | 3915 | 0.2 | qtr 4 2019-20
The estimated completion date has been revised to quarter 4 2019-20 as works are deferred due to the proximity to the West Gate Tunnel works.
– Mount Dandenong Tourist Road upgrades (metropolitan various) | 9615.4 | 770.4 | 300 | 8545 | qtr 3 2020-21
TEI includes $9.615 million of Commonwealth funding. The estimated completion date has been revised to quarter 3 2020-21 due to project redesign.
– O’Herns Road upgrade (Epping) | 102803 | 35390.7 | 59799.6 | 7612.7 | qtr 4 2020-21
TEI has increased by $25.000 million due to market escalation. TEI includes $25.801 million of Commonwealth funding. The estimated completion date has been revised to quarter 4 2020-21 due to delays in environmental approvals.
West Gate Bridge maintenance (metropolitan various) | 17220 | 8123.6 | 7160 | 1936.4 | qtr 4 2019-20
Western Highway duplication – Ballarat to Stawell (regional various) | 656356.9 | 512068 | 39660 | 104628.9 | qtr 2 2021-22
TEI includes $499.380 million of Commonwealth funding. The estimated completion date has been revised to quarter 2 2021-22 due to a change in scope.
Western Roads upgrade (metropolitan various) | 936810 | 718603.6107 | 218206.3893 | 0 | qtr 4 2019-20
TEI includes estimated PPP financial liability.
West Gate Tunnel Project | 6301924 | 2529737.795 | 1601779.298 | 2170407.358
– West Gate Tunnel (metropolitan various) | 6301924 | 2529737.795 | 1601779.298 | 2170407.358 | qtr 2 2022-23
TEI excludes $42.508 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
Yan Yean Road duplication – Stage 1 (Plenty) | 125958.3 | 117736.5 | 6255.7 | 1966.1 | qtr 4 2019-20
Total existing projects | 23763526.1 | 11002005.7057 | 4676594.6828 | 8084925.5625
Total Transport projects | 46928715.1 | 11002455.7057 | 5020670.6828 | 15265302.5626
Other capital expenditure | na | na | 1803027.7251 | na | various
Total 2019-20 Transport capital expenditure |  |  | 6823698.4079
Source: Department of Transport
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Avalon Airport Rail Link – transport corridor protection (Lara) | 1300 | 1299.8 | qtr 4 2018-19
Bacchus Marsh traffic improvements project (Bacchus Marsh) (Regional) | 15073.1 | 13507.5 | qtr 4 2020-21
TEI includes $12.160 million of Commonwealth funding.
Doncaster Area Rapid Transit (metropolitan various) | 41416 | 41416 | qtr 2 2020-21
M80 Ring Road upgrade Sunshine Avenue to Calder Freeway (Sunshine North) | 293761.8 | 172416.4 | qtr 4 2020-21
TEI includes $150.000 million of Commonwealth funding.
Plenty Road Upgrade – Stage 1 (Mill Park) | 35194 | 34632.8 | qtr 4 2019-20
TEI has increased by $8.500 million due to market escalation.
Princes Highway East – Traralgon to Sale duplication (regional various) | 259067.2 | 245849.4 | qtr 4 2021-22
TEI includes $210.000 million of Commonwealth funding.
Rural and Regional Roads Package | 9615 | 9615
- Hamilton Highway upgrade (regional various) | 9615 | 9615 | qtr 4 2019-20
TEI includes $4.807 million of Commonwealth funding.
Thompsons Road duplication (Lyndhurst) | 123243 | 122978.5 | qtr 4 2020-21
Urban Congestion Package
- Bedford Road and Canterbury Road upgrade (Heathmont) | 48 | 48 | qtr 4 2018-19
TEI includes $0.048 million of Commonwealth funding.
- Footscray Road upgrade (West Melbourne) | 9627 | 0 | qtr 4 2019-20
- Maroondah Highway – Bellara Drive intersection upgrade (metropolitan various) | 7692 | 5863 | qtr 4 2020-21
TEI includes $7.692 million of Commonwealth funding.
- Maroondah Highway – Dunlavin Road Intersection upgrade (Mitcham) | 96 | 96 | qtr 4 2018-19
TEI includes $0.096 million of Commonwealth funding.
- Nepean Highway – Forest Drive intersection upgrade (Mount Martha) | 192 | 192 | qtr 4 2018-19
TEI includes $0.192 million of Commonwealth funding.
West Gate Tunnel project
- Monash Freeway upgrade – EastLink to Clyde Road (metropolitan various) | 282879 | 263173.4 | qtr 4 2019-20
- Webb Dock access improvement (metropolitan various) | 61302 | 60389 | qtr 2 2017-18
Estimated to be completed after publication date and before 30 June 2019
Midland Highway/Napier Street improvement works (Bendigo) | 34608.6 | 32322.6 | qtr 4 2020-21
TEI has increased by $5.606 million due to the complexity of utility services relocation.
MR4 – Business Performance Reporting Template (BPRT) – finance system upgrades (metropolitan various) | 1100 | 900.1 | qtr 4 2018-19
The estimated completion date has been revised to quarter 4 2018-19 to reflect proposed additional works required on the system.
Renewal and upgrade of the Intelligent Traffic System (statewide) | 3474 | 2122 | qtr 4 2020-21
Safer Country Crossings Program (statewide) | 43333.2 | 43333 | qtr 4 2019-20
Streamlining Hoddle Street (Richmond) | 108554 | 95181.6 | qtr 4 2020-21
Source: Department of Transport
Department of Treasury and Finance
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Better revenue management system (Melbourne) | 11982 | 8281 | 2400 | 1301 | qtr 4 2020-21
The estimated completion date has been revised. This project is funded through the Sustainability Fund and not included in the totals.
Greener Government Buildings (statewide) | 20000 | 2900 | 17100 | .. | qtr 4 2019-20
The estimated completion date has been revised. This project is funded through the Sustainability Fund and not included in the totals.
Procurement reform (statewide) | 1000 | .. | 1000 | .. | qtr 4 2019-20
The estimated completion date has been revised. This project is funded through the Sustainability Fund and not included in the totals.
State Revenue Office Land Tax Compliance Program (Melbourne) | 2625 | 1325 | 1300 | .. | qtr 4 2019-20
Total existing projects | 15607 | 9606 | 4700 | 1301
Total Treasury and Finance projects | 15607 | 9606 | 4700 | 1301
Other capital expenditure Other capital expenditure includes DTF owned buildings capital maintenance funding, replacement of IT assets, annual upgrades of buildings and fleet turnover. | na | na | 28147.4042 | na | various
Total 2019-20 Treasury and Finance capital expenditure |  |  | 32847.4042
Source: Department of Treasury and Finance
Parliament
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Total Parliament projects | 0 | 0 | 0 | 0
Other capital expenditure | na | 2550.5841 |  | na | various
Total 2019-20 Parliament capital expenditure |  | 2550.5841
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Remediation – Office Accommodation in the Parliamentary Precinct (East Melbourne) | 45464 | 41824 | qtr 4 2018-19
Source: Parliament
Court Services Victoria
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Aboriginal Justice Agreement 4 (Melbourne) | 1295 | 0 | 636 | 659 | qtr 4 2021-22
Security upgrades to strengthen court safety (statewide) | 5041 | 0 | 2707 | 2334 | qtr 2 2021-22
Bendigo Law Courts Redevelopment (Bendigo) | 152396 | 0 | 19900 | 132496 | qtr 1 2022-23
Improving court access through additional audio-visual technology (statewide) | 3802 | 0 | 1901 | 1901 | qtr 4 2020-21
Total new projects | 162534 | 0 | 25144 | 137390
Source: Court Services Victoria
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Bendigo Law Court Redevelopment - land acquisition (Bendigo) | 6000 | 4000 | 2000 | 0 | qtr 4 2019-20
The project completion date has been revised for settlement of land acquisition.
Court Safety and Security (statewide) | 6275 | 6010 | 265 | 0 | qtr 4 2019-20
The project completion date has been extended to allow for post construction works.
Courts case management system (statewide) | 66800 | 6728 | 7015 | 53057 | qtr 4 2020-21
Echuca Court Safety and Security (Echuca) | 4850 | 1650 | 3200 | 0 | qtr 4 2019-20
Forensic mental health implementation plan – Priority services reform (regional various) | 1738 | 682.1 | 997 | 58.9 | qtr 4 2020-21
Implementation of Youth Justice Reform (metropolitan various) | 13670 | 2016 | 5293 | 6361 | qtr 4 2020-21
The estimated completion date has been extended following a detailed planning process.
Safe and sustainable Victorian courts (statewide) | 7234 | 1337 | 5320 | 577 | qtr 4 2020-21
Specialist Family Violence Integrated Court Response (statewide) | 37558 | 5573 | 30299 | 1686 | qtr 4 2020-21
TEI has been reduced due to a funding transfer from capital to operating. The estimated completion date has been extended to align with the updated project plan.
Supreme Court of Victoria – IT upgrade (Melbourne) | 10501 | 3579 | 4052 | 2870 | qtr 4 2020-21
The estimated completion date has been extended due to a change in project scope. TEI includes funding transfer from operating to capital for the procurement of digital software.
Wyndham Law Courts Redevelopment (Werribee) | 14000 | 0 | 14000 | 0 | qtr 4 2019-20
Project name changed from "Bendigo and Werribee Law Courts redevelopment (Bendigo and Werribee)" to "Wyndham Law Courts Redevelopment". The project completion date has been revised for settlement of land acquisition.
Total existing projects | 168626 | 31575.1 | 72441 | 64609.9
Total Court Services Victoria projects | 331160 | 31575.1 | 97585 | 201999.9
Other capital expenditure | na | na | -14113.557 | na | various
Other capital expenditure incorporates impacts such as funding sourced from internal reprioritisations and revaluation of assets.
Total 2019-20 Court Services Victoria capital expenditure |  |  | 83471.443
Source: Court Services Victoria
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Ice Action Plan – Expansion of the Drug Court of Victoria (Melbourne) | 1110 | 1099 | qtr 4 2017-18
Project was included in last year’s completed project list and has been completed.
Video Conferencing (Statewide) | 10034 | 9499 | qtr 4 2017-18
The project was included in last year’s completed project list and has been completed.
Estimated to be completed after publication date and before 30 June 2019
Access to Justice – VCAT (Melbourne) | 5277 | 5277 | qtr 4 2018-19
Additional Court Capacity (statewide) | 1260 | 1260 | qtr 4 2018-19
TEI includes funding transfer from operating to capital for upgrades to audio and visual equipment at the Magistrates’ Courts.
Court Integrated Service Program (CISP) and CISP Remand Outreach Pilot (statewide) | 2466 | 2466 | qtr 4 2018-19
TEI includes transfer from operating to capital for the Drug Court fit out at 350 Queen Street.
Drug Court Expansion (Melbourne) | 662 | 662 | qtr 4 2018-19
TEI includes funding transfer from operating to capital for the refurbishment of the Melbourne Magistrates’ Court.
Shepparton Law Courts (Shepparton) | 68090 | 67956 | qtr 4 2018-19
The completion date was extended following the discovery of asbestos during construction.
Source: Court Services Victoria
Country Fire Authority
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
2019-20 Base capital fleet upgrade (statewide) | 12381 | 0 | 6381 | 6000 | qtr 4 2020-21
2019-20 Base capital fleet upgrade – non-fire trucks (statewide) | 6693 | 0 | 6693 | 0 | qtr 4 2019-20
2019-20 Base capital land and building upgrades (statewide) | 5535 | 0 | 5535 | 0 | qtr 4 2019-20
2019-20 Base plant and equipment upgrade (statewide) | 818 | 0 | 818 | 0 | qtr 4 2019-20
Emergency services local infrastructure (statewide) | 14700 | 0 | 2600 | 12100 | qtr 4 2021-22
Total new projects | 40127 | 0 | 22027 | 18100
Source: Country Fire Authority
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Base capital fleet upgrade 2018-19 (statewide) | 11434 | 3449 | 5490 | 2495 | qtr 1 2020-21
TEI has reduced due to $0.694 million having been redirected to Base capital fleet upgrade 2016-17 (statewide). Cash flow and timing has been revised in line with a revised project schedule.
Base capital land and buildings upgrade 2018-19 (statewide) | 12901 | 10901 | 2000 | 0 | qtr 1 2019-20
TEI has reduced by $0.685 million. Cash flow and timing has been revised in line with a revised project schedule.
Base plant and equipment upgrade 2018-19 (statewide) | 798 | 783 | 15 | 0 | qtr 1 2019-20
Cash flow and timing has been revised in line with a revised project schedule.
CFA Fiskville Transition Program – New Training Capability (statewide) | 41741 | 16903 | 16933.5 | 7904.5 | qtr 2 2021-22
Cash flow and timing has been revised in line with a revised project schedule.
Compressed air foam systems (statewide) | 1530 | 100 | 0 | 1430 | qtr 4 2020-21
Timing has been revised in line with a revised project schedule.
Country Fire Authority Stations Program (statewide) | 10050 | 7257 | 1793 | 1000 | qtr 3 2020-21
Cash flow and timing has been revised in line with a revised project schedule.
Emergency services high-priority infrastructure program (statewide) | 9100 | 900 | 5200 | 3000 | qtr 3 2020-21
Cash flow and timing has been revised in line with a revised project schedule.
Fiskville and Regional Victorian Emergency Management Training Centres Remediation (statewide) | 23754 | 10899 | 6795 | 6060 | qtr 2 2020-21
Cash flow and timing has been revised in line with a revised project schedule.
Morwell emergency services hub (Morwell) | 5000 | 3554 | 1446 | 0 | qtr 4 2019-20
New Craigieburn fire station (Craigieburn) | 10500 | 225 | 3300 | 6975 | qtr 4 2020-21
Cash flow has been revised in line with a revised project schedule.
Regional support to volunteerism sustainability (statewide) | 2585 | 2434 | 151 | 0 | qtr 4 2019-20
Cash flow and timing has been revised in line with a revised project schedule.
Specialist Appliances (statewide) | 9975 | 752 | 3223 | 6000 | qtr 2 2020-21
Cash flow and timing has been revised in line with a revised project schedule.
Truganina fire station (Truganina) | 3750 | 175 | 1515 | 2060 | qtr 2 2020-21
Funded through the Growth Areas Infrastructure Contribution. Cash flow and timing has been revised in line with a revised project schedule.
Volunteer Support – Critical Infrastructure and Fleet (statewide) | 11000 | 4025 | 5480 | 1495 | qtr 2 2020-21
Funded through the Growth Areas Infrastructure Contribution. Cash flow and timing has been revised in line with a revised project schedule.
Wyndham Vale fire station (Wyndham Vale) | 3750 | 215 | 1435 | 2100 | qtr 2 2020-21
Funded through the Growth Areas Infrastructure Contribution. Cash flow and timing has been revised in line with a revised project schedule.
Total existing projects | 157868 | 62572 | 54776.5 | 40519.5
Total Country Fire Authority projects | 197995 | 62572 | 76803.5 | 58619.5
Source: Country Fire Authority
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Base capital fleet upgrade 2016-17 (statewide) | 12334 | 12334 | qtr 3 2018-19
TEI has been revised to reflect a revised schedule of upgrades.
Base plant and equipment upgrade 2017-18 (statewide) | 402 | 402 | qtr 4 2018-19
Published in 2018-19 Budget as complete. The project did not reach practical completion until quarter 2 2018-19.
Morwell emergency services hub (new project for 2015-16) (Morwell) | 3000 | 3000 | qtr 4 2018-19
Estimated to be completed after publication date and before 30 June 2019
Base capital fleet upgrade (non fire trucks) 2018-19 (statewide) | 6011 | 6011 | qtr 1 2019-20
TEI has decreased due to $0.493 million having been redirected to the Base capital fleet upgrade (non-fire trucks) 2017-18 (statewide) and $0.026 million to the Base capital fleet upgrade (non-fire trucks) 2016-17 (statewide). Both projects were reported as practically complete in the 2018-19 Budget, but did not financially close until after 30 June 2018.
Base capital fleet upgrade 2017-18 (statewide) | 12381 | 12381 | qtr 1 2019-20
Base capital land and buildings upgrade 2017-18 (statewide) | 11005 | 11005 | qtr 1 2019-20
Enhancing the CFA’s capability (statewide) | 1764 | 1764 | qtr 4 2018-19
TEI has increased due to $0.764 million having been redirected from output.
Replacement of respiratory protection equipment (statewide) | 13589 | 13589 | qtr 4 2019-20
TEI has reduced due to $0.346 million having been redirected to output.
Source: Country Fire Authority
Metropolitan Fire and Emergency Services Board
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Broadmeadows fire station refurbishment (Broadmeadows) | 2600 | 0 | 850 | 1750 | qtr 4 2020-21
Computer equipment and software upgrade/replacement 2019-20 (metropolitan various) | 8764 | 0 | 3196 | 5568 | qtr 4 2021-22
Ringwood fire station refurbishment (Ringwood) | 2000 | 0 | 300 | 1700 | qtr 4 2021-22
Station alteration and major maintenance 2019-20 (metropolitan various) | 400 | 0 | 400 | 0 | qtr 4 2019-20
Vehicles – Fire fighting appliance replacement 2019-20 (metropolitan various) | 7800 | 0 | 2190 | 5610 | qtr 4 2021-22
Vehicles – Passenger car and light commercial upgrade/replacement 2019-20 (metropolitan various) | 3284 | 0 | 3284 | 0 | qtr 4 2019-20
All remaining Projects with a TEI less than $250 000 (metropolitan various) | 510 | 0 | 410 | 100 | qtr 4 2020-21
Total new projects | 25358 | 0 | 10630 | 14728
Source: Metropolitan Fire and Emergency Services Board
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Appliance Health & Safety Program | 570 | 337 | 233 | 0 | qtr 4 2019-20
Cash flow has been revised in line with a revised project schedule.
Box Hill fire station – construction (Box Hill) | 7500 | 1037 | 2200 | 4263 | qtr 4 2020-21
Cash flow has been revised in line with a revised project schedule.
Brooklyn fire station – construction (Brooklyn) | 5598 | 360 | 2130 | 3108 | qtr 3 2020-21
TEI, cash flow and timing has been revised in line with a revised project schedule.
Computer equipment and software upgrade/replacement 2017-18 (metropolitan various) | 5848 | 974 | 580 | 4294 | qtr 4 2020-21
TEI and cash flow has been revised in line with a revised project schedule.
Computer equipment and software upgrade/replacement 2018-19 (metropolitan various) | 3930 | 2838 | 1092 | 0 | qtr 4 2019-20
TEI and cash flow has been revised in line with a revised project schedule.
Derrimut fire station – construction (Derrimut) | 9350 | 1677 | 4500 | 3173 | qtr 2 2020-21
Cash flow and timing has been revised in line with a revised project schedule.
Enhanced gas detection (metropolitan various) | 1442 | 122 | 1320 | 0 | qtr 4 2019-20
Cash flow has been revised in line with a revised project schedule.
HazMat asset replacement (metropolitan various) | 309 | 209 | 100 | 0 | qtr 4 2019-20
Hose deployment bag (metropolitan various) | 1391 | 0 | 580 | 811 | qtr 4 2021-22
Cash flow has been revised in line with a revised project schedule.
Marine upgrade/replacement (metropolitan various) | 3100 | 736 | 1025 | 1339 | qtr 2 2021-22
TEI, cash flow and timing has been revised in line with a revised project schedule.
Replacement of respiratory protection equipment (statewide) | 5552 | 5420 | 132 | 0 | qtr 1 2019-20
Cash flow and timing has been revised in line with a revised project schedule.
SAP Hana Enterprise Cloud (metropolitan various) | 8077 | 2538 | 5539 | 0 | qtr 2 2019-20
Project name changed from SAP Stability and Security – Stage 2 (metropolitan various) published in the 2018-19 Budget. TEI has increased due to a change in the project scope. Cash flow and timing has been revised in line with a revised project schedule.
Vehicles – Firefighting appliance replacement (metropolitan various) | 21977 | 19492 | 2485 | 0 | qtr 2 2019-20
TEI and cash flow has been revised in line with a revised project schedule.
Vehicles – Firefighting appliance replacement 2018-19 (metropolitan various) | 400 | 300 | 100 | 0 | qtr 4 2019-20
TEI and cash flow has been revised in line with a revised project schedule.
Vehicles – Firefighting appliance upgrade 2017-18 (metropolitan various) | 1215 | 573 | 490 | 152 | qtr 2 2020-21
Cash flow and timing has been revised in line with a revised project schedule.
Vehicles – Firefighting heavy appliance replacement (metropolitan various) | 6010 | 3657 | 2353 | 0 | qtr 3 2019-20
Cash flow and timing has been revised in line with a revised project schedule.
All remaining projects with a TEI less than $250 000 (metropolitan various) | 1218 | 1007 | 54 | 157 | qtr 1 2019-20
TEI has increased due to a change in the project scope. Cash flow and timing has been revised in line with a revised project schedule.
Total existing projects | 83487 | 41277 | 24913 | 17297
Total Metropolitan Fire and Emergency Services Board projects | 108845 | 41277 | 35543 | 32025
Source: Metropolitan Fire and Emergency Services Board
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Breathing apparatus capability (metropolitan various) | 665 | 665 | qtr 3 2018-19
Final TEI reflects efficiencies achieved in the project.
Glen Iris fire station – Construction rebuild (Glen Iris) | 8951 | 8951 | qtr 3 2018-19
TEI has decreased by $0.743 million.
Estimated to be completed after publication date and before 30 June 2019
Computer equipment and software upgrade/replacement 2016-17 (metropolitan various) | 12244 | 12244 | qtr 4 2018-19
Enhanced Forced Entry Tool (metropolitan Various) | 1997 | 1997 | qtr 4 2018-19
Final TEI reflects efficiencies achieved in the project.
Mobile Command and Control Infrastructure (MCCI) (metropolitan various) | 8765 | 0 | qtr 4 2018-19
This project has been withdrawn and capital funding has been reprioritised. The project may return in the future in a revised capital project containing elements of the original.
Station alteration and major maintenance 2018-19 (metropolitan various) | 1909 | 1909 | qtr 4 2018-19
TEI has increased due to a change in the project scope.
Vehicles – Passenger car and light commercial upgrade/replacement 2018-19 (metropolitan various) | 2060 | 2060 | qtr 4 2018-19
TEI has decreased by $0.540 million to reflect revised scope.
Source: Metropolitan Fire and Emergency Services Board

## Chapter 3
Asset Initiatives
Barwon Region Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Other works and services – corporate (regional various) | 3070 | 235 | 580 | 2255 | various
Sewer collection – main sewers (regional various) | 22733 | 0 | 0 | 22733 | various
Sewer collection – water reclamation and disposal (regional various) | 8764 | 0 | 519 | 8245 | various
Water supply – reticulation systems (regional various) | 2324 | 0 | 0 | 2324 | various
Water supply – transfer and major distribution systems (regional various) | 26765 | 98 | 1031 | 25636 | various
All remaining projects with a TEI less than $1 million | 32 | 32 | 0 | 0 | various
Total new projects | 63688 | 365 | 2130 | 61193
Source: Barwon Region Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Other works and services – corporate (regional various) | 223108 | 67459 | 13551 | 142098 | various
Project TEI has increased since the 2018-19 Budget due to an expanded project scope.
Recycled water (regional various) | 74221 | 3587 | 3641 | 66993 | various
Sewer collection – main sewers (regional various) | 100493 | 27852 | 3645 | 68996 | various
Sewer collection – reticulation and other works (regional various) | 133307 | 41597 | 6804 | 84906 | various
Sewer collection – water reclamation and disposal (regional various) | 115091 | 31369 | 10737 | 72985 | various
Project TEI has increased since the 2018-19 Budget due to an expanded project scope.
Water supply – headworks (regional various) | 89287 | 6147 | 9739 | 73401 | various
Water supply – reticulation systems (regional various) | 145666 | 47893 | 8247 | 89526 | various
Water supply – transfer and major distribution systems (regional various) | 150912 | 19368 | 7768 | 123776 | various
Water supply – treatment and quality improvements (regional various) | 44828 | 11609 | 5774 | 27445 | various
All remaining projects with a TEI less than $1 million | 985 | 0 | 865 | 120 | various
Total existing projects | 1077898 | 256881 | 70771 | 750246
Total Barwon Region Water Corporation projects | 1141586 | 257246 | 72901 | 811439
Source: Barwon Region Water Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Other works and services – corporate (regional various) | 1841 | 1841 | various
Sewer collection – water reclamation and disposal (regional various) | 2131 | 2074 | various
Water supply – headworks (regional various) | 5421 | 5370 | various
Water supply – reticulation systems (regional various) | 1735 | 1735 | various
Water supply – transfer and major distribution systems (regional various) | 5342 | 5319 | various
All remaining projects with a TEI less than $1 million | 207 | 207 | various
Source: Barwon Region Water Corporation
Cemeteries
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Development of Islamic monumental stock (Springvale) | 1970 | 0 | 1970 | 0 | qtr 4 2019-20
Development of Robina, Oaks, Birches stock (Springvale) | 1225.3 | 0 | 1225.3 | 0 | qtr 4 2019-20
IT architecture (Springvale) | 1751.9 | 300 | 1451.9 | 0 | qtr 4 2019-20
All remaining projects with a TEI less than $1 million | 8909.5 | 0 | 8909.5 | 0 | qtr 4 2019-20
Total new projects | 13856.8 | 300 | 13556.8 | 0
Source: Cemeteries
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Centre of care and wellbeing building (Springvale) | 2500 | 1250 | 1250 | 0 | qtr 2 2019-20
Project completion date has been delayed compared with the 2018-19 Budget due to increased work required.
Ely Court development (Keilor) | 12441.7 | 4460.6 | 1801 | 6180 | qtr 4 2021-22
Project TEI has decreased compared with the 2018-19 Budget as a result of re-profiled budget expenditure.
Grave development (Lilydale) | 3772.7 | 30.7 | 230 | 3512 | qtr 4 2021-22
This project was announced after the 2018-19 Budget and therefore did not appear in 2018-19 Budget Paper No. 4.
Harkness greenfield development (Harkness) | 13330.8 | 530.8 | 5000 | 7800 | qtr 4 2022-23
This project was announced after the 2018-19 Budget and therefore did not appear in 2018-19 Budget Paper No. 4.
Implementation of the new Greater Metropolitan Cemetery Trusts digital strategy (Fawkner) | 11731.8 | 5470.7 | 461.2 | 5800 | qtr 4 2022-23
Project TEI has increased compared with the 2018-19 Budget as a result of re-profiled budget expenditure.
Infrastructure works (Bunurong) | 4795 | 3495 | 1300 | 0 | qtr 4 2019-20
Project TEI has increased compared with the 2018-19 Budget due to a change in project scope.
Lilydale Cemetery infrastructure (Lilydale) | 2177.2 | 952.2 | 300 | 925 | qtr 4 2020-21
Project TEI has increased compared with the 2018-19 Budget as a result of re-profiled budget expenditure.
Northern Memorial Park depot (Fawkner) | 1585.9 | 85.9 | 1500 | 0 | qtr 4 2019-20
This project was announced after the 2018-19 Budget and therefore did not appear in 2018-19 Budget Paper No. 4.
Northern Memorial Park expansion (Fawkner) | 26426.2 | 5378.2 | 3492.5 | 17555.5 | qtr 4 2027-28
Due to the length and cost of the project, it has been rescoped into stages in order to best estimate costs and meet community demand. As such, future year expenditure is subject to change in order to meet community and public requirements for the long and short term.
Plant and equipment replacement program (statewide) | 3963.1 | 995.6 | 1400 | 1567.4 | qtr 4 2021-22
This project was announced after the 2018-19 Budget and therefore did not appear in 2018-19 Budget Paper No. 4.
Preston Mausoleum – Rectification Strategy (Preston) | 1355.8 | 355.8 | 500 | 500 | qtr 4 2020-21
This project was announced after the 2018-19 Budget and therefore did not appear in 2018-19 Budget Paper No. 4.
Records building (Springvale) | 1200 | 600 | 600 | 0 | qtr 2 2019-20
Project TEI has increased compared with the 2018-19 Budget due to increased work required. This has also delayed the project’s completion date.
Road rehabilitation program (statewide) | 1145.3 | 59.4 | 350 | 736 | qtr 4 2022-23
Project TEI has decreased compared with the 2018-19 Budget as a result of re-profiled budget expenditure.
All remaining projects with a TEI of less than $1 million | 13707.2 | 3889.8 | 5646.3 | 4171.1 | qtr 4 2022-23
Total existing projects | 100132.7 | 27554.7 | 23831 | 48747
Total Cemeteries projects | 113989.5 | 27854.7 | 37387.8 | 48747
Source: Cemeteries
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Altona Wagtail area development (Altona) | 1300 | 1300 | qtr 4 2018-19
Geelong Cemeteries Trust – construction of Mausoleum stage 3 (Geelong) | 1500 | 1500 | qtr 3 2018-19
Lilydale Memorial Park vaults (Lilydale) | 1216.2 | 1216.2 | qtr 4 2018-19
This project was announced after the 2018-19 Budget and therefore did not appear in the 2018-19 Budget.
Office accommodation (Fawkner) | 2194 | 2194 | qtr 4 2018-19
Project TEI increased compared with the 2018-19 Budget as a result of re-profiled budget expenditure.
Padre Pio 3 – mausoleum (Springvale) | 4300 | 4300 | qtr 4 2018-19
Project TEI increased compared with the 2018-19 Budget due to an increase in volume of stock.
Song He Yuan stock extension (Springvale) | 27707 | 27707 | qtr 4 2018-19
Project TEI increased compared with the 2018-19 Budget due to latent conditions.
All remaining projects with a TEI less than $1 million | 15510.8 | 15510.8 | qtr 4 2018-19
Source: Cemeteries
Central Gippsland Region Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Fleet purchases – unregulated agribusiness (Dutson) | 2382 | 0 | 242 | 2140 | ongoing
Yallourn North water supply to bypass Energy Australia (Yallourn) | 1026 | 1026 | 0 | 0 | qtr 4 2018-19
All remaining projects with a TEI less than $1 million | 10971 | 773 | 643.29 | 9554.71 | various
Total new projects | 14379 | 1799 | 885.29 | 11694.71
Source: Central Gippsland Region Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Agricultural minor works (regional various) | 2107 | 123 | 258 | 1726 | ongoing
Ancilliary capital equipment (regional various) | 2261 | 461 | 108 | 1692 | qtr 4 2027-28
Bulk waste water capital projects (regional various) | 6824 | 315 | 568 | 5941 | ongoing
Bulk water capital projects (regional various) | 7099 | 1885 | 192 | 5022 | qtr 4 2027-28
The TEI for this project has changed compared to last year due to a change in the project scope.
Communications infrastructure (regional various) | 2602 | 260 | 197 | 2145 | ongoing
Continued software development of supervisory control and data acquisition (SCADA) (regional various) | 2601 | 229 | 235 | 2137 | ongoing
Convert Sale sewer pump station 2 to underground (Sale) | 2174 | 0 | 0 | 2174 | qtr 4 2022-23
Coongulla water – Heyfield interconnector (Coongulla) | 6547 | 396 | 157 | 5994 | qtr 4 2022-23
Customer meter replacements (regional various) | 6027 | 538 | 551 | 4938 | ongoing
Drouin waste water treatment plant upgrade (Drouin) | 34248 | 3548 | 12844 | 17856 | qtr 4 2021-22
Electrical switchboard upgrades (regional various) | 2991 | 244 | 289 | 2458 | qtr 4 2021-22
Fleet – agribusiness tractors combine harvester (Dutson Downs) | 3082 | 210 | 395 | 2477 | ongoing
Fleet purchases (regional various) | 18009 | 1798 | 1560 | 14651 | ongoing
The TEI for this project has decreased compared to the 2018-19 Budget due to a change in project scope.
Gippsland water factory anaerobic reactor rebuild (Morwell) | 8876 | 0 | 0 | 8876 | qtr 4 2027-28
Gippsland water factory membrane replacement program (Morwell) | 14194 | 2145 | 889 | 11160 | qtr 4 2027-28
The TEI for this project has increased compared to the 2018-19 Budget due to a change in project scope.
Gippsland water factory minor improvement works (Morwell) | 10061 | 1345 | 131 | 8585 | ongoing
Information technology infrastructure (regional various) | 2361 | 223 | 64 | 2074 | ongoing
Loch Sport low pressure sewer systems (Loch Sport) | 1165 | 104 | 107 | 954 | qtr 4 2024-25
Maffra waste water treatment plant lagoon 1 desludge (Maffra) | 1806 | 0 | 0 | 1806 | qtr 4 2024-25
Maffra water treatment plant chemical systems upgrade (Maffra) | 1200 | 0 | 0 | 1200 | qtr 4 2023-24
Maffra water treatment plant new chlorine or sodium hypochlorite dosing facility (Maffra) | 1058 | 0 | 0 | 1058 | qtr 4 2025-26
Maffra water treatment plant refurbishment of clarifier (Maffra) | 1836 | 0 | 0 | 1836 | qtr 4 2026-27
Major customer meter replacements (regional various) | 1180 | 105 | 108 | 967 | ongoing
Meter replacement program (regional various) | 1470 | 65 | 141 | 1264 | ongoing
Mirboo North water rising main replacement (Mirboo North) | 3749 | 258 | 3437 | 54 | qtr 4 2020-21
Moe waste water treatment plant inlet screen and grit removal (Moe) | 2072 | 106 | 872 | 1094 | qtr 4 2023-24
This project from the 2018-19 Budget was included under 'All remaining projects with a TEI less than $1 million'. This project has since been re-forecast as having a TEI greater than $1 million.
Moe water – new treated water basin (Moe) | 3797 | 0 | 146 | 3651 | qtr 4 2020-21
This project from the 2018-19 Budget was included under 'All remaining projects with a TEI less than $1 million'. This project has since been re-forecast as having a TEI greater than $1 million.
Moe water treatment plant – basin liners and covers (Moe) | 2091 | 5 | 104 | 1982 | qtr 4 2021-22
The TEI for this project has changed compared with the 2018-19 Budget due to a change in project scope.
Moondarra – Pine Gully dam safety remediation works (Moondarra) | 1687 | 0 | 0 | 1687 | qtr 4 2023-24
Moondarra – Buckleys Hill – Australian National Committee of Large Dams remediation works stage 1 – (Morwell) | 6783 | 0 | 0 | 6783 | qtr 4 2025-26
Morwell sewer – Holmes Road sewer augmentation (Morwell) | 1485 | 0 | 0 | 1485 | qtr 4 2027-28
This project from the 2018-19 Budget was included under 'All remaining projects with a TEI less than $1 million'. This project has since been re-forecast as having a TEI greater than $1 million.
Morwell sewer – Polden Cresent sewer pump station upgrade – stage three residual network augmentation (Morwell) | 2108 | 0 | 0 | 2108 | qtr 4 2026-27
Morwell water – Buckleys Basin and water treatment plant land acquisition and new Buckleys Basin (Morwell) | 13286 | 0 | 320 | 12966 | qtr 4 2027-28
Morwell water – Buckleys Hill – clear water storage cover and liner (Morwell) | 1243 | 0 | 1243 | 0 | qtr 4 2019-20
This project from the 2018-19 Budget was included under 'All remaining projects with a TEI less than $1 million'. This project has since been re-forecast as having a TEI greater than $1 million.
Morwell water – Holmes Road/McDonald Road water augmentation (Morwell) | 1155 | 0 | 0 | 1155 | qtr 4 2025-26
Newborough basin liners and covers (Newborough) | 1006 | 0 | 0 | 1006 | qtr 4 2021-22
Northways treated water basin cover and liner replacement (Churchill) | 1497 | 0 | 53 | 1444 | qtr 4 2022-23
Rawson waste water treatment plant emergency storage (Rawson) | 1126 | 0 | 0 | 1126 | qtr 4 2023-24
Rawson water – distribution main from water treatment plant to Parkers Corner pressure reducing valve (Rawson) | 1766 | 0 | 0 | 1766 | qtr 4 2026-27
Regional outfall sewer channel relining improvement works (regional various) | 1910 | 0 | 192 | 1718 | ongoing
Regional outfall sewer renewal program through Traralgon (Traralgon) | 6930 | 0 | 627 | 6303 | ongoing
The TEI for this project has increased compared with the 2018-19 Budget due to a change in project scope.
Renewable energy – solar panels on Moe waste water treatment plant, Traralgon water treatment plant and Traralgon office (regional various) | 1818 | 1818 | 0 | 0 | qtr 4 2019-20
Renewable energy – solar panels on Warragul waste water treatment plant and Warragul water treatment plant (Warragul) | 1091 | 0 | 1091 | 0 | qtr 4 2019-20
This project from the 2018-19 Budget was included under 'All remaining projects with a TEI less than $1 million'. This project has since been re-forecast as having a TEI greater than $1 million.
Renewable energy Dutson wind generator (Dutson) | 3743 | 0 | 0 | 3743 | qtr 4 2024-25
Renewable energy Moondarra hydro pump station (Moondarra) | 3014 | 0 | 0 | 3014 | qtr 4 2024-25
Replace pressure sewer pumps components (Seaspray, Coongulla and Loch Sport) | 6782 | 125 | 501 | 6156 | ongoing
Reticulation renewals (regional various) | 18769 | 2268 | 1280 | 15221 | ongoing
The TEI for this project has increased compared with the 2018-19 Budget due to a change in project scope.
SCADA asset upgrade program (regional various) | 5620 | 502 | 514 | 4604 | ongoing
Sale sewer outfall sewer pump station and land acquisition (Sale) | 10319 | 4287 | 5979 | 53 | qtr 4 2020-21
The TEI for this project has increased compared with the 2018-19 Budget due to a change in project scope.
Sale waste water treatment plant capacity upgrade (Sale) | 1248 | 0 | 0 | 1248 | qtr 4 2025-26
Saline waste outfall pipeline stage 4 and 5 (regional various) | 8139 | 0 | 0 | 8139 | qtr 4 2027-28
The TEI for this project has increased compared with the 2018-19 Budget due to a change in project scope.
Sanders treated water basin cover and liner replacement (Churchill) | 2386 | 0 | 0 | 2386 | qtr 4 2022-23
Sewer pump station mechanical and electrical (regional various) | 5781 | 583 | 522 | 4676 | ongoing
The TEI for this project has increased compared with the 2018-19 Budget due to a change in project scope.
Sewer reticulation customer charter initiative – minor capital projects (regional various) | 6108 | 1043 | 513 | 4552 | qtr 4 2027-28
Sewer reticulation upgrades – all systems (regional various) | 16432 | 2268 | 1280 | 12884 | ongoing
The TEI for this project has increased compared with the 2018-19 Budget due to a change in project scope.
Sewer trunk main renewals program (regional various) | 13118 | 0 | 522 | 12596 | ongoing
The TEI for this project has increased compared with the 2018-19 Budget due to a change in project scope.
Shared asset projects (regional various) | 18510 | 6615 | 946 | 10949 | qtr 4 2027-28
The TEI for this project has decreased compared with the 2018-19 Budget due to a change in project scope.
Shared assets – water (regional various) | 6735 | 321 | 663 | 5751 | ongoing
This project from the 2018-19 Budget was included under 'All remaining projects with a TEI less than $1 million'. This project has since been re-forecast as having a TEI greater than $1 million.
Smart metering (regional various) | 1067 | 0 | 0 | 1067 | qtr 4 2025-26
Software upgrade (regional various) | 5962 | 397 | 165 | 5400 | ongoing
Soil organic recycling facility machinery renewal program (Dutson) | 6333 | 826 | 853 | 4654 | ongoing
Soil organic recycling facility overland conveyor and fixed trommel screen (Dutson) | 2023 | 0 | 0 | 2023 | qtr 4 2022-23
Soil organic recycling facility site and amenities (Dutson) | 1081 | 20 | 107 | 954 | ongoing
Soil organic recycling facility waste treatment (Dutson) | 5931 | 260 | 587 | 5084 | ongoing
Trafalgar Eight Mile Road sewer pump station and rising main (Trafalgar) | 1981 | 0 | 209 | 1772 | qtr 4 2021-22
Traralgon Peterkin Street sewer pump station capacity upgrade (Traralgon) | 3009 | 0 | 0 | 3009 | qtr 4 2025-26
Traralgon sewer – Breed Street emergency storage (Traralgon) | 1064 | 1044 | 20 | 0 | qtr 4 2019-20
This project from the 2018-19 Budget was included under 'All remaining projects with a TEI less than $1 million'. This project has since been re-forecast as having a TEI greater than $1 million.
Traralgon sewer – Glengarry sewer pump station emergency storage and reconfiguration (Glengarry) | 1167 | 0 | 0 | 1167 | qtr 4 2022-23
Traralgon sewer Peterkin Street rising main upgrade (Traralgon) | 1311 | 0 | 0 | 1311 | qtr 4 2023-24
Traralgon water – connect Traralgon and Morwell water networks stage one (Traralgon) | 8985 | 0 | 0 | 8985 | qtr 4 2024-25
Traralgon water – hydro turbine on inlet valve (Traralgon) | 1655 | 0 | 1600 | 55 | qtr 4 2020-21
Tyers water – Glengarry Cairnbrook Road water reticulation renewal (Tyers) | 1369 | 0 | 0 | 1369 | qtr 4 2024-25
Tyers water – replace cover of Rosedale service basin (Rosedale) | 1138 | 0 | 0 | 1138 | qtr 4 2024-25
Tyers water treatment plant – basin liners and covers (Tyers) | 1720 | 0 | 0 | 1720 | qtr 4 2022-23
Unplanned plant failures for wastewater (e.g. pumps, instruments, plant components) (regional various) | 9196 | 698 | 709 | 7789 | ongoing
Warragul Drouin water – Drouin West basin (Drouin) | 4258 | 0 | 0 | 4258 | qtr 4 2025-26
The TEI for this project has increased compared with the 2018-19 Budget due to a change in project scope.
Warragul Drouin water capacity upgrade of 450 mm spine main between Tyssen treated water pump station and Lillico Road (Warragul) | 2665 | 0 | 0 | 2665 | qtr 4 2019-20
Warragul South treated water basin cover and liner replacement (Warragul) | 1039 | 0 | 0 | 1039 | qtr 4 2025-26
Warragul sewer – North East augmentation (Warragul) | 4956 | 0 | 320 | 4636 | qtr 4 2022-23
Warragul sewer – waste water treatment plant upgrade (Warragul) | 11509 | 0 | 0 | 11509 | qtr 4 2027-28
The TEI for this project has increased compared with the 2018-19 Budget as it now includes project construction costs.
Warragul waste water north east augmentation (Warragul) | 1200 | 0 | 0 | 1200 | qtr 4 2025-26
Warragul water – CBD distribution main bypass (Warragul) | 9834 | 0 | 373 | 9461 | qtr 4 2019-20
Warragul water – rider main stage 1 (Warragul) | 1382 | 236 | 21 | 1125 | qtr 4 2021-22
This project from the 2018-19 Budget was included under 'All remaining projects with a TEI less than $1 million'. This project has since been re-forecast as having a TEI greater than $1 million.
Warragul water treatment plant basin liners and covers (Warragul) | 1471 | 31 | 1419 | 21 | qtr 4 2022-23
Water main renewal (Vary, Savige and Williams Streets) (Morwell) | 1962 | 0 | 0 | 1962 | qtr 4 2025-26
Water pressure reducing valve to lower pressure in the central business district (Warragul) | 1834 | 0 | 0 | 1834 | qtr 4 2025-26
Water quality improvement minor works (regional various) | 4227 | 426 | 382 | 3419 | ongoing
Water reticulation improvement minor works (regional various) | 6070 | 1339 | 479 | 4252 | ongoing
Water treatment – off specification treated water storage at key water treatment plants (regional various) | 1237 | 0 | 0 | 1237 | qtr 4 2027-28
This project from the 2018-19 Budget was included under 'All remaining projects with a TEI less than $1 million'. This project has since been re-forecast as having a TEI greater than $1 million.
Water treatment minor capital projects (regional various) | 13845 | 1245 | 1171 | 11429 | ongoing
Water treatment plants filter upgrade refurbishment program (regional various) | 2520 | 0 | 160 | 2360 | ongoing
Yallourn North sewer rising main replacement stage 2 (Yallourn North) | 5438 | 0 | 0 | 5438 | qtr 4 2025-26
All remaining projects with a TEI less than $1 million | 51813 | 5071 | 5336.765 | 41405.235 | various
The following projects were all above $1 million last year but have been re-forecast and are now all under $1 million: Customer information and billing system (regional various), Gippsland water factory membrane operating system cell liner upgrade program (Morwell), Moondarra regulated pines to natives plantation (Moondarra), Soil organic recycling facility asbestos landfill (Dutson), Warragul Drouin water – Tyssen treated water pump station capacity upgrade (Warragul), Warragul South high-level tank renewal (Warragul), Warragul sewer – desludge lagoons (Warragul), Warragul water – Labertouche water main (Warragul), Moe sewer – Yarragon township sewer pump station rising main and pump station capacity upgrade (Yarragon), Moe water – Increase treated water supply volume at Darnum (Moe), Warragul water treatment plant – increase size of sewer line from sludge lagoon to sewer system (Warragul).
Total existing projects | 507335 | 45786 | 53510.765 | 408038.235
Total Central Gippsland Region Water Corporation projects | 521714 | 47585 | 54396.055 | 419732.945
Source: Central Gippsland Region Water Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Drouin water – basin cover replacement (Drouin) | 1460 | 1460 | qtr 4 2018-19
Drouin water booster pumps (Drouin) | 2847 | 2847 | qtr 4 2018-19
Morwell sewer – Polden Crescent sewer pump station upgrade (Morwell) | 1085 | 1085 | qtr 4 2018-19
Sale water reticulation renewals (Sale) | 2650 | 2650 | qtr 4 2018-19
Sale water treatment plant high lift pump station upgrade (Sale) | 1037 | 1037 | qtr 4 2018-19
Saline waste outfall pipeline 5.5km stage 3 to South Gippsland Highway (regional various) | 2863 | 2863 | qtr 4 2018-19
Warragul – Moe water supply interconnect (water supply and demand strategy action 6) (Warragul) | 8238 | 8238 | qtr 4 2018-19
All remaining completed projects with a TEI less than $1 million | 6394 | 6394 | qtr 4 2018-19
Source: Central Gippsland Region Water Corporation
Central Highlands Region Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Fleet replacement program and building maintenance (regional various) | 2530 | 0 | 2530 | 0 | qtr 4 2020-21
Headworks improvements – construction (regional various) | 4237 | 0 | 4237 | 0 | qtr 4 2025-26
Information management implementation (regional various) | 2570.8 | 0 | 2570.8 | 0 | ongoing
Land development shared assets (regional various) | 1820 | 0 | 1820 | 0 | qtr 4 2022-23
Sewerage collection system upgrade (regional various) | 800 | 0 | 800 | 0 | qtr 4 2022-23
Waste water reticulation replacements (regional various) | 2918 | 0 | 2918 | 0 | qtr 4 2022-23
Waste water treatment plant upgrades (regional various) | 8570 | 0 | 8570 | 0 | qtr 4 2022-23
Water meters replacement (regional various) | 445 | 0 | 445 | 0 | qtr 4 2022-23
Water network upgrades (regional various) | 1200 | 0 | 1200 | 0 | qtr 4 2022-23
Water reticulation replacement (regional various) | 3186 | 0 | 3186 | 0 | qtr 4 2022-23
Water supply (tanks) renewal (regional various) | 1342 | 0 | 1342 | 0 | qtr 4 2022-23
Water treatment plant upgrade (regional various) | 460 | 0 | 460 | 0 | qtr 4 2022-23
Total new projects | 30078.8 | 0 | 30078.8 | 0
Source: Central Highlands Region Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Fleet replacement program and building maintenance (regional various) | 12822.046 | 4237 | 4237 | 4348.046 | ongoing
Project TEI has increased as a result of required fleet upgrades needing to meet 4-star safety ratings.
Headworks improvements – construction (regional various) | 51451.07 | 2570.8 | 2570.8 | 46309.47 | ongoing
Project TEI has increased due to several large raw water supply projects having been brought forward.
Information management implementation (regional various) | 17456.028 | 1820 | 1820 | 13816.028 | ongoing
Project TEI has increased due to higher costs associated with security upgrades.
Land development shared assets (regional various) | 3454.943 | 1342 | 1342 | 770.943 | ongoing
Sewerage collection system upgrade (regional various) | 32251.434 | 0 | 0 | 32251.434 | ongoing
Waste water reticulation and treatment scheme (regional various) | 33708.809 | 2918 | 2918 | 27872.809 | ongoing
Waste water reticulation replacements (regional various) | 20643.291 | 8570 | 8570 | 3503.291 | ongoing
Project TEI has increased reflecting the inclusion of accelerated pipe relinings and renewals, which have been found to be required earlier than anticipated as to meet service standards.
Waste water treatment plant upgrades (regional various) | 58257.306 | 445 | 445 | 57367.306 | ongoing
Project TEI has decreased due to a combination of deferred capital works as well as a more cost-effective and improved design having been identified.
Water meters replacement (regional various) | 5228.531 | 1200 | 1200 | 2828.531 | ongoing
Water network upgrades (regional various) | 12599.013 | 0 | 0 | 12599.013 | ongoing
Water quality improvement (regional various) | 6740.56 | 3186 | 3186 | 368.56 | ongoing
Water reticulation replacement (regional various) | 15713.074 | 460 | 460 | 14793.074 | ongoing
Project TEI has increased reflecting the inclusion of accelerated pipe relinings and renewals, which have been found to be required earlier than anticipated as to meet service standards.
Water supply (tanks) renewal (regional various) | 14733.99 | 800 | 800 | 13133.99 | ongoing
Water treatment plant upgrade (regional various) | 13901.93 | 0 | 0 | 13901.93 | ongoing
All remaining projects with a TEI less than $1 million | 6722.681 | 2530 | 2530 | 1662.681 | ongoing
Total existing projects | 305684.706 | 30078.8 | 30078.8 | 245527.106
Total Central Highlands Region Water Corporation projects | 335763.506 | 30078.8 | 60157.6 | 245527.106
Source: Central Highlands Region Water Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Fleet replacement program and building maintenance (regional various) | 2061 | 2061 | qtr 4 2018-19
Headworks improvements – construction (regional various) | 5945 | 5945 | qtr 4 2018-19
Information management implementation (regional various) | 2398.8 | 2398.8 | qtr 4 2018-19
Land development shared assets (regional various) | 1037 | 1037 | qtr 4 2018-19
Sewerage collection system upgrade (regional various) | 350 | 350 | qtr 4 2018-19
Waste water reticulation replacements (regional various) | 2692 | 2692 | qtr 4 2018-19
Waste water treatment plant upgrades (regional various) | 7020 | 7020 | qtr 4 2018-19
Water meters replacement (regional various) | 615 | 615 | qtr 4 2018-19
Water network upgrades (regional various) | 70 | 70 | qtr 4 2018-19
Water quality improvement (regional various) | 5 | 5 | qtr 4 2018-19
Water reticulation replacement (regional various) | 2402 | 2402 | qtr 4 2018-19
Water supply (tanks) renewal (regional various) | 3093 | 3093 | qtr 4 2018-19
Water treatment plant upgrade (regional various) | 405 | 405 | qtr 4 2018-19
Source: Central Highlands Region Water Corporation
City West Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Asset performance renewals - sewer 2019-2020 (metropolitan various) | 13256 | 0 | 13256 | 0 | ongoing
Asset performance renewals - water 2019-2020 (metropolitan various) | 17248 | 0 | 17248 | 0 | ongoing
Developer reimbursements - alternative water 2019-2020 (metropolitan various) | 2583 | 0 | 2583 | 0 | ongoing
Developer reimbursements - sewer 2019-2020 (metropolitan various) | 15216 | 0 | 15216 | 0 | ongoing
Developer reimbursements - water 2019-2020 (metropolitan various) | 6702 | 0 | 6702 | 0 | ongoing
Facility works 2019-2020 (metropolitan various) | 9038 | 0 | 9038 | 0 | ongoing
IT infrastructure expansion 2019-2020 (Footscray) | 11025 | 0 | 11025 | 0 | ongoing
Plant and equipment 2019-2020 (metropolitan various) | 2724 | 0 | 2724 | 0 | ongoing
Solar farm (Werribee) | 1200 | 0 | 1200 | 0 | ongoing
Various alternative water growth projects 2019-2020 (metropolitan various) | 3797 | 0 | 3797 | 0 | ongoing
Water metering 2019-2020 (metropolitan various) | 2190 | 0 | 2190 | 0 | ongoing
Total new projects | 84979 | 0 | 84979 | 0
Source: City West Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Customer management system (Footscray) | 2908 | 408 | 2500 | 0 | ongoing
Digital metering (metropolitan various) | 4232.239 | 3542.239 | 690 | 0 | ongoing
This project was originally forecast to have a TEI of less than $1 million and was therefore captured under ’All remaining projects with a TEI less than $1 million.’ This amount only represented seed funding for the project. Funding for the remainder of the project has since been approved, and therefore the project TEI has increased accordingly.
Land and property development system (Footscray) | 1000 | 0 | 1000 | 0 | ongoing
Mount Atkinson outlet sewer (Truganina) | 5939 | 0 | 2394 | 3545 | ongoing
Nicholson Street water distribution main renewal (Carlton) | 13500 | 1500 | 12000 | 0 | ongoing
Project TEI has increased due to adjustments to the forecast based on the latest information currently available.
Ravenhall outlet sewer (Melton) | 3191 | 0 | 191 | 3000 | ongoing
Project TEI has decreased due to the selection of an alternative route for the sewer outlet.
Records management system (Footscray) | 2914.916 | 1000 | 1914.916 | 0 | ongoing
Sewer strategy stage 2 (Melbourne) | 32500 | 3000 | 10000 | 19500 | ongoing
Project TEI has increased due to adjustments to the forecast based on the latest information currently available.
Stormwater harvesting (Werribee) | 3611.985 | 1169.5 | 2442.485 | 0 | ongoing
Project TEI has increased due to adjustments to the forecast based on the latest information currently available.
Tarneit West outlet sewer (section 1) (Tarneit) | 26797 | 0 | 0 | 26797 | ongoing
Transition of Oracle to the Cloud (Footscray) | 2000 | 0 | 0 | 2000 | ongoing
Upgrade to sewer pump station – SPS44 (Werribee) | 7510 | 500 | 7010 | 0 | ongoing
Project TEI has increased due to adjustments to the forecast based on the latest information currently available.
Total existing projects | 106104.14 | 11119.739 | 40142.401 | 54842
Total City West Water Corporation projects | 191083.14 | 11119.739 | 125121.401 | 54842
Source: City West Water Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Asset performance renewals – sewer (metropolitan various) | 11117.929 | 11117.929 | qtr 4 2018-19
Project TEI has decreased due to project contingencies not being required.
Asset performance renewals – water (metropolitan various) | 22620.385 | 22620.385 | qtr 4 2018 -19
Better planning allowed the project to achieve good momentum earlier than anticipated, resulting in a higher level of TEI being completed for the year.
Developer reimbursements – alternative water (metropolitan various) | 1810.844 | 1810.844 | qtr 4 2018-19
Developer reimbursements – sewer (metropolitan various) | 22681 | 22681 | qtr 4 2018-19
Project TEI has decreased due to project contingencies not being required.
Developer reimbursements – water (metropolitan various) | 2548.134 | 2548.134 | qtr 4 2018-19
Project TEI has decreased due to project contingencies not being required.
Facility works (metropolitan various) | 1282.721 | 1282.721 | qtr 4 2018-19
Project TEI has decreased due to project contingencies not being required.
IT infrastructure expansion (Footscray) | 13422 | 13422 | qtr 4 2018-19
Project TEI has increased due to some work being brought forward from the following year.
Plant and equipment (metropolitan various) | 1500 | 1500 | qtr 4 2018-19
Sanctuary Lakes stage 1 upgrade (Point Cook) | 5200 | 5200 | qtr 4 2018-19
Spencer Street sewer augmentation (Melbourne) | 21700 | 21700 | qtr 3 2018-19
Project TEI has decreased due to project contingencies not being required.
Water metering (metropolitan various) | 4329.779 | 4329.779 | qtr 4 2018-19
Project TEI has decreased due to project contingencies not being required.
Werribee West growth works (Werribee) | 181000 | 181000 | qtr 4 2018-19
Source: City West Water Corporation
Coliban Region Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Bendigo water treatment plant sludge drying beds upgrade (Bendigo) | 3398.0513 | 214.2173 | 410.182 | 2773.652 | qtr 4 2021-22
Laanecoorie raw water storage and pump station (Laanecoorie) | 2302.6598 | 129.9998 | 43.18 | 2129.48 | qtr 4 2020-21
Recycled water class A reconfiguration (Bendigo) | 2550.851 | 75 | 88.716 | 2387.135 | qtr 4 2021-22
Strathfieldsaye east sewer collection augmentation (Bendigo) | 1241.071 | 250 | 991.071 | 0 | qtr 2 2020-21
Water reclamation plant renewals and optimisation (regional various) | 5396 | 1238 | 616 | 3542 | ongoing
Water treatment plant renewals and optimisation (regional various) | 3408 | 572 | 460 | 2376 | ongoing
All remaining projects with a TEI less than $1 million | 22596 | 1211 | 1085.7423 | 20299.2576 | ongoing
Total new projects | 40892.6331 | 3690.2171 | 3694.8913 | 33507.5246
Source: Coliban Region Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Asset information management system enhancements and data (Bendigo) | 2612.9891 | 1259.1411 | 157.176 | 1196.672 | ongoing
Project expenditure has been revised in line with the project schedule.
Billing, customer, stakeholder management system (Bendigo) | 4165 | 3173.7564 | 991.052 | 0.19157 | qtr 2 2020-21
Project expenditure has been revised in line with the project schedule. Budget has been redirected from expenditure decrease in the project titled Intelligent business (regional various).
Castlemaine water network augmentation – water mains in Campbells Creek (Castlemaine) | 1060 | 0 | 0 | 1060 | qtr 4 2022-23
Project has been delayed due to competing priorities.
Channel renewals (regional various) | 2589.9063 | 815.1413 | 215.902 | 1558.863 | ongoing
Project expenditure has been revised in line with the project schedule to reflect the change in scope of the project.
Digital customer metering program (regional various) | 5444 | 1027.5378 | 992.179 | 3424.2832 | qtr 4 2022-23
Project expenditure has been revised in line with the project schedule. The increase in budget is due to project scope changes.
Echuca West tanks (Echuca) | 5520.987 | 110 | 871.457 | 4539.53 | qtr 4 2024-25
Project expenditure has been revised in line with the project schedule.
Echuca odour mitigation sewer pump station No.1 and sewer pump station No.11 (Echuca) | 1348.7135 | 228.7555 | 1119.958 | 0 | qtr 3 2019-20
Project expenditure has been revised in line with the project schedule.
Echuca water treatment plant additional clear water storage (Echuca) | 7871.2555 | 689.0185 | 1758.409 | 5423.828 | qtr 4 2021-22
Project expenditure has been revised in line with the project schedule. This project has been combined with another project titled ’Echuca water treatment plant booster pump upgrade (Echuca)’, which was reported as an ’Existing Project’ in the 2018-19 Budget.
Edwards Road tank to Strathfieldsaye water main (Bendigo) | 4303.728 | 45.612 | 58.402 | 4199.714 | qtr 4 2024-25
Project expenditure has been revised in line with the project schedule. Due to planning and design option analysis an appropriate solution has been determined significantly lower than original estimates.
Epsom Huntly water main extension (Bendigo) | 4428 | 0 | 0 | 4428 | qtr 4 2023-24
Project has been delayed due to competing priorities.
Epsom duplication of 375mm water main along Midland Highway (Bendigo) | 1412.48 | 10 | 0 | 1402.48 | qtr 4 2022-23
Project expenditure has been revised in line with the project schedule. The project expenditure has decreased due to revised project estimates.
Flow meters (Bendigo) | 1155 | 0 | 0 | 1155 | qtr 1 2023-24
Project has been delayed due to competing priorities.
Geographic information system (regional various) | 1515.3824 | 845.8784 | 84.792 | 584.712 | ongoing
Project expenditure has been revised in line with the project schedule.
Gifted assets labour overhead (Bendigo) | 4135.6726 | 1125.6696 | 358.92 | 2651.083 | ongoing
Project expenditure has been revised in line with the project schedule. Decrease in budget mainly due to improved internal efficiencies and alignment to developer scheduled works.
Heathcote backlog sewerage scheme (Heathcote) | 4813.0631 | 4466.0401 | 347.023 | 0 | qtr 1 2020-21
Project expenditure has been revised in line with the project schedule.
Heathcote water reclamation plant and reuse system upgrade (Heathcote) | 2442 | 233 | 148.14 | 2060.86 | qtr 4 2022-23
Project expenditure has been revised in line with the project schedule. Budget has been redirected to cover increased expenditure in the project titled ’Heathcote water treatment plant disinfection upgrade (Heathcote).’
Heathcote water treatment plant disinfection upgrade (Heathcote) | 4257.474 | 2196.502 | 2042.814 | 18.158 | qtr 4 2024-25
Project expenditure has been revised in line with the project schedule. Budget has been redirected from expenditure decrease in the project titled ’Heathcote water reclamation plant and reuse system upgrade (Heathcote).’
High-priority main channel replacements (regional various) | 5781.0228 | 64.7238 | 785.095 | 4931.204 | ongoing
Project expenditure has been revised in line with the project schedule. Increase in budget due to the inclusion of decommissioning into the project scope.
Inflow and infiltration (regional various) | 1092.9411 | 935.3931 | 19.627 | 137.921 | ongoing
Project expenditure has been revised in line with the project schedule. The decrease in expenditure relates to funds reprioritised to other renewal projects including Sewer main renewals (regional various) and operational programs.
Integrated water and sewer planning (regional various) | 8214.242 | 995 | 796.872 | 6422.37 | ongoing
This project has combined six previously reported projects, four with a TEI greater than $1 million ’Sewer network augmentation plans (regional various)’, ’Water network augmentation plans (regional various)’, ’Water treatment plant augmentation plans (regional various)’ and ’Water reclamation plant augmentation plans (regional various)’, and two projects previously reported in ’All remaining projects with a TEI less than $1 million’.
Intelligent business (regional various) | 7761.7708 | 2065.8138 | 709.604 | 4986.353 | ongoing
Project expenditure has been revised in line with the project schedule.
Kangaroo Flat gravity sewer construction (Bendigo) | 2372 | 0 | 0 | 2372 | qtr 1 2024-25
Project has been delayed due to competing priorities.
Kyneton water reclamation plant mechanical works (Kyneton) | 11218.7916 | 427.7326 | 785.096 | 10005.963 | qtr 4 2024-25
Project expenditure has been revised in line with the project schedule. Budget has increased due to an expanded scope and to be consistent with the revised estimated delivery expenditure.
Land management (regional various) | 3223.8193 | 2034.7343 | 232.545 | 956.54 | ongoing
Project expenditure has been revised in line with the project schedule.
Maiden Gully and Marong improve water pressures stage 1 (regional various) | 3701.3187 | 329.2587 | 1570.192 | 1801.868 | qtr 4 2020-21
Project expenditure has been revised in line with the project schedule. The project has been disaggregated into multiple projects including ’Marong tank 2ml and pump (Marong)’, reported as an ’Existing project’ and ’Maiden Gully and Marong improve water pressures stage 2 (regional various)’, reported as a ’New project’ with a TEI less than $1 million.
Marong tank 2ml and pump (Marong) | 5087.823 | 15.378 | 0 | 5072.445 | qtr 4 2020-21
Previously reported in ’All remaining projects with a TEI less than $1 million’.
Meter replacement program (regional various) | 3091.9633 | 2091.7193 | 172.72 | 827.524 | ongoing
Project expenditure has been revised in line with the project schedule.
Occupational health and safety remedial upgrades of main channel offtakes (regional various) | 2356.1335 | 1254.2695 | 511.097 | 590.767 | ongoing
Previously reported as completed in 2018-19. The project completion date has been updated to reflect the revised project schedule.
Occupational health and safety remedial works program remedial works program (regional various) | 6325.3066 | 3050.4826 | 533.864 | 2740.96 | ongoing
Project expenditure has been revised in line with the project schedule. Increase in budget due to high risk assets identified requiring remedial works.
Planned corrective reactive maintenance (regional various) | 15241.0368 | 7953.3418 | 911.372 | 6376.323 | ongoing
Project expenditure has been revised in line with the project schedule. Prior year savings have resulted in a significant decrease in the estimated budget compared to the previous budget.
Raw water systems investigations (regional various) | 2307.231 | 416.658 | 235.528 | 1655.045 | ongoing
Previously reported in ’All remaining projects with a TEI less than $1 million’. This project has now been prioritised as an ongoing program, which has resulted in an increased budget.
Sewer main renewals (regional various) | 10618.1771 | 6468.3341 | 508.744 | 3641.099 | ongoing
Project expenditure has been revised in line with the project schedule.
Sewer pumping station renewals (regional various) | 4008.7073 | 2018.1963 | 353.293 | 1637.218 | ongoing
Project expenditure has been revised in line with the project schedule. The increase in expenditure compared the prior year submission mainly relates to the omission of expenditure forecasts in 2019-20 and 2020-21, which have now been reprioritised for the 2019-20 budget.
Sludge handling Castlemaine water reclamation plant (Castlemaine) | 4838 | 0 | 0 | 4838 | qtr 4 2022-23
Project has been delayed due to revised timeframes.
Sludge processing upgrades Bendigo water reclamation plant (Bendigo) | 9438 | 0 | 79 | 9359 | qtr 4 2022-23
Project was delayed due to contract negotiations.
Superpipe (regional various) | 1342.0035 | 394.2135 | 84.792 | 862.998 | ongoing
Project expenditure has been revised in line with the project schedule. The decrease in expenditure mainly relates to the reprioritisation of works.
Supervisory control and data acquisition hardware (Bendigo) | 2283.1489 | 782.4689 | 356.852 | 1143.828 | ongoing
Project expenditure has been revised in line with the project schedule.
Supervisory control and data acquisition software and security (Bendigo) | 2302.7788 | 785.8258 | 83.534 | 1433.419 | ongoing
Project expenditure has been revised in line with the project schedule. Decrease in budget is mainly attributed to savings in prior years.
Vehicle renewals (regional various) | 2256.6504 | 1005.3774 | 152.048 | 1099.225 | ongoing
Project expenditure has been revised in line with the project schedule.
Water augmentation greenfield developments (regional various) | 1870 | 0 | 361 | 1509 | ongoing
Project has been delayed due to developer approvals.
Water main renewals (regional various) | 9765.2497 | 4849.7577 | 612.374 | 4303.118 | ongoing
Project expenditure has been revised in line with the project schedule.
Water reticulation tanks (regional various) | 1384.7948 | 723.0928 | 82.436 | 579.266 | ongoing
Previously reported in ’All remaining projects with a TEI less than $1 million’.
Water treatment plant programmable logic controller renewal program (regional various) | 1964.2904 | 474.0844 | 353.292 | 1136.914 | ongoing
Project expenditure has been revised in line with the project schedule.
All remaining projects with a TEI less than $1 million | 9424 | 3887.6892 | 668.384 | 4867.9268 | ongoing
This balance includes the projects ’Groundwater supply Goornong water treatment plant (Goornong)’, ’Heathcote water treatment plant taste and odour (Heathcote)’, ’Sewer augmentation greenfield developments (regional various)’, ’Strathfieldsaye water main duplication (Bendigo)’, and ’Water augmentation greenfield developments (regional various)’, as these projects now have forecast TEIs less than $1 million.
Total existing projects | 198346.8528 | 59249.5983 | 20105.585 | 118991.6696
Total Coliban Region Water Corporation projects | 239239.4859 | 62939.8154 | 23800.4764 | 152499.1942
Source: Coliban Region Water Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Bendigo recycled water scheme upgrade (Bendigo) | 1408.8811 | 1408.8811 | qtr 4 2018-19
This project was reported as completed in the 2018-19 Budget Paper No. 4, however it has since incurred additional expenditure during project finalisation, and is now scheduled for completion by 30 June 2019.
Bendigo water treatment plant sludge management – sewer upgrade (Bendigo) | 1212.3002 | 1212.3002 | qtr 2 2018-19
The project TEI decreased with respect to initial budget due to a business decision to deliver the next stage of the project through a new project. The new project titled ’Bendigo water treatment plant sludge drying beds upgrade (Bendigo)’ commenced in 2018-19 and is reported as an ’Existing project’ in this budget.
Bridgewater and Laanecoorie water treatment plant short term (regional various) | 4153.5873 | 4153.5873 | qtr 3 2018-19
This project was reported as completed in the 2018-19 Budget Paper No. 4, however it has since incurred additional expenditure during project finalisation, and is now scheduled for completion by 30 June 2019.
Cohuna water treatment plant clear water tank renewal (Cohuna) | 2209.5839 | 2209.5839 | qtr 4 2018 -19
This project was reported as completed in the 2018-19 Budget Paper No. 4, however it has since incurred additional expenditure during project finalisation, and is now scheduled for completion by 30 June 2019.
Coliban main channel renewals works (regional various) | 5273.1253 | 5273.1253 | qtr 4 2018-19
This project was reported as completed in the 2018-19 Budget Paper No. 4, however it has since incurred additional expenditure during project finalisation, and is now scheduled for completion by 30 June 2019.
Rural system reconfiguration (Harcourt) | 37715.1332 | 37715.1332 | qtr 3 2018-19
This project was reported as completed in the 2018-19 Budget Paper No. 4, however it has since incurred additional expenditure during project finalisation, and is now scheduled for completion by 30 June 2019.
Supervisory control and data acquisition data integrity (Bendigo) | 1319.8388 | 1319.8388 | qtr 4 2018-19
This project was reported as completed in the 2018-19 Budget Paper No. 4, however it has since incurred additional expenditure during project finalisation, and is now scheduled for completion by 30 June 2019.
Telemetry replacement (Bendigo) | 3561.7231 | 3561.7231 | qtr 4 2018-19
This project was reported as completed in the 2018-19 Budget Paper No. 4, however it has since incurred additional expenditure during project finalisation, and is now scheduled for completion by 30 June 2019.
Water reclamation plant maintenance (regional various) | 2099.271 | 2099.271 | qtr 4 2018-19
TEI decreased with respect to initial budget due to project scope changes.
Water treatment plant maintenance (regional various) | 2123.323 | 2123.323 | qtr 4 2018-19
TEI decreased with respect to initial budget due to project scope changes.
All remaining projects with a TEI less than $1 million | 8553.0764 | 8553.0764 | qtr 4 2018 -19
This balance includes the projects ’Echuca and Cohuna toxins, taste and odours (Echuca)’ and ’Sewer network augmentation plans (regional various)’ as these projects now have forecast TEIs less than $1 million.
Source: Coliban Region Water Corporation
Director of Housing (PNFC)
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Building new homes to fight homelessness (statewide) | 209099 | 0 | 33460 | 175639 | qtr 2 2022-23
Acquisition general construction 2019-20 (statewide) | 25231 | 0 | 25231 | 0 | qtr 4 2019-20
High rise upgrades in 2019-20 (metropolitan various) | 19270 | 0 | 19270 | 0 | qtr 4 2019-20
Low rise upgrade in 2019-20 (statewide) | 59026.8 | 0 | 59026.8 | 0 | qtr 4 2019-20
Oakover and Stokes/Penola stage 2 (Preston) | 15856.6 | 1373.9 | 75 | 14407.7 | qtr 3 2024-25
Social housing pipeline projects (statewide) | 14733.3 | 100 | 9400 | 5233.3 | qtr 4 2020-21
All remaining projects with a TEI of less than $1 million | 83442.289 | 0 | 83442.289 | 0 | qtr 4 2019-20
Total new projects | 426658.989 | 1473.9 | 229905.089 | 195280
Source: Director of Housing (PNFC)
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Acquisition of 10 units in South Division (statewide) | 3958.6 | 1708.6 | 2250 | 0 | qtr 4 2019-20
The project TEI has increased compared with the 2018-19 Budget due to escalation of construction costs.
Acquisition of 20 units in West Division (statewide) | 4520 | 3579 | 941 | 0 | qtr 1 2019-20
The project’s estimated completion date has been extended to quarter 1 2019-20 due to planning delays.
Acquisition of 38 units in North Division (statewide) | 8570 | 7080 | 1490 | 0 | qtr 3 2019-20
The project’s estimated completion date has been extended to quarter 3 2019-20 due to planning delays.
Carlton redevelopment – 246 units/sites (North-West metropolitan) | 146570 | 144063.6 | 506.4 | 2000 | qtr 2 2022-23
The project’s estimated completion date has been extended to quarter 2 2022-23 due to poor pre-sales of the private apartments.
Communal Family Violence Refuges – replacement and growth program (statewide) | 15000 | 13818.541 | 1181.459 | 0 | qtr 1 2019-20
The project’s estimated completion date has been extended to quarter 1 2019-20 due to planning delays.
Efficient Government Buildings (statewide) | 13385.5 | 13355.784 | 29.716 | 0 | qtr 1 2019-20
The project’s estimated completion date has been extended to quarter 1 2019-20 due to planning delays.
Family violence – Aboriginal refuges (statewide) | 8575 | 1635 | 6940 | 0 | qtr 4 2019-20
Family violence – refuge redevelopment (statewide) | 47902 | 8328.063 | 28500 | 11073.937 | qtr 4 2019-20
Flemington estate redevelopment (Flemington) | 30000 | 4217.616 | 2705.3 | 23077.084 | qtr 4 2022-23
The project’s cashflow has been revised due to procurement delays, however the TEI remains unchanged.
Heidelberg redevelopment – 600 units/sites (Heidelberg) | 160000 | 86974.327 | 21053.75 | 51971.923 | qtr 4 2022-23
The project’s cashflow has been revised due to town planning permit issues and inclement weather conditions. The project’s TEI remains unchanged.
High-rise fire sprinkler upgrade – stage 2 (metropolitan various) | 21682 | 4030 | 7407 | 10245 | qtr 2 2022-23
The project’s estimated completion date has been amended due to a publishing error in the 2018-19 Budget.
Markham Avenue estate redevelopment (Ashburton) | 2500 | 0 | 0 | 2500 | qtr 4 2028-29
Following revocation, further feasibility is being undertaken. The TEI and completion date are to be determined.
Public housing renewal program (statewide) | 185000 | 23065.4 | 10255.5 | 151679.1 | qtr 4 2028-29
Rooming houses upgrade (statewide) | 10000 | 3819.031 | 6180.969 | 0 | qtr 4 2019-20
The project’s estimated completion date has been extended to quarter 4 2019-20 due to planning issues.
Westmeadows redevelopment – 144 units/sites (Westmeadows) | 74512.426 | 62550.126 | 8662.3 | 3300 | qtr 4 2020-21
The project’s TEI has increased due to escalation of construction costs. The estimated completion date has been extended to quarter 4 2020-21 due to delays in executing the development agreement.
Total existing projects | 732175.526 | 378225.088 | 98103.394 | 255847.044
Total Director of Housing (PNFC) projects | 1158834.515 | 379698.988 | 328008.483 | 451127.044
Source: Director of Housing (PNFC)
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Aboriginal transitional housing (statewide) | 2689 | 2689 | qtr 4 2018-19
Acquisition of 16 units in South Division (statewide) | 5596 | 5596 | qtr 4 2018-19
High-rise fire sprinkler upgrade – stage 1 (metropolitan various) | 3000 | 3000 | qtr 4 2018-19
High-rise upgrades in 2018-19 (metropolitan various) | 22095 | 22095 | qtr 4 2018-19
Preston redevelopment stage 1 (Preston) | 23500 | 23500 | qtr 4 2018-19
Rooming houses upgrade program (metropolitan various) | 10000 | 10000 | qtr 4 2018-19
All remaining projects with TEI of less than $1 million | 129538 | 129538 | qtr 4 2018-19
Source: Director of Housing (PNFC)
East Gippsland Region Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Raising winter storage embankment/ increase irrigation (Paynesville) | 3531 | 0 | 85 | 3446 | qtr 4 2022-23
Rising main replacement (Bairnsdale) | 1180 | 0 | 180 | 1000 | qtr 4 2021-22
Sarsfield tanks to Johnsonville main supply pipeline upgrade (Bairnsdale) | 1235 | 0 | 1235 | 0 | qtr 4 2019-20
All remaining projects with a TEI less than $1 million | 1250 | 0 | 1250 | 0 | qtr 4 2018-19
Total new projects | 7196 | 0 | 2750 | 4446
Source: East Gippsland Region Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
The project ’Energy efficiency upgrades (regional various)’ has not been individually listed, as the project TEI is now below $1 million due to the project scope having since been reduced. It is included in this balance.
Clear water storage augmentation (Sarsfield) | 2606 | 410 | 2196 | 0 | qtr 4 2019-20
This project did not appear in the 2018-19 Budget Paper No. 4, as it had been originally scheduled as a new project for 2019-20. As a result of project priority analysis following the 2018-19 Budget, this project has since been brought forward and commenced in 2018-19.
Developer financed works – wastewater (regional various) | 2100 | 300 | 300 | 1500 | ongoing
Developer financed works – water (regional various) | 1400 | 200 | 200 | 1000 | ongoing
Mitchell water master plan – Wy Yung Basin tank or liner (Bairnsdale) | 11250 | 500 | 5750 | 5000 | qtr 4 2019-20
All remaining projects with a TEI less than $1 million | 14314.0482 | 8867.0482 | 5447 | 0 | qtr 4 2018-19
Total existing projects | 31670.0482 | 10277.0482 | 13893 | 7500
Total East Gippsland Region Water Corporation projects | 38866.0482 | 10277.0482 | 16643 | 11946
Source: East Gippsland Region Water Corporation
Gippsland and Southern Rural Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
All remaining projects with a TEI less than $1 million | 1833.158 | 0 | 447.355 | 1385.803 | ongoing
Total new projects | 1833.158 | 0 | 447.355 | 1385.803
Source: Gippsland and Southern Rural Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Bacchus Marsh Irrigation District modernisation (Bacchus Marsh) | 13020 | 11914.801 | 671.857 | 433.342 | ongoing
MID 2030: modernising the Macalister Irrigation District (Gippsland) Phase 1B | 60000 | 47786.548 | 8735.613 | 3477.839 | ongoing
Werribee Irrigation District modernisation (Werribee) | 31320 | 26810.607 | 4115.222 | 394.171 | ongoing
All remaining projects with a TEI less than $1 million | 22977.643 | 3731.4927 | 4868.434 | 14377.7164 | ongoing
Total existing projects | 127317.643 | 90243.4487 | 18391.126 | 18683.0683
Total Gippsland and Southern Rural Water Corporation projects | 129150.801 | 90243.4487 | 18838.481 | 20068.8713
Source: Gippsland and Southern Rural Water Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
All remaining projects with a TEI less than $1 million | 12423.9152 | 12423.9152 | qtr 4 2017-18
Source: Gippsland and Southern Rural Water Corporation
Goulburn Murray Rural Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
All remaining projects with a TEI less than $1 million | 12544 | 0 | 12544 | 0 | various
Total new projects | 12544 | 0 | 12544 | 0
Source: Goulburn Murray Rural Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Connections project (regional various) | 1099986.137 | 1053016.137 | 46970 | 0 | qtr 2 2020-21
ICT enhancement projects (regional various) | 29873.604 | 9921.64 | 2872.24 | 17079.724 | various
Linear program (regional various) | 85515.998 | 39254.012 | 3937.61 | 42324.376 | various
Project TEI has increased due to revised scope and work program.
Structure program (regional various) | 76532.424 | 33167.497 | 7088.274 | 36276.653 | various
Project TEI has increased due to revised scope and work program.
Total existing projects | 1291908.163 | 1135359.286 | 60868.124 | 95680.753
Total Goulburn Murray Rural Water Corporation projects | 1304452.163 | 1135359.286 | 73412.124 | 95680.753
Source: Goulburn Murray Rural Water Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Cairn Curran outlet works upgrade stage 2 electrical (Cairn Curran) | 1780.7741 | 1780.7741 | qtr 4 2018-19
All remaining projects with a TEI less than $1 million | 13011.9609 | 13011.9609 | qtr 4 2018-19
Source: Goulburn Murray Rural Water Corporation
Goulburn Valley Region Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Digital infrastructure projects (regional various) | 1500 | 0 | 75 | 1425 | ongoing
Water treatment plant augmentation stage 3 (Cobram) | 3715 | 0 | 0 | 3715 | qtr 4 2026-27
All remaining projects with a TEI less than $1 million | 1672 | 0 | 100 | 1572 | various
Total new projects | 6887 | 0 | 175 | 6712
Source: Goulburn Valley Region Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Above ground asset replacement (regional various) | 10500 | 500 | 500 | 9500 | ongoing
As part of an annual capital expenditure review, projects are reassessed in terms of project nature and scope of works. As a result, this may impact project TEI and anticipated completion date.
Asset acquisitions – corporate assets (regional various) | 41825 | 2000 | 1825 | 38000 | ongoing
As part of an annual capital expenditure review, projects are reassessed in terms of project nature and scope of works. As a result, this may impact project TEI and anticipated completion date.
Asset acquisitions – digital assets (regional various) | 10100 | 600 | 475 | 9025 | ongoing
As part of an annual capital expenditure review, projects are reassessed in terms of project nature and scope of works. As a result, this may impact project TEI and anticipated completion date.
Asset management information system replacement (regional various) | 2405 | 300 | 950 | 1155 | qtr 4 2020-21
Clear water storage augmentation (Shepparton) | 3455 | 0 | 0 | 3455 | qtr 4 2036-37
TEI has been reviewed in line with current requirements.
Corporate office upgrades (Shepparton) | 2200.209 | 100 | 250 | 1850.209 | qtr 4 2023-24
Project approved and commenced during 2018-19.
Councils – water and sewer (regional various) | 8700 | 700 | 400 | 7600 | ongoing
The presentation of council works may change from time to time to reflect more accurate running rates.
Customer billing/customer relationship management system replacement – digital strategy (regional various) | 3000 | 0 | 100 | 2900 | qtr 4 2023-24
The estimated completion date has been extended to quarter 4 2023-24.
DN375 direct feed water main to south tank (Shepparton) | 3970 | 0 | 0 | 3970 | qtr 4 2025-26
TEI has been reviewed in line with current requirements.
DN375 water main south of Raftery road (Shepparton) | 1650 | 0 | 0 | 1650 | qtr 4 2030-31
TEI has been reviewed in line with current requirements.
DN450 trunk water main south of Kialla Lakes drive (Shepparton) | 1145 | 0 | 0 | 1145 | qtr 4 2026-27
TEI has been reviewed in line with current requirements and project completion date has been extended to quarter 4 2026-27.
Energy performance program – climate change mitigation program (regional various) | 2018 | 497 | 306 | 1215 | qtr 4 2023-24
TEI has been revised to achieve project objective.
Finance system upgrade (regional various) | 2687.082 | 700 | 500 | 1487.082 | qtr 4 2019-20
The project completion date and TEI has been revised as a result of issues identified during software implementation. Project reference changed from 1 506 published in the 2018-19 Budget.
Fryers street office relocation (Shepparton) | 6565 | 0 | 0 | 6565 | qtr 4 2031-32
TEI has been reviewed in line with current requirements and project completion date has been extended to quarter 4 2031-32.
Gooram pipeline replacement (Euroa) | 5567.778 | 91 | 0 | 5476.778 | qtr 4 2024-25
TEI has been revised as a result of change in project scope.
Intangible assets, standards, policies and frameworks (regional various) | 1100 | 50 | 100 | 950 | ongoing
Project approved and commenced during 2018-19.
Intelligent metering (regional various) | 2280 | 135 | 750 | 1395 | qtr 4 2021-22
TEI has been revised to achieve project objective.
Landowner reticulation works – sewer (regional various) | 63500 | 3500 | 3000 | 57000 | ongoing
The presentation of developer works may change from time to time to reflect more accurate running rates.
Landowner reticulation works – water (regional various) | 42500 | 2500 | 2000 | 38000 | ongoing
The presentation of developer works may change from time to time to reflect more accurate running rates.
Lemnos pump station upgrade (Shepparton) | 1891 | 0 | 0 | 1891 | qtr 4 2028-29
TEI has been reviewed in line with current requirements.
McLennan street pump station upgrade (Mooroopna) | 1730 | 0 | 0 | 1730 | qtr 4 2030-31
TEI has been reviewed in line with current requirements.
McLennan street water main augmentation (Mooroopna) | 1665 | 0 | 0 | 1665 | qtr 4 2034-35
TEI has been reviewed in line with current requirements.
Microbial risk reduction (regional various) | 15747.98 | 0 | 200 | 15547.98 | qtr 4 2027-28
TEI has been revised to achieve project objective.
Minor infrastructure items (regional various) | 5781 | 200 | 546 | 5035 | ongoing
As part of an annual capital expenditure review, projects are reassessed in terms of project nature and scope of works. As a result, this may impact project TEI and anticipated completion date.
Non potable upgrades (regional various) | 2115 | 0 | 0 | 2115 | qtr 4 2024-25
Non revenue bulk flow meters upgrade and replacement (regional various) | 2015 | 95 | 95 | 1825 | ongoing
As part of an annual capital expenditure review, projects are reassessed in terms of project nature and scope of works. As a result, this may impact project TEI and anticipated completion date.
Occupational health and safety initiatives (regional various) | 1100 | 0 | 150 | 950 | ongoing
As part of an annual capital expenditure review, projects are reassessed in terms of project nature and scope of works. As a result this may impact project TEI and anticipated completion date.
Old Dookie road water main (Shepparton) | 1071.877 | 0 | 0 | 1071.877 | qtr 4 2028-29
Project scope revised, previously included under projects with TEI less than $1 million in the 2018-19 Budget.
Outfall rising main replacement (Shepparton) | 3409.636 | 1386 | 1100 | 923.636 | qtr 4 2020-21
TEI has been reduced, project forecast to be delivered under budget and project completion date has been extended to quarter 4 2020-21.
Pipeline construction (Broadford/Kilmore) | 15960 | 0 | 0 | 15960 | qtr 4 2029-30
TEI has been revised to achieve project objective.
Raw water pump station augmentation (Shepparton) | 1286.142 | 137 | 662 | 487.142 | qtr 4 2020-21
TEI has been reduced, project forecast to be delivered under budget and project completion date has been revised to quarter 4 2020-21.
Renewables program – climate change mitigation program (regional various) | 8003.554 | 300 | 3581 | 4122.554 | qtr 4 2022-23
TEI has been revised to achieve project objective.
Replacement of Abbinga reservoir (Euroa) | 3600 | 142 | 2652 | 806 | qtr 4 2020-21
The estimated completion date has been postponed to meet operational requirements.
Sewer pump station – 01 rising main replacement (Seymour) | 4499.611 | 12 | 0 | 4487.611 | qtr 4 2024-25
TEI has been reviewed in line with current requirements and project completion date has been extended to quarter 4 2024-25.
Sewer pump station – 04 pump station and rising main upgrade (Nagambie) | 3057.18 | 121 | 611 | 2325.18 | qtr 4 2022-23
Project completion date has been extended to quarter 4 2022-23.
Sewer relining program – blockage prevention (regional various) | 16985 | 965 | 965 | 15055 | ongoing
As a part of annual capital expenditure review projects are reassessed in terms of project nature and scope of works. As a result this may impact project TEI and anticipated completion date.
Sewer relining program – collapse prevention (regional various) | 26440 | 1000 | 1000 | 24440 | ongoing
As part of an annual capital expenditure review, projects are reassessed in terms of project nature and scope of works. As a result this may impact project TEI and anticipated completion date.
Sewer relining program – manhole rehabilitation (regional various) | 2835 | 168 | 168 | 2499 | ongoing
As part of an annual capital expenditure review, projects are reassessed in terms of project nature and scope of works. As a result this may impact project TEI and anticipated completion date.
Sewer rising main no.1 replacement (Euroa) | 2190.139 | 91 | 150 | 1949.139 | qtr 4 2022-23
The estimated completion date has been extended to quarter 4 2022-23.
Shared assets – sewer (regional various) | 8365 | 365 | 400 | 7600 | ongoing
The presentation of shared works may change from time to time to reflect more accurate running rates.
Shared assets – water (regional various) | 8355 | 355 | 400 | 7600 | ongoing
The presentation of shared works may change from time to time to reflect more accurate running rates.
Shepparton operation centre 14ml tank floor replacement (Shepparton) | 2210 | 50 | 100 | 2060 | qtr 4 2022-23
TEI has been revised to achieve project objective and project completion date extended to quarter 4 2022-23.
Shepparton south tank pump station upgrade (Shepparton) | 1555 | 0 | 0 | 1555 | qtr 4 2023-24
TEI has been reviewed in line with current requirements.
South sewer pump station rising main stage 4 (Kialla Lakes) | 1480 | 0 | 0 | 1480 | qtr 4 2024-25
Supervisory control and data acquisition infrastructure replacement (regional various) | 9985 | 0 | 0 | 9985 | qtr 4 2027-28
The estimated completion date has been extended to quarter 4 2027-28.
Switchboard replacements (regional various) | 8500 | 400 | 405 | 7695 | ongoing
As part of an annual capital expenditure review, projects are reassessed in terms of project nature and scope of works. As a result this may impact project TEI and anticipated completion date.
Waste management facility additional winter storage (Kilmore) | 5215.351 | 0 | 0 | 5215.351 | qtr 4 2026-27
TEI has reduced due to an alternate solution.
Waste management facility additional winter storage (Mansfield) | 3095 | 0 | 0 | 3095 | qtr 4 2027-28
Waste management facility additional winter storage and irrigation area (Tongala) | 2020 | 0 | 0 | 2020 | qtr 4 2036-37
TEI has been reviewed in line with current requirements and project completion date has been extended to quarter 4 2036-37.
Waste management facility high rate anaerobic lagoon cover replacement (Shepparton) | 7155.641 | 495 | 4367 | 2293.641 | qtr 4 2021-22
TEI has been revised to achieve project objective and project completion date extended to quarter 4 2021-22.
Waste management facility high rate anaerobic lagoon replacement (Mooroopna) | 1955 | 0 | 0 | 1955 | qtr 4 2024-25
TEI has been reviewed in line with current requirements and project completion date has been extended to quarter 4 2024-25.
Waste management facility inlet works upgrades (regional various) | 2547.897 | 140 | 105 | 2302.897 | qtr 4 2019-20
TEI has been reviewed in line with current requirements and project completion date has been postponed to quarter 4 2019-20.
Waste management facility irrigation capacity upgrade (Broadford) | 1669 | 0 | 0 | 1669 | qtr 4 2025-26
TEI has been revised to achieve project objective.
Waste management facility irrigation capacity upgrade (Yea) | 2037 | 0 | 0 | 2037 | qtr 4 2030-31
TEI has been reviewed in line with current requirements.
Waste management facility lagoon 6 refurbishment (Alexandra) | 1387 | 0 | 0 | 1387 | qtr 4 2034-35
TEI has been revised to achieve project objective.
Waste management facility offsets project (Kilmore) | 15550.558 | 5000 | 6302 | 4248.558 | qtr 4 2021-22
TEI has been revised based on awarded contract costs.
Waste management facility offsets project (Mansfield) | 4741 | 240 | 400 | 4101 | qtr 4 2023-24
The estimated completion date has been extended to quarter 4 2023-24.
Waste management facility winter storage capacity upgrade (Shepparton) | 1350 | 0 | 0 | 1350 | qtr 4 2028-29
Water mains replacement (regional various) | 72205 | 2000 | 2000 | 68205 | ongoing
As part of an annual capital expenditure review, projects are reassessed in terms of project nature and scope of works. As a result this may impact project TEI and anticipated completion date.
Water meters replacement (regional various) | 8400 | 325 | 370 | 7705 | ongoing
As part of an annual capital expenditure review, projects are reassessed in terms of project nature and scope of works. As a result this may impact project TEI and anticipated completion date.
Water meters stock (regional various) | 1890 | 90 | 90 | 1710 | ongoing
As part of an annual capital expenditure review, projects are reassessed in terms of project nature and scope of works. As a result this may impact project TEI and anticipated completion date.
Water network augmentation – stage 2 (Alexandra) | 1345 | 0 | 0 | 1345 | qtr 4 2023-24
Water treatment plant capacity upgrade (Tatura) | 7700.004 | 5100 | 1332 | 1268.004 | qtr 4 2020-21
TEI has been reduced. Project forecast to be delivered under budget and project completion date has been extended to quarter 4 2020-21.
Water treatment plant capacity upgrade (Yea) | 2040 | 0 | 0 | 2040 | qtr 4 2030-31
Project scope revised. Previously included under projects with TEI less than $1 million in the 2018-19 Budget.
Water treatment plant improvement works (Shepparton) | 1210 | 0 | 0 | 1210 | qtr 4 2027-28
TEI has been reviewed in line with current requirements.
Water treatment plant optimisation (regional various) | 12400 | 600 | 500 | 11300 | ongoing
As part of an annual capital expenditure review, projects are reassessed in terms of project nature and scope of works. As a result this may impact project TEI and anticipated completion date.
Water treatment plant upgrade (Broadford) | 7498.739 | 98 | 230 | 7170.739 | qtr 4 2024-25
TEI has been revised to achieve project objective.
Water treatment plant upgrade (Mansfield) | 5535 | 0 | 0 | 5535 | qtr 4 2025-26
TEI has been revised to achieve project objective.
Water treatment plant upgrade (Nathalia) | 11274 | 0 | 0 | 11274 | qtr 4 2026-27
TEI has been reviewed in line with current requirements.
All remaining projects with a TEI less than $1 million | 35691.901 | 4065 | 6083 | 25543.901 | various
Some projects listed in last year’s budget are not listed this year as they either have not progressed to final approval and commencement stage or the TEI is now less than $1 million.
Total existing projects | 592914.279 | 35613 | 46120 | 511181.279
Total Goulburn Valley Region Water Corporation projects | 599801.279 | 35613 | 46295 | 517893.279
Source: Goulburn Valley Region Water Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Additional waste management facility winter storage stage 2 (Tatura) | 3804.737 | 3804.737 | qtr 4 2018-19
The estimated completion date has been extended to quarter 4 2018-19.
Clear water storage augmentation (Euroa) | 1783.763 | 1783.763 | qtr 4 2018-19
The estimated completion date has been extended to quarter 4 2018-19.
Clear water storage augmentation (Nathalia) | 2015.268 | 2015.268 | qtr 4 2018-19
TEI has been reduced. Project forecast to be delivered under budget.
Duplication of the Shepparton-Mooroopna transfer pipeline (Mooroopna) | 2030 | 0 | qtr 4 2018-19
This project is no longer going ahead.
Raw water storage augmentation (Euroa) | 8687.549 | 8687.549 | qtr 4 2018-19
TEI has been revised due to acquisition of land.
Supply main replacement (Dookie) | 679 | 679 | qtr 4 2018-19
Budget carryover from a completed project will be used to fund a new project.
Waste management facility additional irrigation area (Kilmore) | 1100 | 0 | qtr 4 2018-19
This project is no longer proceeding.
Water treatment plant augmentation stage 2 (Cobram) | 2326.756 | 2326.756 | qtr 4 2018-19
Project completion date has been brought forwarded to quarter 4 2018-19. TEI has been reduced by $3.5 million which has been redirected to stage 3 and initiated as a new project in the 2019-20 Budget.
Water treatment plant sludge management (Euroa) | 1275.164 | 1275.164 | qtr 4 2018-19
TEI has been revised due to additional works identified during defects liability period.
All remaining projects with a TEI less than $1 million | 3058.175 | 3058.175 | various
Source: Goulburn Valley Region Water Corporation
Grampians Wimmera Mallee Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
East Grampians rural water supply (East Grampians) | 43822.0904 | 1702.4988 | 14040 | 28079.5916 | qtr 4 2020-21
Water quality upgrade (Ultima) | 1683.3595 | 0 | 200 | 1483.3595 | qtr 4 2020-21
Total new projects | 45505.4498 | 1702.4988 | 14240 | 29562.951
Source: Grampians Wimmera Mallee Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Dam safety works (regional various) | 1899.4654 | 706.0885 | 229.1668 | 964.2101 | ongoing
Embankment rehabilitation (Lake Fyans) | 2774.8875 | 0 | 0 | 2774.8875 | qtr 4 2020-21
TEI has decreased due to revised scope and costing.
Headworks structure renewals (regional various) | 3333.529 | 1024.6642 | 599.9996 | 1708.8652 | ongoing
Office and depot renewals (regional various) | 1065.795 | 686.3247 | 125 | 254.4703 | ongoing
TEI has increased to over $1 million due to revised project scope and costing.
Renewable energy projects (regional various) | 3684.1146 | 2513.1128 | 1171.0018 | 0 | qtr 4 2019-20
TEI has increased to over $1 million due to revised project scope and costing.
Rural water supply project (South West Loddon) | 87783.571 | 79329.571 | 8454 | 0 | qtr 4 2019-20
Sewer mains – replacement and other works (regional various) | 10804.9588 | 4375.2238 | 1935.0137 | 4494.7213 | ongoing
Sewerage schemes (Goroke) | 1395 | 70 | 1325 | 0 | qtr 4 2019-20
Urban remote metering and customer portal (regional various) | 6881.3584 | 2064.4075 | 4816.9509 | 0 | qtr 4 2019-20
Project TEI has increased because this now includes meter replacement programs listed in last year’s budget.
Waste water treatment plant upgrades (regional various) | 10406.2817 | 1388.4025 | 3431.642 | 5586.2372 | ongoing
Water mains – replacement and other works (regional various) | 17142.5832 | 3314.7666 | 3537.8617 | 10289.9549 | ongoing
TEI has increased due to revised project scope and costing.
Water treatment plant major infrastructure (regional various) | 7624.2709 | 1182.0857 | 1335.5839 | 5106.6012 | ongoing
Water treatment plant upgrades – health-based treatment targets (regional various) | 2971.0452 | 0 | 200 | 2771.0452 | qtr 4 2021-22
Water treatment plant upgrades and modernisation (regional various) | 1444.6668 | 357.252 | 422.7949 | 664.6198 | ongoing
TEI has increased to over $1 million due to revised project scope and costing.
All remaining projects with a TEI less than $1 million | 18886.4388 | 4085.8702 | 3664.013 | 11136.5557 | ongoing
TEI includes Domestic and stock water pump stations renewals (regional various) listed in last year’s budget, because the project TEI has been reduced to less than $1 million. TEI also includes New water treatment facilities (regional various) from last year, because this project has now been split into specific water treatment projects with TEIs less than $1 million.
Total existing projects | 178097.9661 | 101097.7695 | 31248.0281 | 45752.1685
Total Grampians Wimmera Mallee Water Corporation projects | 223603.416 | 102800.2683 | 45488.0281 | 75315.1195
Source: Grampians Wimmera Mallee Water Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Mallee town treated water supply projects (Sea Lake, Brim, Beulah, Woomelang) | 17488.0854 | 17488.0854 | qtr 4 2018-19
This project was listed as completed last year. However, the project TEI has been increased due to revised scope and costing and will therefore be completed in 2018-19.
Regulated flow metering and structure upgrades (regional various) | 1770.7784 | 1770.7784 | qtr 4 2018-19
TEI has increased to over $1 million due to revised project scope and costing.
All remaining projects with a TEI less than $1 million | 547.4789 | 547.4789 | qtr 4 2018-19
Source: Grampians Wimmera Mallee Water Corporation
Lower Murray Urban Rural Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Irrigation – main replacements (regional various) | 7755 | 320 | 1860 | 5575 | qtr 4 2022-23
Total new projects | 7755 | 320 | 1860 | 5575
Source: Lower Murray Urban Rural Water Corporation
Existing projects(a)
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Irrigation – minor capital – replacement (Mildura) | 4285 | 365 | 1055 | 2865 | qtr 4 2022-23
TEI has increased due to revised project scope and costing.
Irrigation – replace central pump station rising main (Mildura) | 2500 | 2500 | 0 | 0 | qtr 4 2019-20
TEI has decreased due to revised project scope and costing.
Main replacements (regional various) | 6360 | 150 | 850 | 5360 | qtr 4 2022-23
TEI has increased due to revised project scope and costing.
Mildura West water treatment plant upgrade to clear scada (Mildura) | 600 | 0 | 600 | 0 | qtr 4 2019-20
Mildura water treatment plant 7th Street upgrade power supply (Mildura) | 1500 | 800 | 700 | 0 | qtr 4 2019-20
Purchase of water (regional) | 4320 | 0 | 1080 | 3240 | qtr 4 2022-23
Rehabilitation of sewers (regional various) | 4300 | 0 | 1000 | 3300 | qtr 4 2022-23
Sewer – all sites gifted assets (regional various) | 3200 | 0 | 800 | 2400 | qtr 4 2022-23
Sewer – all sites minor capital works – new (regional various) | 1030 | 30 | 250 | 750 | qtr 4 2022-23
Sewer – all sites minor capital works – replacement (regional various) | 2250 | 250 | 475 | 1525 | qtr 4 2022-23
Sewer – waste water treatment plant upgrade to clear SCADA (Koorlong) | 1200 | 0 | 100 | 1100 | qtr 4 2022-23
Sewer – all sites land development (regional various) | 1000 | 0 | 250 | 750 | qtr 4 2022-23
Sewer – waste water treatment plant construct 400 ML wet weather storage no 1 (Koorlong) | 3500 | 1000 | 2500 | 0 | qtr 4 2019-20
Water – all sites minor capital works – new (regional various) | 1120 | 120 | 250 | 750 | qtr 4 2022-23
Water – all sites land development (regional various) | 1000 | 0 | 250 | 750 | qtr 4 2022-23
Water – all sites minor capital works – replacement (regional various) | 1150 | 30 | 310 | 810 | qtr 4 2022-23
Water – gifted assets (regional various) | 1600 | 0 | 400 | 1200 | qtr 4 2022-23
Water – ultra violet all treatment plants (regional various) | 7430 | 830 | 0 | 6600 | qtr 4 2022-23
Water – water treatment plant 6 ML ground level storage (Swan Hill North) | 3100 | 0 | 0 | 3100 | qtr 4 2020-21
Water – water treatment plant treated water pump station (stage 1) (Swan Hill North) | 1600 | 0 | 0 | 1600 | qtr 4 2020-21
All remaining projects with a TEI less than $1 million | 16635 | 4350 | 3935 | 8350 | qtr 4 2022-23
TEI includes Minor irrigation capital works – replacement (regional various) which was listed in last year’s budget, because project TEI has now decreased to less than $1 million.
Total existing projects | 69680 | 10425 | 14805 | 44450
Total Lower Murray Urban Rural Water Corporation projects | 77435 | 10745 | 16665 | 50025
Source: Lower Murray Urban Rural Water Corporation
Note:-
(a) All project forecasts have undergone revision to ensure project scope and costs are still relevant. Project scope and costs have been updated to reflect project current status.
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Irrigation – main replacements (regional various) | 1076.22 | 1076.22 | qtr 4 2018-19
TEI has increased to over $1 million due to revised project scope and costing.
Main replacements (regional various) | 1174.437 | 1174.437 | qtr 4 2018-19
Rehabilitation of sewers (regional various) | 974.354 | 974.354 | qtr 4 2018-19
Replacement of sewerage outfall main Blackwire Road (Swan Hill) | 1834.2 | 1834.2 | qtr 4 2018-19
Waste water treatment plant carousel repairs (regional various) | 1019 | 1019 | qtr 4 2018-19
Water – treated water pump station (Kerang) | 952.765 | 952.765 | qtr 4 2018-19
Water – water treatment plant logic control automation (Kerang) | 1231.971 | 1231.971 | qtr 4 2018-19
All remaining projects with a TEI less than $1 million | 9909 | 9909 | qtr 4 2018-19
Source: Lower Murray Urban Rural Water Corporation
Melbourne Water Corporation(a)
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Corporate support projects (statewide) | 51713 | 0 | 1490 | 50223 | ongoing
Drainage and flood projects (statewide) | 335639 | 0 | 11186 | 324453 | ongoing
Eastern treatment plant projects (Bangholme) | 530012 | 0 | 2280 | 527732 | ongoing
Information technology projects (statewide) | 174272 | 0 | 10230 | 164042 | ongoing
Land development projects (statewide) | 828189 | 0 | 35194 | 792995 | ongoing
Sewerage transfer projects (statewide) | 351431 | 0 | 3723 | 347708 | ongoing
Water production and storage projects (statewide) | 160742 | 0 | 1068 | 159674 | ongoing
Water quality projects (statewide) | 121095 | 0 | 0 | 121095 | ongoing
Water transfer projects (statewide) | 367730 | 0 | 5589 | 362141 | ongoing
Waterways condition projects (statewide) | 172330 | 0 | 1613 | 170717 | ongoing
Waterways stormwater quality projects (statewide) | 187784 | 0 | 4700 | 183084 | ongoing
Western treatment plant projects (Werribee) | 650900 | 0 | 1420 | 649480 | ongoing
All remaining projects with a TEI less than $1 million | 49208 | 0 | 23557 | 25651 | ongoing
Total new projects | 3981045 | 0 | 102050 | 3878995
Source: Melbourne Water Corporation
Note:-
(a) Melbourne Water Corporation structures its projects as programs of work, which comprise new, existing and completed components year on year. The TEI for the programs of work identified in the 2019-20 Budget includes three years forward following the final budget year, and three years preceding the first budget year. The TEIs for the programs of work are therefore likely to differ significantly between budget years, as forecasts are revised continuously.
Existing projects(a)
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Corporate support projects (statewide) | 60493 | 17845 | 9574 | 33074 | ongoing
This project was previously listed as Corporate projects (statewide) in the 2018-19 Budget.
Drainage and flood projects (statewide) | 103682 | 42127 | 15424 | 46131 | ongoing
Eastern treatment plant projects (Bangholme) | 304281 | 89366 | 92031 | 122884 | ongoing
Information technology projects (statewide) | 35312 | 6304 | 11083 | 17925 | ongoing
Land development projects (statewide) | 371941 | 156961 | 50397 | 164583 | ongoing
Sewerage transfer projects (statewide) | 562252 | 187168 | 46562 | 328522 | ongoing
Water production and storage projects (statewide) | 204369 | 63339 | 85061 | 55969 | ongoing
Water quality projects (statewide) | 118144 | 37729 | 12784 | 67631 | ongoing
Water transfer projects (statewide) | 510297 | 235183 | 38137 | 236977 | ongoing
Waterways condition projects (statewide) | 87482 | 40431 | 19460 | 27591 | ongoing
This project was previously listed as Waterways condition, drainage and flood protection projects (statewide) in the 2018-19 Budget.
Waterways stormwater quality projects (statewide) | 32626 | 11227 | 10790 | 10609 | ongoing
Western treatment plant projects (Werribee) | 555760 | 206416 | 40692 | 308652 | ongoing
All remaining projects with a TEI less than $1 million | 186208 | 101630 | 31064 | 53514 | ongoing
Total existing projects | 3132847 | 1195726 | 463059 | 1474062
Total Melbourne Water Corporation projects | 7113892 | 1195726 | 565109 | 5353057
Source: Melbourne Water Corporation
(a) Melbourne Water Corporation structures its projects as programs of work, which comprise new, existing and completed components year on year. The TEI for the programs of work identified in the 2019-20 Budget includes three years forward following the final budget year, and three years preceding the first budget year. The TEIs for the programs of work are therefore likely to differ significantly between budget years, as forecasts are revised continuously.
Completed projects(a)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Alexandra Parade main drain redecking (Fitzroy) | 10916 | 9821 | qtr 1 2018-19
Argus Street retarding basin upgrade (Cheltenham) | 1013 | 784 | qtr 1 2018-19
Banyan Reserve retarding basin upgrade (Carrum Downs) | 1083 | 1043 | qtr 1 2018-19
Brooklyn pump station 22 kilovolt high voltage switchboard renewal (Brooklyn) | 1163 | 669 | qtr 2 2018-19
Burgess Street drain section 15 (Brooklyn) | 3244 | 2913 | qtr 3 2018-19
Business process optimisation continuous value stream 2017-18 (regional various) | 1840 | 1822 | qtr 1 2018-19
Business process optimisation continuous value stream 2018-19 (regional various) | 2047 | 0 | qtr 4 2018-19
Campbellfield retarding basin upgrade (Glenroy) | 1628 | 1246 | qtr 1 2018-19
Canterbury retarding basin upgrade (Bayswater South) | 1567 | 209 | qtr 4 2018-19
Cardinia fluoride plant renewal (Cardinia) | 5866 | 5832 | qtr 1 2018-19
Clyde Creek Hartleigh estate retarding basin wetland 6 land acquisition (Clyde) | 3705 | 2 | qtr 4 2018-19
Clyde Creek section 58 land acquisition (Cranbourne) | 3427 | 3422 | qtr 1 2018-19
Clyde Creek section 74 and 79 retarding basin wetland (Clyde North) | 2909 | 2397 | qtr 1 2018-19
Clyde Creek section 76 (Clyde North) | 3199 | 1245 | qtr 4 2018-19
Commonwealth Serum Laboratories retarding basin upgrade (Broadmeadows) | 1663 | 1074 | qtr 3 2018-19
Dandenong Creek levee banks upgrade (metropolitan various) | 2511 | 2507 | qtr 1 2018-19
Developer funded works system (regional various) | 4319 | 4314 | qtr 1 2018-19
Disaster recovery servers to cloud (regional various) | 1896 | 1682 | qtr 2 2018-19
Dohertys drain section 12 (Truganina) | 3737 | 3699 | qtr 1 2018-19
Dohertys drain section 23 and 24 part 1 (Truganina) | 2518 | 1918 | qtr 4 2018-19
Eastern treatment plant access and safety improvements (Bangholme) | 2463 | 288 | qtr 4 2018-19
Eastern treatment plant influent pumping stations high voltage switchboard and motor renewal (Bangholme) | 11878 | 11810 | qtr 1 2018-19
Eastern treatment plant secondary sedimentation tank civil renewals (Bangholme) | 1670 | 8 | qtr 2 2018-19
Fairbairn Road retarding basin embankment upgrades (Cranbourne) | 2300 | 2256 | qtr 1 2018-19
Green Street retarding basin upgrade (Mooroolbark) | 1123 | 171 | qtr 4 2018-19
Hessell Road retarding basin embankment upgrade (Berwick) | 1034 | 972 | qtr 1 2018-19
Huntingdale Road retarding basin wetland rectification (Mount Waverley) | 1568 | 489 | qtr 1 2018-19
Inflo content suite 16 upgrade (regional various) | 1586 | 1087 | qtr 2 2018-19
Jacana retarding basin wetland rectification (Jacana) | 6484 | 6477 | qtr 1 2018-19
Kallista fluoride plant (Kallista) | 2139 | 745 | qtr 2 2018-19
Kew pump station 11 kilovolt high voltage switchboard renewal (Kew) | 1981 | 1403 | qtr 2 2018-19
Kilsyth main drain retarding basin upgrade (Kilsyth) | 1878 | 206 | qtr 4 2018-19
Lee Street retarding basin embankment upgrade (Frankston) | 1448 | 1405 | qtr 1 2018-19
Long Island retarding basin upgrade (Frankston) | 2746 | 693 | qtr 2 2018-19
Maximo upgrade 7.6 (regional various) | 2301 | 370 | qtr 4 2018-19
Membrane replacement at Creswell water treatment plant (Healesville) | 3327 | 3445 | qtr 1 2018-19
Merri Creek interceptor rehabilitation (metropolitan various) | 6690 | 6616 | qtr 1 2018-19
Mobility continuous value stream 2017-18 (regional various) | 1726 | 1726 | qtr 1 2018-19
New western treatment plant administration facility power supply (Werribee) | 1121 | 695 | qtr 2 2018-19
Patterson Lakes tidal gates drop boards (Patterson Lakes) | 1091 | 970 | qtr 2 2018-19
Phase 2 customer and community portal (regional various) | 1460 | 0 | qtr 3 2018-19
Shankland and Bridgewater retarding basin remediation (Roxborough Park) | 2279 | 1989 | qtr 2 2018-19
Site security upgrade project phase 2 (regional various) | 1723 | 1531 | qtr 2 2018-19
Skye Road retarding basin upgrade (Frankston) | 1151 | 1071 | qtr 1 2018-19
Ti Tree Creek section 117 (Clyde North) | 1361 | 1293 | qtr 4 2018-19
Tidal canals retaining wall cathodic protection (Patterson Lakes) | 10322 | 9229 | qtr 3 2017-18
Tributory of Davis Creek section 01 (Tarneit) | 1005 | 758 | qtr 2 2018-19
Troups Creek West retarding basin wetland rectification (Narre Warren) | 4584 | 4560 | qtr 1 2018-19
Water network revenue meter upgrade program (metropolitan various) | 8038 | 4985 | qtr 2 2018-19
Werribee West drain section 16 (Wyndham Vale) | 2514 | 1422 | qtr 1 2018-19
Western outfall drain section 3 (Clyde) | 1727 | 1723 | qtr 4 2018-19
Western treatment plant 25W pot chemical oxygen demand pipeline renewal (Werribee) | 8951 | 6517 | qtr 2 2018-19
Western treatment plant 55E pot chemical oxygen demand pipeline renewal 2018 (Werribee) | 2328 | 0 | qtr 4 2018-19
Western treatment plant new biosolids stockpile area (Werribee) | 8819 | 3583 | qtr 3 2018-19
Western treatment plant new maintenance shed (Werribee) | 3901 | 3282 | qtr 2 2018-19
Windows10 standard operating environment enterprise deployment (regional various) | 1359 | 1031 | qtr 2 2018-19
Winneke fire ring main upgrade (Winneke) | 2947 | 2794 | qtr 1 2018-19
Wylies drain main branch section 1 stage 3 (Devon Meadows) | 2295 | 1994 | qtr 4 2018-19
Yarra Glen pump station main pump 1 and 2 drive renewals (Yarra Glen) | 5303 | 4108 | qtr 2 2018-19
Source: Melbourne Water Corporation
Note: -
(a) The listing of 'Completed projects' includes some individual developer works projects, as well as some larger projects from within programs of consilidated works previously reported as 'New' or 'Existing' in the 2018-19 Budget.
North East Region Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Benalla waste water system transfer expansion (Benalla) | 1574 | 0 | 7.87 | 1566.13 | qtr 4 2021-22
Benalla water distribution upgrade (Benalla) | 2439 | 0 | 121.95 | 2317.05 | qtr 4 2020-21
Corryong reuse compliance (Corryong) | 1200 | 0 | 24 | 1176 | qtr 4 2021-22
All remaining projects with a TEI less than $1 million (regional various) | 3021.8 | 0 | 2971.8 | 50 | ongoing
Total new projects | 8234.8 | 0 | 3125.62 | 5109.18
Source: North East Region Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Above ground asset replacement – waste water (regional various) | 4725.375 | 785 | 803 | 3137.375 | ongoing
Above ground asset replacement – water (regional various) | 7173.664 | 1306.549 | 1929.835 | 3937.28 | ongoing
Beechworth waste water system upgrade (Beechworth) | 6029 | 150 | 2261.6 | 3617.4 | qtr 4 2020-21
Name changed from Beechworth sewer and wastewater treatment plant expansion in 2018-19 budget papers.
Bellbridge waste water system upgrade (Bellbridge) | 2042 | 36.84 | 92.1 | 1913.06 | qtr 4 2021-22
Bellbridge water system upgrade (Bellbridge) | 1943 | 155.44 | 1587.56 | 200 | qtr 4 2020-21
Below ground asset replacement – waste water (regional various) | 6411.375 | 543.625 | 881.625 | 4986.125 | ongoing
Below ground asset replacement – water (regional various) | 9873.831 | 2503.049 | 3782.876 | 3587.906 | ongoing
Customer billing system renewal and upgrade (regional various) | 2100 | 0 | 200 | 1900 | qtr 4 2020-21
Information communication technology infrastructure replacements (regional various) | 1800 | 300 | 300 | 1200 | ongoing
Myrtleford waste water treatment plant upgrade project (Myrtleford) | 2922.771 | 2814.688 | 108.083 | 0 | qtr 4 2019-20
Permanent water purchase (regional various) | 1920 | 320 | 320 | 1280 | ongoing
Region-wide digital business sustainability (regional various) | 3526 | 400 | 600 | 2526 | qtr 4 2021-22
Region-wide facilities security upgrade (regional various) | 1050 | 175 | 175 | 700 | ongoing
Region-wide information security compliance (regional various) | 1762 | 17.62 | 17.62 | 1726.76 | qtr 4 2021-22
Region-wide minor capital expenditure (regional various) | 1500 | 250 | 250 | 1000 | ongoing
Project previously had TEI of less than $1 million.
Region-wide renewable energy and climate efficiencies (regional various) | 4000 | 350 | 1000 | 2650 | ongoing
Region-wide strategic land acquisition (regional various) | 1200 | 0 | 150 | 1050 | ongoing
TEI has reduced due to rolling nature of the budget. Prior year purchases have dropped from current year TEI.
Supervisory control and data acquisition system upgrade and replacement (regional various) | 2125 | 200 | 350 | 1575 | ongoing
Tallangatta waste water treatment plant upgrade (Tallangatta) | 1169.3 | 30.18 | 975.82 | 163.3 | qtr 4 2020-21
Vehicle replacement (regional various) | 6361 | 1120 | 1050 | 4191 | ongoing
Wangaratta waste water treatment plant stage 2 upgrade (Wangaratta) | 2636.75 | 75.72 | 2561.03 | 0 | qtr 4 2019-20
Project originally budgeted for 2019-20, brought forward to 2018-19 budget year.
Wangaratta works depot relocation (Wangaratta) | 1500 | 50 | 232.5 | 1217.5 | qtr 4 2020-21
Name change from region-wide depot, buildings and access roads upgrades.
Wodonga Creek pump station upgrade (Wodonga) | 1648.092 | 0 | 498.092 | 1150 | qtr 4 2020-21
Wodonga waste water treatment plant capacity and emissions reduction upgrade (Wodonga) | 11700 | 0 | 585 | 11115 | qtr 4 2022-23
Wodonga waste water treatment plant solar power plant (Wodonga) | 4804 | 96.08 | 144.12 | 4563.8 | qtr 4 2022-23
Yackandandah water distribution upgrade (Yackandandah) | 1580 | 7.2 | 624.8 | 948 | qtr 4 2020-21
All remaining projects with a TEI less than $1 million (regional various) | 6053.6 | 589.852 | 2952.998 | 2510.75 | ongoing
Includes Yackandandah reclaimed water management project as TEI is now less than $1 million.
Total existing projects | 99556.758 | 12276.843 | 24433.659 | 62846.256
Total North East Region Water Corporation projects | 107791.558 | 12276.843 | 27559.279 | 67955.436
Source: North East Region Water Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Bright waste water treatment plant discharge project (Bright) | 3194.085 | 3194.085 | qtr 4 2018-19
Wangaratta ground water supply (Wangaratta) | 2191.38 | 2191.38 | qtr 4 2018-19
Wangaratta waste water treatment plant upgrade (Wangaratta) | 2674.113 | 2674.113 | qtr 4 2018-19
Wodonga waste water treatment plant aeration energy efficiency (Wodonga) | 1321.892 | 1321.892 | qtr 4 2018-19
Source: North East Region Water Corporation
South East Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Corporate miscellaneous (metro various) | 2472 | 0 | 412 | 2060 | ongoing
Meters (metro various) | 1292.154 | 0 | 0 | 1292.154 | ongoing
Recycled water growth – Cardinia Shire Council (Cardinia) | 2680.493 | 0 | 0 | 2680.493 | qtr 4 2022-23
Recycled water growth – City of Casey (Casey) | 2043.962 | 0 | 0 | 2043.962 | ongoing
Sewer growth – Cardinia Shire Council (Cardinia) | 1822.012 | 0 | 1822.012 | 0 | qtr 4 2019-20
Sewer growth – City of Casey (Casey) | 1807.44 | 0 | 0 | 1807.44 | qtr 4 2021-22
Sewer reliability – other (metro various) | 2630 | 0 | 575 | 2055 | ongoing
Water growth – other (metro various) | 2026.81 | 0 | 0 | 2026.81 | qtr 4 2023-24
All remaining projects with a TEI less than $1 million | 1041 | 0 | 122 | 919 | ongoing
Total new projects | 17815.871 | 0 | 2931.012 | 14884.859
Source: South East Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Corporate climate change – other (metro various) | 18202.563 | 67.563 | 1235 | 16900 | ongoing
Decrease in TEI due to reclassification of some projects to ’Sewer system growth – Pakenham sewage treatment plant (Cardinia)’ and ’Sewer system reliability – Mt Martha sewage treatment plant (Mornington)’.
Corporate miscellaneous (metro various) | 37909.083 | 5030.083 | 7759 | 25120 | ongoing
Information technology – other (metro various) | 143305.715 | 21605.715 | 22000 | 99700 | ongoing
Decrease in TEI due to decrease in budgeted investment for IT project requirements.
Land and buildings miscellaneous (metro various) | 5107.369 | 2455.699 | 1058.17 | 1593.5 | ongoing
Meters (metro various) | 68012.708 | 9734.38 | 13899.332 | 44378.996 | ongoing
Recycled water – other (metro various) | 48343.559 | 3468.169 | 2829.417 | 42045.973 | ongoing
Recycled water growth – City of Casey (Casey) | 40422.054 | 2841.564 | 7104.604 | 30475.886 | ongoing
Increase in TEI due to increase in scope of works for developer constructed assets.
Sewer backlog – Cardinia Shire Council (Cardinia) | 3240.811 | 216.9 | 3023.911 | 0 | qtr 4 2019-20
Increase in TEI and change in estimated completion date due to increase in budgeted investment and schedule of works.
Sewer backlog – City of Casey (Casey) | 1500 | 0 | 1500 | 0 | qtr 4 2019-20
Change in estimated completion date due to change in schedule of works.
Sewer backlog – Mornington Peninsula Shire (Mornington) | 99425.243 | 13088.389 | 15237.5 | 71099.354 | ongoing
Decrease in TEI due to decrease in budgeted investment for property connections.
Sewer growth – Baw Baw Shire Council (Baw Baw) | 1045.398 | 0 | 0 | 1045.398 | qtr 4 2023-24
Decrease in TEI and change in estimated completion date due to removal of projects.
Sewer growth – Cardinia Shire Council (Cardinia) | 45881.958 | 2126.85 | 2966.929 | 40788.179 | ongoing
Sewer growth – City of Casey (Casey) | 158157.876 | 20128.755 | 14331.781 | 123697.34 | qtr 4 2026-27
Increase in TEI and change in estimated completion date due to inclusion of full scope of large pump station and rising main, which previously only had half the scope due to delivery timeframe.
Sewer growth – City of Greater Dandenong (Dandenong) | 3244.603 | 145.643 | 24.866 | 3074.094 | qtr 4 2022-23
Sewer growth – City of Port Phillip (Port Phillip) | 24303.378 | 0 | 0 | 24303.378 | qtr 4 2022-23
Decrease in TEI due to removal of projects.
Sewer growth – City of Stonnington (Stonnington) | 4221.469 | 0 | 0 | 4221.469 | qtr 4 2021-22
Sewer growth – Kingston City Council (Kingston) | 2310.937 | 65.487 | 500 | 1745.45 | qtr 4 2020-21
Sewer growth – Mornington Peninsula Shire (Mornington) | 9694.723 | 0 | 0 | 9694.723 | qtr 4 2023-24
Decrease in TEI and change in estimated completion date due to decrease in budgeted investment and schedule of works.
Sewer growth – other (metro various) | 33311.292 | 10496.794 | 9539.762 | 13274.736 | ongoing
Decrease in TEI due to decrease in budgeted investment.
Sewer quality – other (metro various) | 17066.994 | 1365.786 | 3933.928 | 11767.28 | ongoing
Sewer reliability – Mornington Peninsula Shire (Mornington) | 2760.244 | 2602.21 | 158.034 | 0 | qtr 2 2019-20
Decrease in TEI due to decrease in budgeted investment.
Sewer reliability – other (metro various) | 146532.833 | 18699.241 | 29795.715 | 98037.877 | ongoing
Decrease in TEI due to decrease in scope and budgeted investment.
Sewer system growth – Blind Bight sewage treatment plant (Casey) | 3214.364 | 2.642 | 131.749 | 3079.973 | qtr 4 2022-23
Change in estimated completion date due to change in schedule of works.
Sewer system growth – Boneo sewage treatment plant (Mornington) | 136833.947 | 44532.185 | 74214.393 | 18087.369 | qtr 4 2028-29
Increase in TEI and change in estimated completion date due to increase in investment and schedule of works.
Sewer system growth – Fisherman’s Bend – sewer mining plant (Port Phillip) | 29976.258 | 286.258 | 26721 | 2969 | qtr 4 2021-22
Sewer system growth – Longwarry sewage treatment plant (Baw Baw) | 10211.078 | 222.182 | 7357.935 | 2630.961 | ongoing
Increase in TEI due to increase in budgeted investment.
Sewer system growth – Mt Martha sewage treatment plant (Mornington) | 3877.654 | 343.26 | 1433 | 2101.394 | qtr 4 2020-21
Decrease in TEI due to decrease in scope and budgeted investment.
Sewer system growth – Pakenham sewage treatment plant (Cardinia) | 81657.631 | 3278.036 | 1780.398 | 76599.197 | qtr 4 2027-28
Increase in TEI and change in estimated completion date due to inclusion of new regional plant and some projects reclassified from ’Corporate climate change – other (metro various)’.
Sewer system growth – Somers sewage treatment plant (Mornington) | 3900 | 0 | 3900 | 0 | qtr 4 2019-20
Change in estimated completion date due to change in scope and schedule of works.
Sewer system reliability – Blind Bight sewage treatment plant (Casey) | 2101.25 | 229.924 | 459.945 | 1411.381 | ongoing
Sewer system reliability – Boneo sewage treatment plant (Mornington) | 12063.741 | 1165.187 | 1683.504 | 9215.05 | ongoing
Sewer system reliability – Koo Wee Rup sewage treatment plant (Cardinia) | 1141.447 | 118.995 | 423.194 | 599.258 | ongoing
Sewer system reliability – Lang Lang sewage treatment plant (Cardinia) | 5261.97 | 56.75 | 533.925 | 4671.295 | ongoing
Sewer system reliability – Mt Martha sewage treatment plant (Mornington) | 25334.978 | 5169.78 | 6468.853 | 13696.345 | ongoing
Decrease in TEI due to change in scope of works, offset with the reclassification of some projects from ’Corporate climate change – other (metro various)’.
Sewer system reliability – Pakenham sewage treatment plant (Cardinia) | 11000.879 | 1763.804 | 892.936 | 8344.139 | ongoing
Decrease in TEI due to reduction in scope.
Sewer system reliability – Somers sewage treatment plant (Mornington) | 3800.427 | 765.417 | 529.626 | 2505.384 | ongoing
Decrease in TEI due to reduction in scope of works, project completed and other minor reductions in scope.
Sewer system reliability – other sewage treatment plant (metro various) | 46540.793 | 3740.582 | 8609.306 | 34190.905 | ongoing
Increase in TEI due to increase in scope of works around sludge drying pans and stock pile areas across all plants.
Water growth – Cardinia Shire Council (Cardinia) | 21443.581 | 71.559 | 1570.599 | 19801.423 | qtr 4 2028-29
Increase in TEI due to increase in scope of works and reclassification of some projects from ’Water growth – City of Casey (Casey)’.
Water growth – City of Casey (Casey) | 15044.34 | 427.013 | 4809.345 | 9807.982 | ongoing
Decrease in TEI due to reclassification of some projects to ’Water growth – Cardinia Shire Council (Cardinia)’ and ’Water growth – other (metro various)’.
Water growth – other (metro various) | 46403.859 | 5003.746 | 6623.069 | 34777.044 | ongoing
Increase in TEI due to reclassification of some projects from ’Water growth – City of Casey (Casey)’.
Water quality – other (metro various) | 1366.9 | 171.9 | 192 | 1003 | ongoing
Water reliability – other (metro various) | 190092.362 | 14390.957 | 28387.058 | 147314.347 | ongoing
Decrease in TEI due to decrease in investment predominantly in renewals program.
All remaining projects with a TEI less than $1 million | 211.58 | 62.712 | 14.865 | 134.003 | qtr 4 2023-24
Sewer growth – City of Monash (Monash) and Sewer growth – Glen Eira City Council (Glen Eira), listed as existing projects in last year’s budget, have been removed from the capital plan at this stage.
Total existing projects | 1565479.849 | 195942.117 | 313634.649 | 1055903.083
Total South East Water Corporation projects | 1583295.72 | 195942.117 | 316565.661 | 1070787.942
Source: South East Water Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Corporate miscellaneous (metro various) | 1499.054 | 1499.054 | qtr 4 2018-19
Sewer reliability – other (metro various) | 6517.723 | 6517.723 | qtr 4 2018-19
Sewer system reliability – Somers sewage treatment plant (Mornington) | 1854.039 | 1854.039 | qtr 4 2018-19
Sewer system reliability – other sewage treatment plant (metro various) | 1355.793 | 1355.793 | qtr 4 2018-19
Water reliability – other (metro various) | 15996.862 | 15996.862 | qtr 4 2018-19
All remaining projects with a TEI less than $1 million | 3863.141 | 3863.141 | qtr 4 2018-19
Source: South East Water Corporation
South Gippsland Region Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Billing system renewal (regional various) | 1748.332 | 0 | 0 | 1748.332 | ongoing
New pressure sewer connections (regional various) | 4440.023 | 0 | 233.991 | 4206.032 | ongoing
Venus Bay outfall renewal (Venus Bay) | 519.354 | 0 | 0 | 519.354 | ongoing
Water supply augmentation (Leongatha) | 6157.221 | 0 | 0 | 6157.221 | ongoing
Total new projects | 12864.93 | 0 | 233.991 | 12630.939
Source: South Gippsland Region Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Bulk entitlement (regional various) | 1703.028 | 0 | 0 | 1703.028 | ongoing
Decrease in project TEI due to revised project cost estimate.
Carbon emission reduction upgrades (regional various) | 3426.586 | 348.3984 | 2521.695 | 556.4926 | qtr 4 2020-21
Increase in project TEI due to revised project cost estimate.
Computers/supervisory control and data acquisition security system (regional various) | 13882.769 | 1203.313 | 1142.18 | 11537.276 | ongoing
Decrease in project TEI due to revised project cost estimate.
Fish Creek treated water trunk main (Fish Creek) | 2609.111 | 0 | 51.15 | 2557.961 | qtr 4 2027-28
Increase in project TEI due to revised project cost estimate.
Foster waste water treatment plant reuse and pipeline (Foster) | 248.607 | 55.26 | 193.347 | 0 | qtr 4 2031-32
Next stage of the project has been deferred and the project scope and TEI have been revised accordingly.
Headworks – dams (regional various) | 5557.249 | 0 | 0 | 5557.249 | ongoing
Decrease in project TEI due to revised project cost estimate.
Hydraulic modelling and network master planning (regional various) | 1879.77 | 430.54 | 336.915 | 1112.315 | ongoing
Decrease in project TEI due to revised project cost estimate.
Inverloch sewer system upgrades (Inverloch) | 7159.498 | 1511.545 | 0 | 5647.953 | ongoing
Decrease in project TEI due to revised project cost estimate.
Korumburra sewer system upgrades (Korumburra) | 4867.594 | 69.945 | 0 | 4797.649 | ongoing
Increase in project TEI due to revised project cost estimate.
Leongatha sewer system upgrades (Leongatha) | 1673.071 | 0 | 0 | 1673.071 | ongoing
Decrease in project TEI due to revised project cost estimate.
Manholes upgrades (regional various) | 4822.685 | 215.3246 | 51.15 | 4556.2104 | ongoing
Increase in project TEI due to revised project cost estimate.
Northern towns project (Korumburra/Poowong/Loch/Nyora) | 37432.962 | 35595.29 | 1392.303 | 445.369 | ongoing
The balance includes water treatment plant augmentation and upgrade (regional various). Decrease in project TEI due to revised project cost estimate.
Northern towns project Stage 3 (Korumburra/Poowong/Loch/Nyora) | 3854.239 | 190.256 | 61.38 | 3602.603 | qtr 4 2027-28
Deferral in project and reduction in scope resulted in a decrease in project TEI. The balance includes Bellview Creek dam repurposing or decommissioning (Bellview Creek).
Nyora duplicate transfer main (Nyora) | 111.076 | 111.076 | 0 | 0 | qtr 4 2031-32
Next stage of the project has been deferred and the project scope and TEI have been revised.
Operational vehicles replacement (regional various) | 8458.616 | 1076.934 | 664.95 | 6716.732 | ongoing
Increase in project TEI due to revised project cost estimate.
Plant and equipment replacement (regional various) | 2898.925 | 59.817 | 255.75 | 2583.358 | ongoing
Decrease in project TEI due to revised project cost estimate.
Poowong Loch Nyora additional connections and renewals (Poowong Loch, Nyora) | 1037.803 | 129.289 | 81.84 | 826.674 | ongoing
Decrease in project TEI due to revised project cost estimate.
Pump station upgrades (regional various) | 15667.869 | 3856.791 | 4514.446 | 7296.632 | qtr 4 2021-22
Transfer of project from ’All remaining completed projects with a TEI less than $1 million’ as the value of the project has been revised to above $1 million. Revised project cost estimate resulted in increase in project TEI.
Raw water pump station renewal (regional various) | 2530.497 | 62.274 | 206.646 | 2261.577 | ongoing
Decrease in project TEI due to revised project cost estimate.
Raw water trunk main upgrades/duplications (regional various) | 594.425 | 1.001 | 0 | 593.424 | ongoing
Increase in project TEI due to revised project cost estimate.
Replacement and rehabilitation of water mains (regional various) | 14822.805 | 299.192 | 511.5 | 14012.113 | ongoing
Increase in project TEI due to revised project cost estimate.
Reticulation sewer replacements/rehabilitation (regional various) | 10790.041 | 1823.959 | 878.757 | 8087.325 | ongoing
Increase in project TEI due to revised project cost estimate.
Reuse and outfall renewal (regional various) | 372.747 | 31.831 | 30.7101 | 310.2059 | ongoing
Decrease in project TEI due to revised project cost estimate.
Sewer rising main expansion (Wonthaggi) | 2505.445 | 0 | 0 | 2505.445 | ongoing
Decrease in project TEI due to revised project cost estimate.
Sewer rising main renewal (regional various) | 1228.161 | 39.0497 | 51.15 | 1137.9613 | ongoing
Increase in project TEI due to revised project cost estimate.
Sewer sidelines renewal (regional various) | 2734.83 | 192.293 | 51.15 | 2491.387 | ongoing
Increase in project TEI due to revised project cost estimate.
Sewer system renewal expansion (regional various) | 2267.914 | 0 | 0 | 2267.914 | ongoing
Decrease in project TEI due to revised project cost estimate.
South Gippsland Water facilities renewal (regional various) | 10682.942 | 994.7863 | 2762.1 | 6926.0557 | qtr 4 2020-21
Increase in project TEI due to an expanded project scope.
Trunk main upgrades/duplications (regional various) | 1066.959 | 50 | 102.3 | 914.659 | qtr 4 2032-33
Deferral in project and reduction in scope resulted in a decrease in project TEI.
Venus Bay outfall renewal (Venus Bay) | 5821.358 | 0 | 0 | 5821.358 | ongoing
Decrease in project TEI due to revised project cost estimate.
Venus Bay outfall upgrade (Venus Bay) | 10695.896 | 9.9125 | 0 | 10685.9835 | qtr 4 2027-28
Project has been brought forward resulting in an increase in project TEI from last year.
Waste water treatment plants renewal upgrade and expansion (regional various) | 12568.174 | 119.16 | 243.474 | 12205.54 | ongoing
Increase in project TEI due to revised project cost estimate.
Water meters (regional various) | 1835.469 | 180.786 | 112.53 | 1542.153 | ongoing
Increase in project TEI due to revised project cost estimate.
Water supply augmentation (Leongatha) | 744.908 | 44.155 | 0 | 700.753 | ongoing
Previously named ’Bellview Creek dam repurposing or decommissioning (Bellview Creek)’. Revision of scope has resulted in a decrease of project TEI.
Water treatment plant augmentation and upgrade (regional various) | 3815.014 | 136.205 | 0 | 3678.809 | ongoing
Increase in project TEI due to revised project cost estimate.
Water treatment plants renewal upgrade expansion (regional various) | 34942.858 | 996.349 | 2585.505 | 31361.004 | ongoing
Increase in project TEI due to an expanded project scope.
Wonthaggi sewer system upgrades (Wonthaggi) | 12952.008 | 3228.1749 | 1530.408 | 8193.4251 | ongoing
Decrease in project TEI due to revised project cost estimate.
All remaining projects with a TEI less than $1 million | 14341.333 | 3020.525 | 2993.456 | 8327.352 | various
Transfer of a project renamed ’Pump station upgrades (regional various)’ as the value of the project has been revised to above $1 million.
Total existing projects | 264605.242 | 56083.4325 | 23326.792 | 185195.0175
Total South Gippsland Region Water Corporation projects | 277470.172 | 56083.4325 | 23560.783 | 197825.9565
Source: South Gippsland Region Water Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Replacement and rehabilitation of water mains (regional various) | 323.754 | 323.754 | qtr 4 2018-19
All remaining projects with a TEI less than $1 million | 153.058 | 153.058 | qtr 4 2018-19
Source: South Gippsland Region Water Corporation
Victorian Ports Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Channels and waterways – capital projects (Port Phillip Bay) | 1980.4 | 0 | 480.4 | 1500 | various
Information technology – upgrades and development (Melbourne) | 7828 | 0 | 868 | 6960 | various
Station Pier capital projects (Port Melbourne) | 23805 | 0 | 655 | 23150 | various
All remaining projects with a TEI less than $1 million | 1000 | 0 | 250 | 750 | various
Total new projects | 34613.4 | 0 | 2253.4 | 32360
Source: Victorian Ports Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Information technology – upgrades and development (Melbourne) | 9013.257 | 1548.257 | 6715 | 750 | ongoing
Station Pier capital projects (Port Melbourne) | 9485 | 1350 | 5335 | 2800 | ongoing
Total existing projects | 18498.257 | 2898.257 | 12050 | 3550
Total Victorian Ports Corporation projects | 53111.657 | 2898.257 | 14303.4 | 35910
Source: Victorian Ports Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Channels and waterways – capital projects (Port Phillip Bay) | 80.4 | 80.4 | qtr 4 2018-19
Information technology – upgrades and development (Melbourne) | -131.858 | -131.858 | qtr 4 2018-19
Information technology projects have been reclassified from capital to recurrent/operating expenditure.
Station Pier capital projects (Port Melbourne) | 2238 | 2239.168 | qtr 4 2018-19
All remaining projects with a TEI less than $1 million | 275 | 275 | qtr 4 2018-19
Source: Victorian Ports Corporation
Victorian Rail Track
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Additional VLocity trains (regional various) | 340000 | 0 | 178400 | 161600 | tbc
Ballarat Bus Interchange (Ballarat) | 5000 | 1150 | 3850 | 0 | qtr 3 2019-20
Better Train Services for Bendigo and Central Victoria (regional various) | 49600 | 0 | 12608 | 36992 | qtr 4 2022-23
Car Parks for Commuters (statewide) | 150000 | 0 | 12500 | 137500 | qtr 4 2022-23
Cranbourne Line Duplication planning and development (metropolitan various) | 750000 | 0 | 12200 | 737800 | qtr 4 2019-20
Digital Train Radio System critical service upgrades (metropolitan various) | 83000 | 15400 | 54900 | 12700 | qtr 4 2020-21
Hurstbridge Line Upgrade Stage 2 (metropolitan various) | 530000 | 0 | 21500 | 508500 | tbc
The completion date is subject to the completion of planning for the project.
Public transport network safety and resilience (metropolitan various) | 59694 | 0 | 46733 | 12961 | qtr 4 2021-22
New trains for Sunbury (metropolitan various) | 2050365 | 0 | 202066 | 1848299 | qtr 2 2024-25
New Trams (metropolitan various) | 144720 | 0 | 68520 | 76200 | tbc
Tram Automatic Vehicle Monitoring (AVM) System Replacement (metropolitan various) | 3530 | 0 | 3530 | 0 | qtr 4 2019-20
Melbourne Airport Rail | 680680 | 10000 | 50000 | 620680 | tbc
This funding represents the Commonwealth contribution to the project. The Government has made a substantial provision in the Victorian Transport Fund for this project. The project is in its planning phase.
Suburban Rail Loop | 250000 | tbc | tbc | tbc | tbc
Funding is for detailed planning and development activities.
Western Rail Plan | 75000 |  | 18600 | 56400 | tbc
Funding is for detailed planning and development activities.
Waurn Ponds Track Duplication – Stage 2 (regional various) | 2000 | 2000 | 0 | 0 | qtr 4 2019-20
The completion date refers to planning and development work only.
Total new projects | 5173589 | 28550 | 685407 | 4209632
Source: Department of Transport
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Additional station car parks and upgrades (metropolitan various) | 4700 | 1537 | 3163 | 0 | qtr 3 2019-20
The estimated completion date has been revised to quarter 3 2019-20.
Additional X’Trapolis Metropolitan Trains (metropolitan various) | 103501 | 47949 | 51245.6 | 4306.4 | qtr 4 2019-20
The estimated completion date has been extended to quarter 4 2019-20 to accommodate the updated delivery schedule of the Digital Train Radio System.
Bayside rail improvements (metropolitan various) | 115000 | 111995.3 | 3005.2 | 0 | qtr 2 2019-20
The estimated completion date has been revised to quarter 2 2019-20 to integrate train operational requirements, including at the Newport Maintenance Facility.
Caulfield to Dandenong conventional signalling and power infrastructure upgrade (metropolitan various) | 608121 | 561183 | 46938 | 0 | qtr 2 2019-20
TEI excludes $0.160 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
City Loop fire and safety upgrade (stage 2) and intruder alarm (Melbourne) | 151743.3 | 41175.7 | 21224.4 | 89343.2 | tbc
The main delivery contractor has been put into administration, and work is progressing to assess the impact to cost and schedule.
Coinvestment for upgrades to State owned rail sidings (regional various) | 8500 | 0 | 4000 | 4500 | qtr 4 2021-22
The estimated completion date has been revised to quarter 4 2021-22 due to drought conditions and revised timeframes of delivery partner.
Cranbourne Pakenham and Sunbury Line Upgrades | 539540 | 456926 | 82614 | 0 | qtr 2 2019-20
E-Class Tram Procurement Stage 4 (metropolitan various) | 93000 | 21871.5 | 47934.6 | 23193.9 | qtr 4 2020-21
Enhancing public transport safety and security (statewide) | 16386 | 1043 | 4315.6 | 11027.4 | qtr 4 2020-21
Enhancing safety on the train network (statewide) | 60615 | 8898.7 | 20152.9 | 31563.6 | qtr 2 2020-21
Flinders Street Station Redevelopment (Melbourne) | 100000 | 98753.1 | 1246.9 | 0 | qtr 1 2019-20
The estimated completion date has been revised to quarter 1 2019-20 to implement signage and pathing improvements.
Frankston Line stabling (Kananook) | 236683 | 109993.9 | 124072.7 | 2616.4 | qtr 3 2019-20
TEI excludes $0.002 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards.
High Capacity Metro Trains (metropolitan various) | 2176000 | 595958 | 296024 | 1284018 | qtr 1 2023-24
TEI includes financing costs.
High Capacity Metro Trains – rolling stock cascade works (metropolitan various) | 55000 | 43075 | 11787 | 138 | qtr 2 2019-20
Improvements to the North-East line (regional various) | 15000 | 8027.1 | 6972.9 | 0 | qtr 4 2019-20
The estimated completion date has been revised to quarter 4 2019-20 due to revised time frames.
Improving public transport accessibility (metropolitan various) | 11286 | 666.3 | 10620.1 | 0 | qtr 4 2019-20
The estimated completion date has been revised due to early completion of scheduled work.
Life extension for Comeng trains (metropolitan various) | 75000 | 23085 | 28518.7 | 23396 | qtr 1 2021-22
The estimated completion date has been revised to quarter 1 2021-22 due to revised time frames.
Major periodic maintenance on the regional rail network (regional various) | 287913 | 184913 | 103000 | 0 | qtr 4 2019-20
The estimated completion date has been revised to quarter 4 2019-20 to prioritise critical asset maintenance works.
Metro Tunnel (metropolitan various) | 10883144.1 | 4460097 | 1590996.4416 | 4832050 | qtr 2 2025-26
TEI excludes $109.380 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. TEI excludes financing costs.
Metropolitan rail infrastructure renewal program (metropolitan various) | 1489361 | 441696.5 | 274865 | 772799.5 | qtr 4 2024-25
TEI has been reduced by $4.450 million due to savings, and $35.127 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. As a rolling program of works, the TEI varies from year to year. TEI incorporates all capital funding for metropolitan rail infrastructure renewals from 2016-17 to 2024-25, including funding provided in the 2017-18 Budget Update for the management of the new train and tram franchise agreement that commenced on 30 November 2017.
Minor capital works fund (metropolitan various) | 61271.6 | 20358 | 10913.7 | 29999.9 | qtr 4 2022-23
TEI incorporates all capital funding from 2016-17 to 2022-23. As this is a rolling program of works, the TEI varies from year to year.
More E-Class trams and infrastructure (metropolitan various) | 215462.2 | 56358.1 | 69352.4 | 89751.7 | qtr 4 2021-22
The estimated completion date has been revised to quarter 4 2021-22 as works are progressing to secure land holdings for the power substations.
More regional trains – New Vlocity Trains (regional various) | 270424 | 170817 | 66072 | 33535 | qtr 4 2020-21
TEI has reduced by $5.701 million due to savings.
More regional trains – Regional Network Development Plan (regional various) | 226335 | 156192 | 24041.1 | 46101.9 | qtr 4 2019-20
TEI has reduced by $2.500 million due to savings.
Murray Basin Rail Project (regional various) | 567700 | 371873 | 178429 | 17398 | tbc
$20.200 million has been reallocated to this project from the Regional Rail Revival - (Murray Basin Rail Project). The TEI includes funding for the ‘Rail Infrastructure Upgrades from Maryborough and Ararat to Ballarat’, a $1.000 million contribution from GrainCorp, and $35.000 million of Commonwealth funding for Ballarat Line Upgrade Stage 2. These projects have been combined for reporting purposes and the estimated completion date is to be confirmed.
Network Transition Plan – Phase A | 255838 | 236091 | 19747 | 0 | qtr 2 2019-20
New E-Class trams (metropolitan various) | 280204.2 | 160835.6 | 36503.6 | 82865 | qtr 4 2020-21
The estimated completion date has been revised to quarter 4 2020-21 as works are progressing to secure land holdings for the power substations.
New VLocity carriages for the regional network (regional various) | 252356.3 | 144791.3 | 92165 | 15400 | qtr 4 2021-22
The estimated completion date has been revised due to revised scope. TEI excludes $2.150 million due to savings, and $1.638 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards.
Non-urban train radio renewal (regional various) | 63290.5 | 55113 | 8177.7 | 0 | qtr 4 2019-20
The estimated completion date has been revised to quarter 4 2019-20 to reflect the integration of Regional Rail Communication Network systems with the metropolitan digital train radio system. The TEI has increased by $8.939 million to more accurately reflect funding from other sources.
Ongoing delivery of night network (statewide) | 3165 | 1050 | 2115 | 0 | qtr 4 2019-20
The estimated completion date has been revised to quarter 4 2019-20 to reflect the delivery schedule of bus infrastructure and alignment with future timetable changes.
Public Transport accessibility improvements (metropolitan various) | 16102 | 2581.2 | 10714.9 | 2805.8 | qtr 2 2020-21
Railway crossing upgrades (statewide) | 44012.8 | 11889.1 | 9302.5 | 22821.1 | qtr 4 2022-23
TEI incorporates all capital funding for the railway crossing program from 2017-18 to 2022-23. As this is a rolling program of works, the TEI varies from year to year.
Regional Rail Revival | 1436952.2 | 445139.9 | 407464 | 584348.3
– Ballarat Line Upgrade Stage 1 (regional various) | 545014.2 | 370471.9 | 158365 | 16177.3 | qtr 4 2019-20
TEI includes $467.000 million of Commonwealth funding, and excludes $4.441 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards.
– Ballarat Line Upgrade Stage 2 (regional various) | 4000 | 756 | 3244 | 0 | qtr 4 2022-23
TEI has decreased by $35 million due to works redirected to the Freight-Passenger Rail Separation Project.
– Bendigo/Echuca Line Upgrade (Bendigo) | 91000 | 3380 | 41900 | 45720 | qtr 3 2020-21
TEI includes $82.000 million of Commonwealth funding.
– Geelong Line Upgrade – Waurn Ponds Duplication (Stage 1) (regional various) | 110000 | 4491 | 41097 | 64412 | qtr 2 2022-23
TEI includes $99.000 million of Commonwealth funding.
– Gippsland Line Upgrade Stage 1 (regional various) | 433938 | 31335 | 44387 | 358216 | qtr 2 2022-23
TEI includes $418.000 million of Commonwealth funding, and excludes $1.062 million due to certain expenditure being recognised as operating instead of capital in line with accounting standards. The estimated completion date has been revised due to packaging of the Gippsland-Shepparton-Bendigo alliance.
– Gippsland Line Upgrade Stage 2 – Avon Bridge (regional various) | 95000 | 9852 | 45569 | 39579 | qtr 1 2020-21
TEI includes $86.000 million of Commonwealth funding.
– Upgrades to the North East Line (regional various) | 44000 | 9218 | 16915 | 17867 | qtr 2 2021-22
TEI includes $4.000 million GAIC funding for Donnybrook Station, and excludes $235.000 million of Commonwealth works allocated to Australian Rail Track Corporation.
– Warrnambool Line Upgrade (regional various) | 114000 | 15636 | 55987 | 42377 | qtr 4 2021-22
TEI includes $104.000 million of Commonwealth funding.
Road and rail minor works fund – rail (statewide) | 35825 | 34235.4 | 1589.4 | 0 | qtr 4 2019-20
TEI has been reduced by $0.545 million due to savings. The estimated completion date has been revised to quarter 4 2019-20 to reflect the work for Tactile Ground Surface indicators under the Platform Gap Mitigation program.
Shepparton Corridor Upgrade – Stage 1 (Shepparton) | 32654 | 3264.3 | 29388.7 | 1 | qtr 2 2022-23
TEI excludes $0.346 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. The estimated completion date has been revised due to the delivery of the crossing loop being included as part of Shepparton Corridor Upgrade – Stage 2. Project name changed from ’Shepparton line upgrade and additional services’ published in the 2018-19 Budget.
Shepparton Corridor Upgrade – Stage 2 (Shepparton) | 312487 | 10384 | 18500 | 283603 | qtr 2 2022-23
TEI excludes $0.422 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards. Project name changed from ’Shepparton Line Upgrade – Stage 2’ published in 2018-19 Budget. The estimated completion date has been revised due to the packaging of the Gippsland-Shepparton-Bendigo alliance.
South Yarra Station upgrade (South Yarra) | 12326 | 1246.1 | 11079.9 | 0 | qtr 4 2019-20
The estimated completion date has been revised to quarter 4 2019-20 to reflect delays experienced in the contractual lease negotiations.
Sustaining the V/Line train fleet (regional various) | 23062 | 10599.8 | 12462.2 | 0 | qtr 4 2019-20
Ticketing Systems Services Agreement (TSSA) (statewide) | 68500 | 15977 | 16873 | 35650 | qtr 4 2022-23
Train station car parking (statewide) | 71799.8 | 4337.9 | 37473.9 | 29988 | qtr 2 2020-21
TEI has increased by $11.800 million due to funding received from the Growth Area Infrastructure Contribution to commence works on Sunbury Station car park expansion and the Cranbourne Station car park expansion. The estimated completion date has been revised to quarter 2 2020-21 to reflect revisions to the delivery schedule.
Tram procurement and supporting infrastructure (metropolitan various) | 804205.4 | 700786.6 | 68933.2 | 34485.5 | qtr 4 2021-22
TEI has reduced by $0.250 million due to savings. The estimated completion date has been revised to quarter 4 2021-22 due to remediation works and the availability of land for substation sites.
Wyndham Vale Stabling Yard (regional various) | 172900 | 82936.1 | 76574.5 | 13389.4 | qtr 3 2019-20
Project name changed from ’Regional rail infrastructure and new regional trains’ published in 2018-19 Budget.
Total existing projects | 22257366.4 | 9915700.5 | 3940569.7416 | 8401096
Total Transport projects | 27430955.4 | 9944250.5 | 4625976.7416 | 12610728
Other capital expenditure | na | na |  | na | various
Total 2019-20 Transport capital expenditure
Source: Department of Transport
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Additional X’Trapolis trains (metropolitan various) | 97370.5 | 87882.4 | qtr 4 2020-21
TEI has reduced by $0.500 million due to savings.
Frankston Station Precinct Development (Frankston) | 61760 | 60871 | qtr 2 2020-21
Hurstbridge rail line upgrade (metropolitan various) | 135905 | 135905 | qtr 1 2020-21
Mernda rail extension project (Mernda) | 603027.4 | 591538.3 | qtr 1 2020-21
TEI has been reduced by $0.024 million due to savings and $1.063 million due to certain expenditure being recognised as operating instead of capital, in line with accounting standards.
Mernda stabling and Broadmeadows government land purchase (Melbourne) | 10650 | 10650 | qtr 2 2020-21
TEI has decreased by $0.400 million due to savings.
Estimated to be completed after publication date and before 30 June 2019
Bendigo and Eaglehawk station upgrades (Bendigo) | 15800 | 15800 | qtr 4 2019-20
Nine additional X’Trapolis trains (metropolitan various) | 174637 | 147553.1 | qtr 4 2021-22
TEI has reduced by $0.363 million due to savings.
Railway Station Car Parking Fund (statewide) | 19920 | 19919.7 | qtr 4 2019-20
Regional rail sustainability (statewide) | 7500 | 7500 | qtr 4 2018-19
Source: Department of Transport
Victorian Regional Channels Authority
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Polyethene buoys (Hastings) | 2016 | 1916 | 100 | 0 | qtr 1 2019-20
Total existing projects | 2016 | 1916 | 100 | 0
Total Victorian Regional Channels Authority projects | 2016 | 1916 | 100 | 0
Source: Victorian Regional Channels Authority
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Port monitoring equipment (Geelong) | 963 | 963 | qtr 4 2018-19
Channel improvements (regional various) was listed as a new project in last year’s budget, but will now be treated as an operating expense and so will not incur the capital expenditure forecasted last year.
Source: Victorian Regional Channels Authority
Wannon Region Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Water reclamation plant effluent reuse upgrade (Hamilton) | 2966.85 | 0 | 156.15 | 2810.7 | qtr 4 2021-22
Water treatment plant UV disinfection system (Warrnambool) | 5475.66 | 0 | 208.2 | 5267.46 | qtr 4 2021-22
All remaining projects with a TEI less than $1 million | 4841.287 | 0 | 3409.913 | 1431.374 | various
Total new projects | 13283.797 | 0 | 3774.263 | 9509.534
Source: Wannon Region Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Carbon reduction program (regional various) | 2390.825 | 17.345 | 1368.915 | 1004.565 | ongoing
Improve summer flows in Gellibrand River (Gellibrand) | 1884.21 | 0 | 988.95 | 895.26 | qtr 4 2021-22
New clear water storage (Hamilton) | 1353.3 | 64.1 | 1289.2 | 0 | qtr 4 2019-20
New drying area (Hamilton) | 3260.22 | 2364.96 | 895.26 | 0 | qtr 4 2019-20
Refurbish biosolids facility (Camperdown) | 2862.75 | 169.895 | 1974.565 | 718.29 | qtr 4 2020-21
Previously unbudgeted project started in 2018-19.
Replacement vehicles – commercial (regional various) | 4240.188 | 642.401 | 570.49 | 3027.297 | ongoing
Replacement vehicles – passenger (regional various) | 1523.205 | 238.828 | 188.134 | 1096.243 | ongoing
Servicing of the 12 Apostles visitor centre – sewer and water (Port Campbell) | 5800 | 1800 | 4000 | 0 | qtr 4 2019-20
Sewer pump station renewals (regional various) | 1990.491 | 128.824 | 370.859 | 1490.808 | ongoing
Sewers and manholes (regional various) | 12487.296 | 1716.58 | 1768.813 | 9001.903 | ongoing
Project name change from 'individual towns' to 'regional various' due to consolidation of projects.
Upgrade end of life SCADA RTU (regional various) | 3643.5 | 102.918 | 417.582 | 3123 | qtr 4 2021-22
Previously unbudgeted project started in 2018-19.
Wangoom Road water tower and water pump station (Warrnambool) | 4417.743 | 27.718 | 746.525 | 3643.5 | qtr 4 2021-22
Water main replacements (regional various) | 6875.898 | 931.241 | 944.741 | 4999.916 | ongoing
Project name change from 'individual towns' to 'regional various' due to consolidation of projects.
Water pump station renewals (regional various) | 1973.362 | 102.717 | 329.036 | 1541.609 | ongoing
Water reclamation plant – augmentation (Warrnambool) | 38725.2 | 728.7 | 15615 | 22381.5 | qtr 4 2021-22
Water reclamation plant renewals (regional various) | 5843.486 | 295.593 | 1373.504 | 4174.389 | ongoing
Project name change from 'individual towns' to 'regional various' due to consolidation of projects.
Water storages renewal (regional various) | 2863.644 | 334.074 | 366.021 | 2163.549 | ongoing
Water transfer pipe renewals (regional various) | 2170.918 | 0 | 515.234 | 1655.684 | ongoing
Water treatment plant renewals (regional various) | 2875.102 | 218.202 | 488.942 | 2167.958 | ongoing
Project name change from 'individual towns' to 'regional various' due to consolidation of projects.
Wollaston Road sewer pump station and water tower (Warrnambool) | 4078 | 1525 | 0 | 2553 | qtr 4 2021-22
Project partially complete with estimated completion date deferred to 2022.
All remaining projects with a TEI less than $1 million | 21629.619 | 3471.585 | 8327.454 | 9830.58 | various
Total existing projects | 132888.957 | 14880.681 | 42539.225 | 75469.051
Total Wannon Region Water Corporation projects | 146172.754 | 14880.681 | 46313.488 | 84978.585
Source: Wannon Region Water Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
LAN/WAN equipment replacement (regional various) | 1264 | 1264 | qtr 4 2018-19
Meter replacement program (regional various) | 2216 | 2216 | qtr 4 2018-19
Replacement minor plant (regional various) | 1114 | 1114 | qtr 4 2018-19
Server infrastructure renewal (Warrnambool) | 3549 | 3549 | qtr 4 2018-19
Sewer pump station emergency storage tank (Port Campbell) | 1267.698 | 1267.698 | qtr 4 2018-19
Previously recorded in ’All remaining projects with a TEI less than $1 million’.
Wind energy project (Portland) | 4184 | 4184 | qtr 4 2018-19
All remaining projects with a TEI less than $1 million | 8354.673 | 8354.673 | various
Source: Wannon Region Water Corporation
Western Region Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Bacchus Marsh recycled water plant – aeration works – Lagoon 1 (Bacchus Marsh) | 1670.795 | 0 | 0 | 1670.795 | qtr 4 2022-23
Bacchus Marsh recycled water plant – aeration works – Lagoon 2 (Bacchus Marsh) | 1709.224 | 0 | 0 | 1709.224 | qtr 4 2023-24
Bacchus Marsh recycled water plant – aeration works – Lagoon 3 (Bacchus Marsh) | 1748.537 | 0 | 0 | 1748.537 | qtr 4 2024-25
Bacchus Marsh recycled water plant – inlet works upgrade (Bacchus Marsh) | 5710.636 | 0 | 0 | 5710.636 | qtr 4 2023-24
Bacchus Marsh recycled water plant – reline primary pond No. 1 (Bacchus Marsh) | 3384.6 | 0 | 0 | 3384.6 | qtr 4 2022-23
Bacchus Marsh recycled water plant – reline primary pond No. 2 (Bacchus Marsh) | 3565.612 | 0 | 0 | 3565.612 | qtr 4 2024-25
Bacchus Marsh recycled water plant – reline primary pond No. 3 (Bacchus Marsh) | 1957.711 | 0 | 0 | 1957.711 | qtr 4 2025-26
Cathodic protection renewals 2020-21 to 2024-25 (metro various) | 1294.151 | 0 | 244.5736 | 1049.5774 | qtr 4 2024-25
Deanside Drive sewer pump station stage 1 (Rockbank) | 5278.543 | 0 | 0 | 5278.543 | qtr 4 2025-26
Emu Creek branch sewer main (Emu Creek) | 3256.823 | 0 | 0 | 3256.823 | qtr 4 2024-25
Gisborne recycled water plant – stage 1 new aeration basin with power upgrade works (Gisborne) | 7499.518 | 0 | 0 | 7499.518 | qtr 4 2022-23
Gisborne recycled water plant – stage 1 convert maturation pond 1 (Gisborne) | 1240.338 | 0 | 61.2 | 1179.138 | qtr 4 2020-21
Hardware – storage array network (Sunbury) | 1053.98 | 0 | 408 | 645.98 | qtr 4 2025-26
Lancefield Road water main (Sunbury) | 2340.78 | 0 | 0 | 2340.78 | qtr 4 2024 -25
Magnet Hill to Riddells Creek transfer main 300 mm (metro various) | 2510.535 | 0 | 0 | 2510.535 | qtr 4 2024 -25
Melton recycled water plant – convert aeration tanks 5 and 6 to IFAS (Melton) | 1654.579 | 0 | 0 | 1654.579 | qtr 4 2021-22
Melton recycled water plant western irrigation network pump station stage 1 (Melton) | 4874.836 | 0 | 428.7601 | 4446.0759 | qtr 4 2021-22
Mount Atkinson north sewer (Melton) | 1194.568 | 0 | 1190 | 4.568 | qtr 1 2020-21
Parwan-Balliang irrigation district network (Bacchus Marsh) | 16570.354 | 0 | 1020 | 15550.354 | qtr 4 2024-25
Parwan-Balliang irrigation district pump station (Bacchus Marsh) | 5651.058 | 0 | 0 | 5651.058 | qtr 4 2023-24
Parwan-Balliang irrigation district storage (Bacchus Marsh) | 5178.991 | 0 | 0 | 5178.991 | qtr 4 2023-24
Parwan-Balliang irrigation district tank western irrigation network (Bacchus Marsh) | 3993.408 | 0 | 0 | 3993.408 | qtr 4 2023-24
Riddells Creek recycled water plant – inlet works upgrade (Riddells Creek) | 1625.762 | 0 | 0 | 1625.762 | qtr 4 2022-23
Romsey recycled water plant upgrade – stage 1 – lagoon remediation (Romsey) | 1300.713 | 0 | 158.1 | 1142.613 | qtr 4 2020-21
Romsey water filtration plant decommissioning (Romsey) | 1683.565 | 0 | 0 | 1683.565 | qtr 4 2024-25
Rosslynne water filtration plant asset replacements (Rosslynne) | 1990.639 | 0 | 0 | 1990.639 | qtr 4 2023-24
Rosslynne water filtration pump – sludge–drying beds (Rosslynne) | 1075.023 | 0 | 0 | 1075.023 | qtr 4 2022-23
Sunbury Road water main (Sunbury) | 1484.788 | 0 | 0 | 1484.788 | qtr 4 2024 -25
Sunbury recycled water plant to Melton recycled water plant interconnector pipeline (Sunbury) | 1333.004 | 0 | 0 | 1333.004 | qtr 4 2028 -29
Supervisory control and data acquisition – telemetry upgrade 2020-2021 to 2024-2025 (metro various) | 2605.473 | 0 | 0 | 2605.473 | qtr 4 2024-25
Sutherlands Road sewer pump station rising main upgrade (Riddells Creek) | 1815.918 | 0 | 177.9076 | 1638.0104 | qtr 4 2020-21
Transfer and raw water pipeline renewals program 2025-26 to 2029-30 (metro various) | 1355.338 | 0 | 0 | 1355.338 | qtr 4 2028-29
Woodend recycled water plant wet weather storage (Woodend) | 1067.49 | 0 | 0 | 1067.49 | qtr 4 2021-22
All remaining projects with a TEI less than $1 million | 46585.138 | 0 | 4237.6776 | 42347.4604 | various
Total new projects | 147262.428 | 0 | 7926.2189 | 139336.2091
Source: Western Region Water Corporation
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Aitken Street upgrade (metro various) | 2793.617 | 0 | 0 | 2793.617 | qtr 4 2024-25
Alfred Road sewer pump station (Melton) | 1341.234 | 0 | 0 | 1341.234 | qtr 4 2024-25
Bacchus Marsh recycled water plant groundwater improvements (Bacchus Marsh) | 2810.224 | 0 | 54.876 | 2755.348 | qtr 4 2024-25
Bacchus Marsh rising main – Woolpack Road-parwan recycled water plant (Bacchus Marsh) | 6014.851 | 2.639 | 925.752 | 5086.46 | qtr 4 2021-22
Bald Hill tank construction (metro various) | 7004.59 | 0 | 0 | 7004.59 | qtr 4 2022-23
Bald Hill tank site purchase (Sunbury) | 1675.824 | 198.697 | 62.363 | 1414.764 | qtr 4 2020-21
Bald Hill tank to Diggers Rest water main (Diggers Rest) | 1661.646 | 0 | 373.543 | 1288.103 | qtr 4 2022-23
Bald Hill to Diggers Rest water main (metro various) | 2773.062 | 0 | 0 | 2773.062 | qtr 4 2023-24
Bald Hill transfer main (Sunbury) | 1497.139 | 0 | 0 | 1497.139 | qtr 4 2021-22
Beattys Road east trunk water main (Melton) | 1282.061 | 0 | 40.8 | 1241.261 | qtr 4 2024-25
Beattys Road recycled water main (Melton) | 3322.358 | 0 | 0 | 3322.358 | qtr 4 2023-24
Beattys Road water main (Melton) | 4727.234 | 0 | 40.8 | 4686.434 | qtr 4 2024-25
Bridge Road water main extension (Melton) | 1371.387 | 1061.276 | 310.111 | 0 | qtr 4 2019-20
Buckland Way sewer pump station (Sunbury) | 1682.653 | 0 | 0 | 1682.653 | qtr 4 2022-23
Buckland Way sewer pump station rising main (Sunbury) | 1211.879 | 0 | 0 | 1211.879 | qtr 4 2022-23
Business intelligences phase 4 – optimisation of asset management and plant operations (metro various) | 1402.636 | 190.863 | 408 | 803.773 | qtr 4 2024-25
Customer water meters replacement program 2018-19 to 2022-23 (metro various) | 2584.829 | 301.331 | 570.672 | 1712.826 | qtr 4 2024-25
Customer water meters replacement program 2023-24 to 2027-28 (metro various) | 1265.571 | 0 | 0 | 1265.571 | qtr 4 2024-25
Davis Road estate main stage 1 (Diggers Rest) | 1474.742 | 870.43 | 0 | 604.312 | qtr 4 2023-24
Derrimut interceptor rising main (Melton) | 4024.903 | 0 | 102 | 3922.903 | qtr 4 2023-24
Diggers Rest pump station trunk water main (Diggers Rest) | 4995.053 | 2569.551 | 2425.502 | 0 | qtr 4 2019-20
Emu Creek branch sewer main (Emu Creek) | 2791.994 | 0 | 0 | 2791.994 | qtr 4 2024-25
Enterprise document management system (metro various) | 1051.442 | 794.096 | 153 | 104.346 | qtr 4 2020-21
Exford Road sewer extension (Melton) | 1360.36 | 1273.413 | 48.542 | 38.405 | qtr 4 2020-21
Ferris Road freeway crossing water main (Melton) | 2701.557 | 2100.114 | 601.443 | 0 | qtr 4 2019-20
Ferris Road south water main (Melton) | 1358.612 | 0 | 0 | 1358.612 | qtr 4 2024-25
Geelong Bacchus Marsh water main (Bacchus Marsh) | 1167.9 | 0 | 33.859 | 1134.041 | qtr 4 2022-23
Geelong Road – sewer rising main Grant Street to Woolpack Road (Bacchus Marsh) | 4130.022 | 973.649 | 2634.643 | 521.73 | qtr 4 2020-21
Gisborne recycled water plant – mechanical dewatering (Gisborne) | 6330.68 | 216.301 | 2655.57 | 3458.809 | qtr 4 2020-21
Gisborne recycled water plant – stage 1 bioreactor (Gisborne) | 5837.132 | 0 | 52.938 | 5784.194 | qtr 4 2023-24
Gisborne recycled water plant – stage 1 inlet works (Gisborne) | 4443.352 | 0 | 52.938 | 4390.414 | qtr 4 2023-24
Grant Street sewer pump station upgrade (Bacchus Marsh) | 4263.868 | 470.526 | 2982.305 | 811.037 | qtr 4 2020-21
Hillside pump station – capacity increase (Hillside) | 1088.362 | 0 | 0 | 1088.362 | qtr 4 2023-24
Holden outlet main (metro various) | 1759.988 | 0 | 102 | 1657.988 | qtr 4 2021-22
House connection branch rehabilitation program 2018-19 to 2022-23 (metro various) | 1951.551 | 218.263 | 333.548 | 1399.74 | qtr 4 2024-25
IT hardware renewals (metro various) | 1277.363 | 0 | 164.322 | 1113.041 | qtr 4 2024-25
IT systems hardware renewals (metro various) | 1222.752 | 147.754 | 263.16 | 811.838 | qtr 4 2024-25
Intelligent network program 2018-19 to 2022-23 (metro various) | 1937.319 | 65.973 | 612 | 1259.346 | qtr 4 2022-23
Intelligent network program 2023-24 to 2027-28 (metro various) | 1359.113 | 0 | 0 | 1359.113 | qtr 4 2024-25
Intelligent water network waternamics programm (metro) | 2557.258 | 2144.324 | 182.792 | 230.142 | qtr 4 2023-24
Kororoit Creek main sewer No.1 (Melton) | 3269.678 | 0 | 0 | 3269.678 | qtr 4 2024-25
Kororoit Creek main sewer No.3 (Melton) | 2354.845 | 0 | 0 | 2354.845 | qtr 4 2024-25
Kororoit Creek main sewer No.4 (Melton) | 1223.84 | 0 | 0 | 1223.84 | qtr 4 2024-25
Kororoit Creek north branch sewer – stage 1 (Melton) | 1207.681 | 0 | 306 | 901.681 | qtr 4 2023-24
Land development system replacement (metro various) | 2380.527 | 140.874 | 0 | 2239.653 | qtr 4 2023-24
Land sewer (Melton) | 1385.211 | 0 | 1020 | 365.211 | qtr 4 2020-21
Magnet Hill to Riddells Creek transfer main (metro various) | 2189.99 | 0 | 103.938 | 2086.052 | qtr 4 2024-25
Master planning – catchment mass balance – water pricing period 4 (metro various) | 1088.312 | 0 | 399.682 | 688.63 | qtr 4 2022-23
Master planning – network sewer (metro various) | 2827.883 | 0 | 270.3 | 2557.583 | qtr 4 2022-23
Master planning – treatment plants 2018-19 to 2022-23 (metro various) | 1634.207 | 10.446 | 280.5 | 1343.261 | qtr 4 2022-23
Melbourne Lancefield Road water main (Sunbury) | 1894.398 | 0 | 0 | 1894.398 | qtr 4 2024-25
Melbourne Water – Merrimu supply connection (metro various) | 5149.503 | 0 | 21.632 | 5127.871 | qtr 4 2023-24
Melbourne to Melton water main duplication (metro various) | 1693.564 | 0 | 0 | 1693.564 | qtr 4 2021-22
Melton South Exford Road sewer pump station (Melton) | 4509.122 | 787.14 | 0 | 3721.982 | qtr 4 2024-25
Melton South Exford Road sewer pump station rising main (Melton) | 2144.537 | 0 | 40.511 | 2104.026 | qtr 4 2021-22
Melton recycled water plant – new belt-press (Melton) | 2080.436 | 313.221 | 1081.14 | 686.075 | qtr 4 2020-21
Melton recycled water plant – treatment upgrade and balancing storage (Melton) | 19251.45 | 877.075 | 2469.633 | 15904.742 | qtr 4 2022-23
Melton recycled water plant and Bacchus Marsh recycled water plant interconnection (metro various) | 14168.512 | 1078.485 | 5058.466 | 8031.561 | qtr 4 2021-22
Melton recycled water plant upgrade – additional PST3 and pumping (Melton) | 3762.544 | 0 | 204 | 3558.544 | qtr 4 2021-22
Melton recycled water plant upgrade – SST4 and inlet channel 3 fit out (Melton) | 6405.563 | 0 | 0 | 6405.563 | qtr 4 2024-25
Melton recycled water plant upgrade – additional waste activated sludge pumping and storage (Melton) | 2928.092 | 0 | 0 | 2928.092 | qtr 4 2024-25
Melton waste to energy facility (Melton) | 2706.481 | 356.024 | 2350.457 | 0 | qtr 4 2019-20
Merrimu water filtration plant – fluoride upgrade (Melton) | 2286.928 | 350 | 306 | 1630.928 | qtr 4 2020-21
Merrimu water filtration plant – upgrade filter (Melton) | 1587.498 | 0 | 0 | 1587.498 | qtr 4 2024-25
Motor vehicles program 2018-19 to 2022-23 (metro various) | 4391.585 | 830.035 | 663 | 2898.55 | qtr 4 2022-23
Motor vehicles program 2023-24 to 2027-28 (metro various) | 2157.314 | 0 | 0 | 2157.314 | qtr 4 2024-25
Mount Atkinson main trunk sewer (Melton) | 1254.6 | 0 | 1254.6 | 0 | qtr 4 2019-20
Myrniong transfer water main (Myrniong) | 5168.029 | 0 | 0 | 5168.029 | qtr 4 2024-25
New Gisborne sewer pump station, rising main and sternway connection (Gisborne) | 1249.5 | 0 | 62.623 | 1186.877 | qtr 4 2021-22
Northern trunk sewer duplication (Bacchus Marsh) | 3372.082 | 179.518 | 3159.349 | 33.215 | qtr 4 2020-21
Office accommodation fitout (metro various) | 1925.967 | 2.377 | 0 | 1923.59 | qtr 4 2022-23
Optimisation of asset management (metro various) | 1482.761 | 462.761 | 1020 | 0 | qtr 4 2019-20
Peacock Court sewer main No.2 (Melton) | 1059.406 | 0 | 510 | 549.406 | qtr 4 2020-21
Plant and equipment renewal program 2018-19 to 2022-23 (metro various) | 1535.948 | 296.142 | 306.159 | 933.647 | qtr 4 2022-23
Project management tool (metro various) | 1660.032 | 657.845 | 204 | 798.187 | qtr 4 2024-25
Provision for support to land development and third party projects (Melton) | 1802.894 | 0 | 1020 | 782.894 | qtr 4 2024-25
Raising Campaspe reservoir (Woodend) | 1759.038 | 0 | 0 | 1759.038 | qtr 4 2024-25
Recycled water plants – 100kW solar PV installation (Melton) | 1404.51 | 435.104 | 969.406 | 0 | qtr 4 2019-20
Replace 375mm main from water filtration plant to Minns Road (Melton) | 7303.092 | 0 | 0 | 7303.092 | qtr 4 2024-25
Riddells Creek recycled water plant offset (Riddells Creek) | 1364.546 | 28.108 | 123.267 | 1213.171 | qtr 4 2024-25
Riddells Road pump station (Sunbury) | 3959.222 | 11.549 | 375.879 | 3571.794 | qtr 4 2021-22
Rockbank Road south water main (Rockbank) | 3600.92 | 0 | 0 | 3600.92 | qtr 4 2021-22
Romsey recycled water plant upgrade – 1.2 ML/day (Romsey) | 1309.125 | 0 | 0 | 1309.125 | qtr 4 2021-22
Romsey recycled water scheme land purchase 2 and irrigation infrastructure (Romsey) | 1309.046 | 57.042 | 1247.256 | 4.748 | qtr 4 2020-21
Rosslynne to Aitken Street transfer main (metro various) | 3807.204 | 0 | 51.969 | 3755.235 | qtr 4 2024-25
Sewage pump station renewals program 2023-24 to 2027-28 (Gisborne) | 2020.624 | 0 | 0 | 2020.624 | qtr 4 2024-25
Sewer pump station to Derrimut interceptor (Melton) | 5073.848 | 0 | 102 | 4971.848 | qtr 4 2022-23
Sewer spill prevention strategy – sewer relining program 2018-19 to 2022-23 (metro various) | 14640.992 | 1500 | 2937.6 | 10203.392 | qtr 4 2024-25
Sewer spill prevention strategy – sewer relining program 2023-24 to 2027-28 (metro various) | 4241.434 | 0 | 0 | 4241.434 | qtr 4 2024-25
Sewer spill prevention strategy CCTV survey program 2018-19 to 2022-23 (metro various) | 2180.548 | 494.614 | 369.95 | 1315.984 | qtr 4 2024-25
Sewer spill prevention strategy CCTV survey program 2023-24 to 2027-28 (metro various) | 1468.967 | 0 | 0 | 1468.967 | qtr 4 2024-25
Sewer spill prevention strategy maintenance hole rehabilitation program 2018-19 to 2022-23 (metro various) | 1375.845 | 203.108 | 269.506 | 903.231 | qtr 4 2024-25
Sunbury Road main outfall sewer (Sunbury) | 3290.406 | 0 | 0 | 3290.406 | qtr 4 2023-24
Sunbury outfall sewer duplication (Sunbury) | 3636.166 | 536.824 | 306 | 2793.342 | qtr 4 2020-21
Sunbury recycled water plant – provision for maintenance under contract (Sunbury) | 1262.356 | 41 | 115.26 | 1106.096 | qtr 4 2024-25
Surbiton Park recycled water plant – convert aeration tank 1 to intergraded fixed-film activated sludge (Melton) | 2001.98 | 0 | 0 | 2001.98 | qtr 4 2024-25
Tame Street sewer pump station upgrade (Diggers Rest) | 1501.367 | 1501.367 | 0 | 0 | qtr 2 2019-20
Taylors Road water main (Melton) | 1454.52 | 0 | 1454.52 | 0 | qtr 4 2019-20
Taylors Road water main – linking Plumpton and Rockbank North (Melton) | 1348.051 | 0 | 0 | 1348.051 | qtr 4 2022-23
Toolern – western waterford sewer (Melton) | 1131.059 | 0 | 0 | 1131.059 | qtr 4 2024-25
Toolern Creek outfall sewer No.1 (Melton) | 1085.66 | 0 | 0 | 1085.66 | qtr 4 2022-23
Toolern Creek outfall sewer No.8 (Melton) | 1195.197 | 0 | 0 | 1195.197 | qtr 4 2023-24
Toolern stormwater harvesting (Melton) | 1640.14 | 1640.14 | 0 | 0 | qtr 1 2019-20
Transfer and raw water pipeline renewals program 2023-24 to 2027-28 (metro various) | 5257.125 | 0 | 0 | 5257.125 | qtr 4 2024-25
Treated water pump station renewals program 2023-24 to 2027-28 (metro various) | 1787.111 | 0 | 0 | 1787.111 | qtr 4 2024-25
Treatment plant automation and robotics program (metro various) | 5821.266 | 0 | 374.177 | 5447.089 | qtr 4 2024-25
Western Water online phase 2 (metro various) | 2043.005 | 573.051 | 0 | 1469.954 | qtr 4 2024-25
Western irrigation network (Melton) | 1244.748 | 1244.748 | 0 | 0 | qtr 2 2019-20
Western irrigation network – full business case (Melton) | 1423.58 | 1423.58 | 0 | 0 | qtr 2 2019-20
Western tank pump station (metro various) | 3988.982 | 120 | 306 | 3562.982 | qtr 4 2021-22
Wet weather flow diversion sewer pump station (Melton) | 5434.912 | 2858.9 | 1975.744 | 600.268 | qtr 4 2020-21
Woodend recycled water plant – upgrade phase 2 – dewatering facility (Woodend) | 5007.371 | 196.521 | 2323.815 | 2487.035 | qtr 4 2020-21
Woodend recycled water plant construct clarifier (Woodend) | 2749.83 | 0 | 71.02 | 2678.81 | qtr 4 2022-23
Woodlea Estate water main (Melton) | 3300 | 3300 | 0 | 0 | qtr 2 2019-20
Woodlea sewer pump station rising main stage 1 (Melton) | 3552.438 | 3552.438 | 0 | 0 | qtr 1 2019-20
Woodlea-Kororoit link water main (Melton) | 1467.657 | 1467.657 | 0 | 0 | qtr 2 2019-20
All remaining projects with a TEI less than $1 million | 138602.295 | 0 | 22976.715 | 115625.58 | various
There are many projects listed in last year’s budget that are not listed this year as they either have not progressed to final approval and commencement stage, or the TEI is now less than $1 million. Additionally, as Western Water adopt an adaptive planning approach, this results in potentially large changes to the capital program as strategies are reviewed with regard to updated information. This may also result in significant change to project TEIs as scope and costs are revised.
Total existing projects | 480745.221 | 41126.894 | 74649.553 | 364968.774
Total Western Region Water Corporation projects | 628007.649 | 41126.894 | 82575.7719 | 504304.9831
Source: Western Region Water Corporation
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Exford waters seventh bend branch sewer (Melton) | 2012.286 | 2012.286 | qtr 4 2018-19
Gisborne recycled water plant filtration and disinfection (Gisborne) | 2216.728 | 2216.728 | qtr 4 2018-19
Leakes Road trunk water main (Melton) | 6204.335 | 6204.335 | qtr 4 2018-19
Melton recycled water plant upgrade – stage 3 (metro various) | 9831.219 | 9831.219 | qtr 4 2018-19
Paynes Road Plumpton structure plant sewer pump station (Melton) | 3905.355 | 3905.355 | qtr 4 2018-19
Recycled water plants – rectification of cogeneration facility (Surbiton Park) | 1237.69 | 1237.69 | qtr 4 2018-19
Rockbank Road 450 water main for Mt Atkinson (Rockbank) | 4840 | 4840 | qtr 4 2018-19
Rockbank South sewer and Troups Road sewer pump station decommissioning (Rockbank) | 1457.657 | 1457.657 | qtr 4 2018-19
Rockbank outfall sewer rising main (Rockbank) | 4608.212 | 4608.212 | qtr 4 2018-19
Romsey recycled water scheme land purchase (Romsey) | 3027.247 | 3027.247 | qtr 4 2018-19
Sewer spill prevention strategy sewer relining program FY17/18 (metro various) | 2014.712 | 2014.712 | qtr 4 2018-19
Sunbury recycled water plant upgrade (Sunbury) | 37900.29 | 37900.29 | qtr 4 2018-19
Taylors Road – water and recycled water mains (Melton) | 2193.332 | 2193.332 | qtr 4 2018-19
Thornhill Park sewer main package 2 (Thornhill) | 1413.324 | 1413.324 | qtr 4 2018-19
Thornhill Park stage 13 branch sewers (Thornhill) | 2305.777 | 2305.777 | qtr 4 2018-19
Troups Road branch sewer (Rockbank) | 1219.308 | 1219.308 | qtr 4 2018-19
Water filtration plant clear water storage rehabilitation (Gisborne) | 1483.099 | 1483.099 | qtr 4 2018-19
Woodlea precinct 3 sewer (Woodlea) | 2426.852 | 2426.852 | qtr 4 2018-19
All remaining projects with a TEI less than $1 million | 6450.91 | 6450.91 | qtr 4 2018-19
Source: Western Region Water Corporation
Westernport Region Water Corporation
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Ian Bartlett water purification plant civil, mechanical and electrical works (Almurta) | 1115.024 | 327.295 | 146.721 | 641.008 | ongoing
King Road master plan (Corinella) | 2013.283 | 0 | 0 | 2013.283 | qtr 4 2023-24
San Remo to Newhaven bridge pipeline and fittings renewal project (San Remo and Newhaven) | 1009.601 | 0 | 0 | 1009.601 | ongoing
Zone metering and pressure management program (regional various) | 1087.669 | 40.276 | 258.11 | 789.283 | ongoing
Total new projects | 5225.577 | 367.571 | 404.831 | 4453.175
Source: Westernport Region Water Corporation
Existing projects (a)
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Business transformation project (Newhaven) | 3263.079 | 660.616 | 2602.463 | 0 | qtr 4 2019-20
Project TEI has increased due to an expanded project scope.
Phillip Island water supply security project (Wimbledon Heights) | 2916.213 | 148.661 | 2767.552 | 0 | qtr 4 2019-20
Plant replacement fleet and equipment 2018-2024 (regional various) | 2368.28 | 567.159 | 398.211 | 1402.91 | ongoing
San Remo basin renewal project (San Remo) | 2219.262 | 0 | 0 | 2219.262 | qtr 4 2023-24
Sewer junction rebuild program (regional various) | 1377.313 | 218.689 | 193.598 | 965.026 | ongoing
Project completion time extended due to expanded project scope.
Sewer pump stations electrical switchboard renewal program (regional various) | 1271.811 | 244.56 | 0 | 1027.251 | ongoing
Project completion date extended due to expanded project scope.
Waste water treatment plant upgrade stage 2 (Cowes) | 3589.54 | 17.234 | 179.477 | 3392.829 | qtr 4 2021-22
Water main replacement program 2018-2024 (regional various) | 3056.632 | 692.158 | 121.273 | 2243.201 | qtr 4 2023-24
Project TEI has increased due to an expanded project scope and timeframe.
Water quality compliance program (Almurta) | 1144.911 | 875.874 | 69.037 | 200 | ongoing
All remaining projects with a TEI less than $1 million | 12303.612 | 3039.385 | 1995.379 | 7268.848 | qtr 4 2025-26
Total existing projects | 33510.653 | 6464.336 | 8326.99 | 18719.327
Total Westernport Region Water Corporation projects | 38736.23 | 6831.907 | 8731.821 | 23172.502
Source: Westernport Region Water Corporation
Note: -
(a) The project 'King Road storage lagoon (Corinella) from the 2018-19 Budget has been discontinued and is currently under a feasibility review.
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
All remaining projects with a TEI less than $1 million | 1660.941 | 1660.941 | qtr 4 2018-19
Source: Westernport Region Water Corporation
Yarra Valley Water Corporation
Existing projects(a)(b)
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Community sewerage (metropolitan various) | 114197.469 | 22270 | 19000 | 72927.469 | ongoing
Facilities (Mitcham) | 5901.362 | 1221.888 | 1233 | 3446.474 | ongoing
Information Technology – infrastructure (Mitcham) | 15036.349 | 4959.125 | 2515 | 7562.224 | ongoing
Project TEI has increased to reflect the transition of expenditure from capital investment to operating expenditure cloud–based solutions.
Information Technology – system improvement (Mitcham) | 37488.401 | 5100 | 8242 | 24146.401 | ongoing
Known base case IT expenditure included in current submission. Additional expenditure will be subject to business case approval.
Motor vehicle fleet (metropolitan various) | 11883.638 | 2670 | 2219 | 6994.638 | ongoing
Sewage treatment (metropolitan various) | 59296.151 | 9120 | 20203 | 29973.151 | ongoing
Sewer growth (Beveridge/Wallan) | 17300.1 | 625.6 | 1883 | 14791.5 | ongoing
Sewer growth (Craigieburn/ Mickleham/Kalkallo/Donnybrook) | 175292.1 | 34269.2 | 49016.3 | 92006.6 | ongoing
Sewer growth (Lalor/Epping/Epping North) | 29651.4 | 16257.6 | 4350.5 | 9043.3 | ongoing
Sewer growth (Mernda/Doreen) | 41031.6 | 5523.9 | 12942.4 | 22565.3 | ongoing
Sewer growth (metropolitan various) | 9472.6 | 857.6 | 1189.6 | 7425.4 | ongoing
Sewer house connection branch renewals (metropolitan various) | 47641.641 | 9650 | 9619 | 28372.641 | ongoing
Sewer improved system capacity (metropolitan various) | 42939.27 | 2510 | 6442 | 33987.27 | ongoing
Sewer main and branch renewals (metropolitan various) | 44396.619 | 15730 | 9720 | 18946.619 | ongoing
Sewer reliability (metropolitan various) | 55156.113 | 8239 | 10422 | 36495.113 | ongoing
Sewer reticulation renewals (metropolitan various) | 63169.842 | 12260 | 12260 | 38649.842 | ongoing
Water customer meter replacements (metropolitan various) | 13640.683 | 2380 | 3950 | 7310.683 | ongoing
Water distribution main renewals (metropolitan various) | 6306.019 | 972 | 1551 | 3783.019 | ongoing
Water growth (Beveridge/Wallan) | 24723.1 | 5877.2 | 5064 | 13781.9 | ongoing
Water growth (Craigieburn/ Mickleham/Kalkallo/Donnybrook) | 55634.2 | 11948.3 | 17482.9 | 26203 | ongoing
Water growth (Greenvale) | 2989.1 | 2311.3 | 677.8 | 0 | ongoing
Water growth (Lalor/Epping/Epping North) | 22827.6 | 3733.4 | 3209 | 15885.2 | ongoing
Water growth (Mernda/Doreen) | 17903.9 | 4198.9 | 5103 | 8602 | ongoing
Water growth (metropolitan various) | 7293 | 428.3 | 428.3 | 6436.4 | ongoing
Water improved quality (metropolitan various) | 34055.923 | 5700 | 6277 | 22078.923 | ongoing
Water main to meter renewals (metropolitan various) | 24916.108 | 4900 | 4900 | 15116.108 | ongoing
Water reliability (metropolitan various) | 47241.171 | 10110 | 9922 | 27209.171 | ongoing
Water reticulation main renewals (metropolitan various) | 126020.056 | 28330 | 28100 | 69590.056 | ongoing
Total existing projects | 1153405.515 | 232153.313 | 257921.8 | 663330.402
Total Yarra Valley Water Corporation projects | 1153405.515 | 232153.313 | 257921.8 | 663330.402
Source: Yarra Valley Water Corporation
Note -
(a) The project TEIs represent the draft 2019-20 Corporate Plan forecasts. Planned capital expenditure is driven by three key areas: 1) maintenance of customer levels through water and sewage renewals; 2) providing new water and sewerage services to growing suburbs; 3) meeting environmental and other obligations. The planned forecasts have been developed taking into account efficient capital expenditure, customer preferences, service levels and risk, which have resulted in project TEI variances when compared with the 2018-19 Budget Paper No. 4.
(b) The project 'Water conservation (metropolitan various) from the 2018-19 Budget is no longer included as the project's funding has been discontinued.
Other PNFCs
New projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
Building a world-class Geelong Performing Arts Centre (Geelong) | 128000 | .. | 15520 | 112480 | qtr 4 2022-23
Bringing the best sports and entertainment to Geelong (Geelong) | 2300 | .. | 2300 | .. | qtr 4 2021-22
State Sports Centre Trust – operational and capital funding (statewide) | 8434 | .. | 8434 | .. | qtr 4 2019-20
All remaining projects with a TEI less than $1 million | 1874.209 | 1394.385 | 479.824 | 0 | qtr 4 2019-20
Total new projects | 140608.209 | 1394.385 | 26733.824 | 112480
Source: Other PNFCs
Existing projects
($ thousand)
| Total estimated investment | Estimated expenditure to 30.06.2019 | Estimated expenditure 2019-20 | Remaining expenditure | Estimated completion date
2018-19 State Netball and Hockey Centre redevelopment (Parkville) | 62000 | 14393 | 38707 | 8900 | qtr 4 2020-21
Corn Hill road carpark (Mount Buller) | 1050 | 800 | 250 | 0 | qtr 2 2019-20
This project was previously included under ‘All remaining projects with a TEI less than $1 million’, and has since the previous State Budget process been re-forecast as having a TEI greater than $1 million.
Melbourne Park redevelopment stage three (Melbourne) | 271555 | 80786 | 108307 | 82462 | qtr 4 2021-22
The TEI includes funding of $40 million from the Melbourne and Olympic Parks Trust. The estimated completion date has been revised.
Melbourne Park redevelopment stage two (Melbourne) | 338121 | 326551 | 11570 | .. | qtr 2 2020-21
TEI includes funding of $40 million from the Melbourne and Olympic Parks Trust.
Mount Buller water storage (Mount Buller) | 8250 | 500 | 2000 | 5750 | qtr 2 2020-21
The TEI has been revised from $2.063 million to $8.25 million to reflect the additional scope that was funded in 2018-19.
Regional Tourism Infrastructure Fund: Enhancing Victoria’s world class nature based tourism destinations (statewide) | 66033 | 50670.604 | 13362.3963 | 1999.9997 | qtr 4 2020-21
This project has a total TEI of $66.033 million, comprising $7.8 million from Parks Victoria and $58.233 million from Phillip Island Nature Parks. The Parks Victoria project completion date has been extended to Q4 2020-21 due to a delay in planning approval and advice regarding environmental and heritage impact.
State Sports Centres Trust operational and capital funding (statewide) | 8951 | 8056 | 895 | .. | qtr 4 2019-20
The estimated completion date has been revised.
Tourism Railway Upgrades (metropolitan various) | 32000 | 4961 | 13240 | 13799 | qtr 4 2021-22
This includes $5.000 million of Commonwealth funding for the capital component of this initiative and includes funding from other sources.
All remaining projects with a TEI less than $1 million | 1064.307 | 817.545 | 246.762 | 0 | qtr 4 2019-20
Project TEI has been revised to align with the latest forecasts.
Total existing projects | 789024.307 | 487535.149 | 188578.1583 | 112910.9997
Total other public non-financial corporations projects | 929632.516 | 488929.534 | 215311.9823 | 225390.9997
Source: Other PNFCs
Completed projects
| Total estimated investment | Estimated expenditure to 30.06.2019 | Financial completion date
Arts Centre Melbourne building services upgrade (Melbourne) | 16439 | 16439 | qtr 2 2018-19
Roads and carparks (Mount Buller) | 1118 | 1107 | qtr 2 2018-19
All remaining projects with a TEI less than $1 milllion | 2105 | 2091.454 | qtr 4 2018-19
Project TEI has been revised to align with the latest forecasts.
Source: Other PNFCs